## PLANGRID
ID | FLATS | Task # | Stamp | Title | Description | Date | Status | Type | Sheet | Location | Root Cause | Created By | Assigned To | Watchers | # Photos | Color | Archived | Start Date | Due Date | Cost Impact | Cost Impact Amount | Schedule Impact | Schedule Impact Amount (days) | List | Last Updated | Closed On
1905F3 | 1905 | 23871 | F3 | F3 FAS Integration IR |  | Jun 01, 2026 @ 16:53 | closed | Issue | 1905_Main 1 Sub B C D E F |  |  | vivek.muralidharan@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jun 09, 2026 @ 09:13 | Jun 09, 2026 @ 09:13
3210D4 | 3210 | 23727 | D4 | D4 Intercom IR | Intercom IR | Apr 30, 2026 @ 04:00 | closed | Issue | 3210 _Main 1 Sub B C D E F | 202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:53 | Jul 22, 2026 @ 12:53
3210D2 | 3210 | 23726 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Apr 30, 2026 @ 04:00 | closed | Issue | 3210 _Main 1 Sub B C D E F | 202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:53 | Jul 22, 2026 @ 12:53
3109C2 | 3109 | 23713 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Apr 30, 2026 @ 04:00 | closed | Planned Work | 3109 _Main 1 Sub B C D E F |  |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 17:49 | Jul 20, 2026 @ 17:49
3109F3 | 3109 | 23699 | F3 | F3 FAS Integration IR | FAS Integration IR | Apr 30, 2026 @ 04:00 | closed | Planned Work | 3109 _Main 1 Sub B C D E F |  |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:27 | Jun 24, 2026 @ 12:27
3109F2 | 3109 | 23697 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Apr 30, 2026 @ 04:00 | closed | Planned Work | 3109 _Main 1 Sub B C D E F |  |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:27 | Jun 24, 2026 @ 12:27
1204C2 | 1204 | 23420 | C2 | C2 Gas Detector/FAS Integration IR |  | May 01, 2026 @ 17:13 | closed | Planned Work | 1204_Main 1 Sub B C D E F |  |  | abishek.govindan@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 03, 2026 @ 09:50 | May 03, 2026 @ 09:50
2002F3 | 2002 | 23417 | F3 | F3 FAS Integration IR |  | May 01, 2026 @ 15:40 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jul 17, 2026 @ 16:07 | Jul 17, 2026 @ 16:07
2002F2 | 2002 | 23416 | F2 | F2 Heat/Smoke Detector IR |  | May 01, 2026 @ 15:40 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jul 21, 2026 @ 15:54 | Jul 21, 2026 @ 15:54
2002D7 | 2002 | 23412 | D7 | D7 Booster IR |  | May 01, 2026 @ 15:40 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jun 02, 2026 @ 12:15 | Jun 02, 2026 @ 12:15
2002D4 | 2002 | 23409 | D4 | D4 Intercom IR |  | May 01, 2026 @ 15:39 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2002D2 | 2002 | 23407 | D2 | D2 ONU Panel/Data Points IR |  | May 01, 2026 @ 15:39 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jul 22, 2026 @ 17:52 | Jul 22, 2026 @ 17:52
2002C2 | 2002 | 23404 | C2 | C2 Gas Detector/FAS Integration IR |  | May 01, 2026 @ 15:39 | closed | Issue | 2002_Main 1 Sub B C D E F |  |  | mohammad.mujiburrahman@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified |  | Jul 22, 2026 @ 17:53 | Jul 22, 2026 @ 17:53
1909C2 | 1909 | 16951 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1909F2 | 1909 | 16946 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 12, 2026 @ 17:57 | May 12, 2026 @ 17:57
1909D7 | 1909 | 16944 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 12, 2026 @ 13:40 | May 12, 2026 @ 13:40
1909D4 | 1909 | 16942 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1909F3 | 1909 | 16939 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 12, 2026 @ 17:59 | May 12, 2026 @ 17:58
1909D2 | 1909 | 16931 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1309C2 | 1309 | 16922 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 04, 2026 @ 17:05 | Jun 04, 2026 @ 17:05
1309F2 | 1309 | 16917 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F | 1309 |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:41 | Apr 23, 2026 @ 12:41
1309D7 | 1309 | 16915 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:10 | Apr 22, 2026 @ 18:10
1309D4 | 1309 | 16913 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:10 | May 11, 2026 @ 12:10
1309F3 | 1309 | 16910 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:49 | Apr 23, 2026 @ 12:49
1309D2 | 1309 | 16902 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 1309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 08:18 | May 05, 2026 @ 08:18
3301F2 | 3301 | 16887 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 15, 2026 @ 13:13 | Jul 15, 2026 @ 13:13
3301D4 | 3301 | 16885 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3301D2 | 3301 | 16880 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 17:03 | Jul 27, 2026 @ 17:03
3301F3 | 3301 | 16877 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:29 | Jun 24, 2026 @ 12:29
3301C2 | 3301 | 16871 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 17:03 | Jul 27, 2026 @ 17:03
3301D7 | 3301 | 16869 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:03 | Jun 01, 2026 @ 14:03
3302F2 | 3302 | 16858 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 15, 2026 @ 13:14 | Jul 15, 2026 @ 13:14
3302D4 | 3302 | 16856 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3302D2 | 3302 | 16851 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 18:16 | Jul 27, 2026 @ 18:16
3302F3 | 3302 | 16848 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:30 | Jun 24, 2026 @ 12:30
3302C2 | 3302 | 16842 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 18:16 | Jul 27, 2026 @ 18:16
3302D7 | 3302 | 16840 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:03 | Jun 01, 2026 @ 14:03
3303F2 | 3303 | 16829 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:03 | Jul 17, 2026 @ 14:03
3303D4 | 3303 | 16827 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 17:53 | Jul 22, 2026 @ 17:53
3303D2 | 3303 | 16822 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 14:12 | Jul 22, 2026 @ 12:54
3303F3 | 3303 | 16819 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:03 | Jul 17, 2026 @ 14:03
3303C2 | 3303 | 16813 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 17:53 | Jul 22, 2026 @ 17:53
3303D7 | 3303 | 16811 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:04 | Jun 01, 2026 @ 14:04
3304F2 | 3304 | 16800 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:10 | Jul 17, 2026 @ 14:10
3304D4 | 3304 | 16798 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 17:53 | Jul 22, 2026 @ 17:53
3304D2 | 3304 | 16793 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:54 | Jul 22, 2026 @ 12:54
3304F3 | 3304 | 16790 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:10 | Jul 17, 2026 @ 14:10
3304C2 | 3304 | 16784 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 08:34 | Jul 23, 2026 @ 08:34
3304D7 | 3304 | 16782 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:04 | Jun 01, 2026 @ 14:04
3305F2 | 3305 | 16771 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:10 | Jul 17, 2026 @ 14:10
3305D4 | 3305 | 16769 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3305D2 | 3305 | 16764 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:54 | Jul 22, 2026 @ 12:54
3305F3 | 3305 | 16761 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3305C2 | 3305 | 16755 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 18:17 | Jul 27, 2026 @ 18:17
3305D7 | 3305 | 16753 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:12 | Jun 01, 2026 @ 14:12
3306F2 | 3306 | 16742 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3306D4 | 3306 | 16740 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 17:16 | Jul 22, 2026 @ 17:16
3306D2 | 3306 | 16735 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:47 | Jul 22, 2026 @ 12:38
3306F3 | 3306 | 16732 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3306C2 | 3306 | 16726 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 17:16 | Jul 22, 2026 @ 17:16
3306D7 | 3306 | 16724 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:13 | Jun 01, 2026 @ 14:13
3307F2 | 3307 | 16713 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3307D4 | 3307 | 16711 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 08:35 | Jul 23, 2026 @ 08:35
3307D2 | 3307 | 16706 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 08:35 | Jul 23, 2026 @ 08:35
3307F3 | 3307 | 16703 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3307C2 | 3307 | 16697 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 08:35 | Jul 23, 2026 @ 08:35
3307D7 | 3307 | 16695 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:13 | Jun 01, 2026 @ 14:13
3308F2 | 3308 | 16684 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:11 | Jul 17, 2026 @ 14:11
3308D4 | 3308 | 16682 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:42 | Jul 23, 2026 @ 09:42
3308D2 | 3308 | 16677 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:43 | Jul 23, 2026 @ 09:43
3308F3 | 3308 | 16674 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3308C2 | 3308 | 16668 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 11:55 | Jul 23, 2026 @ 11:55
3308D7 | 3308 | 16666 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:13 | Jun 01, 2026 @ 14:13
3309F2 | 3309 | 16655 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3309D4 | 3309 | 16653 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3309 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:43 | Jul 23, 2026 @ 09:43
3309D2 | 3309 | 16648 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3309 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:55 | Jul 22, 2026 @ 12:55
3309F3 | 3309 | 16645 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:07 | Jul 17, 2026 @ 16:07
3309C2 | 3309 | 16639 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 11:55 | Jul 23, 2026 @ 11:55
3309D7 | 3309 | 16637 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:22
3401F2 | 3401 | 16626 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3401D4 | 3401 | 16624 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:41 | Jul 24, 2026 @ 09:41
3401D2 | 3401 | 16619 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:41 | Jul 24, 2026 @ 09:41
3401F3 | 3401 | 16616 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3401C2 | 3401 | 16610 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:42 | Jul 24, 2026 @ 09:42
3401D7 | 3401 | 16608 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:30 | Jun 01, 2026 @ 14:30
3402F2 | 3402 | 16597 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3402D4 | 3402 | 16595 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:42 | Jul 24, 2026 @ 09:42
3402D2 | 3402 | 16590 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:42 | Jul 24, 2026 @ 09:42
3402F3 | 3402 | 16587 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3402C2 | 3402 | 16581 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 29, 2026 @ 09:11 | Jul 29, 2026 @ 09:11
3402D7 | 3402 | 16579 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:31 | Jun 01, 2026 @ 14:31
3403F2 | 3403 | 16568 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3403D4 | 3403 | 16566 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:42 | Jul 24, 2026 @ 09:42
3403D2 | 3403 | 16561 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:43 | Jul 24, 2026 @ 09:43
3403F3 | 3403 | 16558 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3403C2 | 3403 | 16552 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:43 | Jul 24, 2026 @ 09:43
3403D7 | 3403 | 16550 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:31 | Jun 01, 2026 @ 14:31
3404F2 | 3404 | 16539 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3404D4 | 3404 | 16537 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:43 | Jul 24, 2026 @ 09:43
3404D2 | 3404 | 16532 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:43 | Jul 24, 2026 @ 09:43
3404F3 | 3404 | 16529 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:12 | Jul 17, 2026 @ 14:12
3404C2 | 3404 | 16523 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:44 | Jul 24, 2026 @ 09:44
3404D7 | 3404 | 16521 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:31 | Jun 01, 2026 @ 14:31
3405F2 | 3405 | 16510 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3405D4 | 3405 | 16508 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:44 | Jul 24, 2026 @ 09:44
3405D2 | 3405 | 16503 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:44 | Jul 24, 2026 @ 09:44
3405F3 | 3405 | 16500 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:13 | Jul 17, 2026 @ 14:13
3405C2 | 3405 | 16494 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:44 | Jul 24, 2026 @ 09:44
3405D7 | 3405 | 16492 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:32 | Jun 01, 2026 @ 14:32
3406F2 | 3406 | 16481 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:36 | Jul 21, 2026 @ 14:36
3406D4 | 3406 | 16479 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:44 | Jul 24, 2026 @ 09:44
3406D2 | 3406 | 16474 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:45 | Jul 24, 2026 @ 09:45
3406F3 | 3406 | 16471 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:13 | Jul 17, 2026 @ 14:13
3406C2 | 3406 | 16465 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 12:50 | Jul 24, 2026 @ 12:50
3406D7 | 3406 | 16463 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:32 | Jun 01, 2026 @ 14:32
3407F2 | 3407 | 16452 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3407D4 | 3407 | 16450 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:49 | Jul 23, 2026 @ 17:49
3407D2 | 3407 | 16445 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:48 | Jul 23, 2026 @ 17:48
3407F3 | 3407 | 16442 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:13 | Jul 17, 2026 @ 14:13
3407C2 | 3407 | 16436 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 17:48 | Jul 23, 2026 @ 17:48
3407D7 | 3407 | 16434 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:33 | Jun 01, 2026 @ 14:33
3408F2 | 3408 | 16423 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3408D4 | 3408 | 16421 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:54 | Jul 23, 2026 @ 17:54
3408D2 | 3408 | 16416 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:54 | Jul 23, 2026 @ 17:54
3408F3 | 3408 | 16413 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:13 | Jul 17, 2026 @ 14:13
3408C2 | 3408 | 16407 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 17:53 | Jul 23, 2026 @ 17:53
3408D7 | 3408 | 16405 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:35 | Jun 01, 2026 @ 14:35
3409F2 | 3409 | 16394 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3409D4 | 3409 | 16392 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:45 | Jul 24, 2026 @ 09:45
3409D2 | 3409 | 16387 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:45 | Jul 24, 2026 @ 09:45
3409F3 | 3409 | 16384 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:14 | Jul 17, 2026 @ 14:14
3409C2 | 3409 | 16378 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:45 | Jul 24, 2026 @ 09:45
3409D7 | 3409 | 16376 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:35 | Jun 01, 2026 @ 14:35
3410F2 | 3410 | 16365 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:14 | Jul 17, 2026 @ 14:14
3410D4 | 3410 | 16363 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3410 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:55 | Jul 23, 2026 @ 17:55
3410D2 | 3410 | 16358 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3410 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 17:54 | Jul 23, 2026 @ 17:54
3410F3 | 3410 | 16355 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:14 | Jul 17, 2026 @ 14:14
3410C2 | 3410 | 16349 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 17:54 | Jul 23, 2026 @ 17:54
3410D7 | 3410 | 16347 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:36 | Jun 01, 2026 @ 14:36
3501F2 | 3501 | 16336 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3501D4 | 3501 | 16334 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:35 | Jul 25, 2026 @ 08:35
3501D2 | 3501 | 16329 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:35 | Jul 25, 2026 @ 08:35
3501F3 | 3501 | 16326 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 14, 2026 @ 10:45 | Jul 14, 2026 @ 10:45
3501C2 | 3501 | 16320 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:45 | Jul 24, 2026 @ 09:45
3501D7 | 3501 | 16318 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:58 | May 09, 2026 @ 13:58
3502F2 | 3502 | 16307 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3502D4 | 3502 | 16305 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:36 | Jul 25, 2026 @ 08:36
3502D2 | 3502 | 16300 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:36 | Jul 25, 2026 @ 08:36
3502F3 | 3502 | 16297 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3502C2 | 3502 | 16291 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:15 | Jul 24, 2026 @ 14:15
3502D7 | 3502 | 16289 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:57 | May 09, 2026 @ 13:57
3503F2 | 3503 | 16278 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3503D4 | 3503 | 16276 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:36 | Jul 25, 2026 @ 08:36
3503D2 | 3503 | 16271 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:37 | Jul 25, 2026 @ 08:37
3503F3 | 3503 | 16268 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3503C2 | 3503 | 16262 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:16 | Jul 24, 2026 @ 14:16
3503D7 | 3503 | 16260 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:56 | May 09, 2026 @ 13:56
3504F2 | 3504 | 16249 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3504D4 | 3504 | 16247 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3504D2 | 3504 | 16242 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:37 | Jul 25, 2026 @ 08:37
3504F3 | 3504 | 16239 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:15 | Jul 17, 2026 @ 14:15
3504C2 | 3504 | 16233 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:16 | Jul 24, 2026 @ 14:16
3504D7 | 3504 | 16231 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:55 | May 09, 2026 @ 13:55
3505F2 | 3505 | 16220 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3505D4 | 3505 | 16218 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3505D2 | 3505 | 16213 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:37 | Jul 25, 2026 @ 08:37
3505F3 | 3505 | 16210 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:16 | Jul 17, 2026 @ 14:16
3505C2 | 3505 | 16204 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:16 | Jul 24, 2026 @ 14:16
3505D7 | 3505 | 16202 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 17:05 | May 09, 2026 @ 13:55
3506F2 | 3506 | 16191 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3506D4 | 3506 | 16189 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3506D2 | 3506 | 16184 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:37 | Jul 25, 2026 @ 08:37
3506F3 | 3506 | 16181 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3506C2 | 3506 | 16175 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:16 | Jul 24, 2026 @ 14:16
3506D7 | 3506 | 16173 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:54 | May 09, 2026 @ 13:54
3507F2 | 3507 | 16162 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3507D4 | 3507 | 16160 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3507D2 | 3507 | 16155 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 09:08 | Jul 25, 2026 @ 09:08
3507F3 | 3507 | 16152 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3507C2 | 3507 | 16146 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:16 | Jul 24, 2026 @ 14:16
3507D7 | 3507 | 16144 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 17:09 | May 09, 2026 @ 13:54
3508F2 | 3508 | 16133 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3508D4 | 3508 | 16131 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3508D2 | 3508 | 16126 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 09:08 | Jul 25, 2026 @ 09:08
3508F3 | 3508 | 16123 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3508C2 | 3508 | 16117 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:17 | Jul 24, 2026 @ 14:17
3508D7 | 3508 | 16115 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 13:54 | May 09, 2026 @ 13:54
3509F2 | 3509 | 16104 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3509D4 | 3509 | 16102 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3509 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
3509D2 | 3509 | 16097 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3509 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:41 | Jul 25, 2026 @ 08:41
3509F3 | 3509 | 16094 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 14:17 | Jul 17, 2026 @ 14:17
3509C2 | 3509 | 16088 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:17 | Jul 24, 2026 @ 14:17
3509D7 | 3509 | 16086 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 18:03 | May 09, 2026 @ 13:53
3601F2 | 3601 | 16075 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3601D4 | 3601 | 16073 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:22 | Jul 31, 2026 @ 18:22
3601D2 | 3601 | 16068 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:27 | Jul 31, 2026 @ 18:27
3601F3 | 3601 | 16065 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:00 | Jul 17, 2026 @ 16:00
3601C2 | 3601 | 16059 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:55 | Aug 01, 2026 @ 08:55
3601D7 | 3601 | 16057 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:28 | May 04, 2026 @ 12:28
3605F2 | 3605 | 16046 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3605D4 | 3605 | 16044 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:22 | Jul 31, 2026 @ 18:22
3605D2 | 3605 | 16039 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3605F3 | 3605 | 16036 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:01 | Jul 17, 2026 @ 16:01
3605C2 | 3605 | 16030 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:55 | Aug 01, 2026 @ 08:55
3605D7 | 3605 | 16028 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:26 | May 04, 2026 @ 12:26
3606F2 | 3606 | 16017 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:37 | Jul 21, 2026 @ 14:37
3606D4 | 3606 | 16015 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:23 | Jul 31, 2026 @ 18:23
3606D2 | 3606 | 16010 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3606F3 | 3606 | 16007 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:01 | Jul 17, 2026 @ 16:01
3606C2 | 3606 | 16001 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:55 | Aug 01, 2026 @ 08:55
3606D7 | 3606 | 15999 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:26 | May 04, 2026 @ 12:26
3210F2 | 3210 | 15988 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3210 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:30 | Jun 24, 2026 @ 12:30
3210F3 | 3210 | 15978 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3210 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 12:30 | Jun 24, 2026 @ 12:30
3210C2 | 3210 | 15972 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3210 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 12:55 | Jul 22, 2026 @ 12:55
3210D7 | 3210 | 15970 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3210 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 08:35 | Jun 01, 2026 @ 14:19
3209F2 | 3209 | 15959 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:19 | Jun 24, 2026 @ 13:19
3209D4 | 3209 | 15957 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:56 | Jul 22, 2026 @ 12:56
3209D2 | 3209 | 15952 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:56 | Jul 22, 2026 @ 12:56
3209F3 | 3209 | 15949 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:19 | Jun 24, 2026 @ 13:19
3209C2 | 3209 | 15943 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 11:58 | Jul 23, 2026 @ 11:58
3209D7 | 3209 | 15941 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:18 | Jun 01, 2026 @ 14:18
3208F2 | 3208 | 15930 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:19 | Jun 24, 2026 @ 13:19
3208D4 | 3208 | 15928 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 08:48 | Jul 21, 2026 @ 08:48
3208D2 | 3208 | 15923 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 08:48 | Jul 21, 2026 @ 08:48
3208F3 | 3208 | 15920 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:20 | Jun 24, 2026 @ 13:20
3208C2 | 3208 | 15914 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3208D7 | 3208 | 15912 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:18 | Jun 01, 2026 @ 14:18
3207F2 | 3207 | 15901 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:20 | Jun 24, 2026 @ 13:20
3207D4 | 3207 | 15899 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 13:26 | Jul 21, 2026 @ 13:26
3207D2 | 3207 | 15894 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 13:26 | Jul 21, 2026 @ 13:26
3207F3 | 3207 | 15891 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:20 | Jun 24, 2026 @ 13:20
3207C2 | 3207 | 15885 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 17:26 | Jul 21, 2026 @ 15:49
3207D7 | 3207 | 15883 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 16:14 | Jun 01, 2026 @ 14:17
3206F2 | 3206 | 15872 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 15, 2026 @ 13:17 | Jul 15, 2026 @ 13:17
3206D4 | 3206 | 15870 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:51 | Jul 20, 2026 @ 17:51
3206D2 | 3206 | 15865 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:51 | Jul 20, 2026 @ 17:51
3206F3 | 3206 | 15862 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:21 | Jun 24, 2026 @ 13:21
3206C2 | 3206 | 15856 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 17:25 | Jul 21, 2026 @ 15:47
3206D7 | 3206 | 15854 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:17 | Jun 01, 2026 @ 14:17
3205F2 | 3205 | 15843 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:21 | Jun 24, 2026 @ 13:21
3205D4 | 3205 | 15841 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:56 | Jul 22, 2026 @ 12:56
3205D2 | 3205 | 15836 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:57 | Jul 22, 2026 @ 12:57
3205F3 | 3205 | 15833 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:21 | Jun 24, 2026 @ 13:21
3205C2 | 3205 | 15827 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 11:59 | Jul 23, 2026 @ 11:59
3205D7 | 3205 | 15825 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 16:12 | Jun 01, 2026 @ 14:17
3204F2 | 3204 | 15814 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:21 | Jun 24, 2026 @ 13:21
3204D4 | 3204 | 15812 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:57 | Jul 22, 2026 @ 12:57
3204D2 | 3204 | 15807 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:57 | Jul 22, 2026 @ 12:57
3204F3 | 3204 | 15804 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:22 | Jun 24, 2026 @ 13:22
3204C2 | 3204 | 15798 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 12:57 | Jul 22, 2026 @ 12:57
3204D7 | 3204 | 15796 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:16 | Jun 01, 2026 @ 08:37
3203F2 | 3203 | 15785 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:22 | Jun 24, 2026 @ 13:22
3203D4 | 3203 | 15783 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 08:48 | Jul 21, 2026 @ 08:48
3203D2 | 3203 | 15778 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 08:49 | Jul 21, 2026 @ 08:49
3203F3 | 3203 | 15775 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:22 | Jun 24, 2026 @ 13:22
3203C2 | 3203 | 15769 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 21, 2026 @ 08:49 | Jul 21, 2026 @ 08:49
3203D7 | 3203 | 15767 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:15 | May 07, 2026 @ 13:35
3202F2 | 3202 | 15756 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:22 | Jun 24, 2026 @ 13:22
3202D4 | 3202 | 15754 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:58 | Jul 22, 2026 @ 12:58
3202D2 | 3202 | 15749 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:58 | Jul 22, 2026 @ 12:58
3202F3 | 3202 | 15746 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:23 | Jun 24, 2026 @ 13:23
3202C2 | 3202 | 15740 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 12:59 | Jul 22, 2026 @ 12:59
3202D7 | 3202 | 15738 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 08:41 | May 07, 2026 @ 13:34
3201F2 | 3201 | 15727 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:23 | Jun 24, 2026 @ 13:23
3201D4 | 3201 | 15725 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:59 | Jul 22, 2026 @ 12:59
3201D2 | 3201 | 15720 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 12:59 | Jul 22, 2026 @ 12:59
3201F3 | 3201 | 15717 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:23 | Jun 24, 2026 @ 13:23
3201C2 | 3201 | 15711 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 12:59 | Jul 22, 2026 @ 12:59
3201D7 | 3201 | 15709 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 08:40 | May 07, 2026 @ 13:34
3109D4 | 3109 | 15696 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3109 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 21, 2026 @ 08:49 | Jul 21, 2026 @ 08:49
3109D2 | 3109 | 15691 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3109 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:53 | Jul 20, 2026 @ 17:53
3109D7 | 3109 | 15680 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3109 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 08:34 | May 04, 2026 @ 17:46
3108F2 | 3108 | 15669 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:27 | Jun 24, 2026 @ 13:26
3108D4 | 3108 | 15667 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:53 | Jul 20, 2026 @ 17:53
3108D2 | 3108 | 15662 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:53 | Jul 20, 2026 @ 17:53
3108F3 | 3108 | 15659 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:27 | Jun 24, 2026 @ 13:27
3108C2 | 3108 | 15653 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 17:53 | Jul 20, 2026 @ 17:53
3108D7 | 3108 | 15651 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:46 | May 04, 2026 @ 17:46
3107F2 | 3107 | 15640 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:28 | Jun 24, 2026 @ 13:28
3107D4 | 3107 | 15638 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:54 | Jul 20, 2026 @ 17:54
3107D2 | 3107 | 15633 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:54 | Jul 20, 2026 @ 17:54
3107F3 | 3107 | 15630 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:28 | Jun 24, 2026 @ 13:28
3107C2 | 3107 | 15624 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 15:06 | Jul 20, 2026 @ 15:06
3107D7 | 3107 | 15622 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:46 | May 04, 2026 @ 17:46
3106F2 | 3106 | 15611 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:28 | Jun 24, 2026 @ 13:28
3106D4 | 3106 | 15609 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 14:32 | Jul 22, 2026 @ 14:32
3106D2 | 3106 | 15604 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 14:32 | Jul 22, 2026 @ 14:32
3106F3 | 3106 | 15601 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:28 | Jun 24, 2026 @ 13:28
3106C2 | 3106 | 15595 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 17:54 | Jul 20, 2026 @ 17:54
3106D7 | 3106 | 15593 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:45 | May 04, 2026 @ 17:45
3105F2 | 3105 | 15582 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:29 | Jun 24, 2026 @ 13:29
3105D4 | 3105 | 15580 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 14:02 | Jul 23, 2026 @ 14:02
3105D2 | 3105 | 15575 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 14:02 | Jul 23, 2026 @ 14:02
3105F3 | 3105 | 15572 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:29 | Jun 24, 2026 @ 13:29
3105C2 | 3105 | 15566 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:00 | Jul 20, 2026 @ 18:00
3105D7 | 3105 | 15564 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:45 | May 04, 2026 @ 17:45
3104F2 | 3104 | 15553 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:29 | Jun 24, 2026 @ 13:29
3104D4 | 3104 | 15551 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:01 | Jul 20, 2026 @ 18:01
3104D2 | 3104 | 15546 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:02 | Jul 20, 2026 @ 18:02
3104F3 | 3104 | 15543 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:29 | Jun 24, 2026 @ 13:29
3104C2 | 3104 | 15537 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 14:30 | Jul 20, 2026 @ 14:30
3104D7 | 3104 | 15535 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:45 | May 04, 2026 @ 17:45
3103F2 | 3103 | 15524 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:29 | Jun 24, 2026 @ 13:29
3103D4 | 3103 | 15522 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:02 | Jul 20, 2026 @ 18:02
3103D2 | 3103 | 15517 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:02 | Jul 20, 2026 @ 18:02
3103F3 | 3103 | 15514 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:30 | Jun 24, 2026 @ 13:30
3103C2 | 3103 | 15508 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:02 | Jul 20, 2026 @ 18:02
3103D7 | 3103 | 15506 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:44 | May 04, 2026 @ 17:44
3102F2 | 3102 | 15495 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:30 | Jun 24, 2026 @ 13:30
3102D4 | 3102 | 15493 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:14 | Jul 23, 2026 @ 12:14
3102D2 | 3102 | 15488 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 13:42 | Jul 23, 2026 @ 13:42
3102F3 | 3102 | 15485 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:30 | Jun 24, 2026 @ 13:30
3102C2 | 3102 | 15479 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:03 | Jul 20, 2026 @ 18:03
3102D7 | 3102 | 15477 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:44 | May 04, 2026 @ 17:44
3101F2 | 3101 | 15466 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:30 | Jun 24, 2026 @ 13:30
3101D4 | 3101 | 15464 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3101_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 11:59 | Jul 23, 2026 @ 11:59
3101D2 | 3101 | 15459 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3101_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 11:59 | Jul 23, 2026 @ 11:59
3101F3 | 3101 | 15456 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:30 | Jun 24, 2026 @ 13:30
3101C2 | 3101 | 15450 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:03 | Jul 20, 2026 @ 18:03
3101D7 | 3101 | 15448 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:02 | May 04, 2026 @ 17:44
3010F2 | 3010 | 15437 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3010 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:31 | Jun 24, 2026 @ 13:31
3010D4 | 3010 | 15435 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3010 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:04 | Jul 20, 2026 @ 18:04
3010D2 | 3010 | 15430 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3010 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:04 | Jul 20, 2026 @ 18:04
3010F3 | 3010 | 15427 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3010 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:31 | Jun 24, 2026 @ 13:31
3010C2 | 3010 | 15421 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3010 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:05 | Jul 20, 2026 @ 18:05
3010D7 | 3010 | 15419 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3010 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:38 | May 04, 2026 @ 17:38
3604F2 | 3604 | 15408 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3604D4 | 3604 | 15406 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 19:03 | Jul 31, 2026 @ 18:23
3604D2 | 3604 | 15401 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3604F3 | 3604 | 15398 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:01 | Jul 17, 2026 @ 16:01
3604C2 | 3604 | 15392 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3604D7 | 3604 | 15390 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:26 | May 04, 2026 @ 12:26
3603F2 | 3603 | 15379 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3603D4 | 3603 | 15377 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:42 | Aug 01, 2026 @ 08:42
3603D2 | 3603 | 15372 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:24 | Jul 31, 2026 @ 18:24
3603F3 | 3603 | 15369 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:01 | Jul 17, 2026 @ 16:01
3603C2 | 3603 | 15363 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 31, 2026 @ 18:24 | Jul 31, 2026 @ 18:24
3603D7 | 3603 | 15361 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:26 | May 04, 2026 @ 12:26
3602F2 | 3602 | 15350 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3602D4 | 3602 | 15348 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:23 | Jul 31, 2026 @ 18:23
3602D2 | 3602 | 15343 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3602F3 | 3602 | 15340 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:02 | Jul 17, 2026 @ 16:02
3602C2 | 3602 | 15334 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3602D7 | 3602 | 15332 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:27 | May 04, 2026 @ 12:27
3607F2 | 3607 | 15321 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3607D4 | 3607 | 15319 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:23 | Jul 31, 2026 @ 18:23
3607D2 | 3607 | 15314 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3607F3 | 3607 | 15311 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:02 | Jul 17, 2026 @ 16:02
3607C2 | 3607 | 15305 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3607D7 | 3607 | 15303 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 14:24 | May 04, 2026 @ 12:25
3608F2 | 3608 | 15292 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:38 | Jul 21, 2026 @ 14:38
3608D4 | 3608 | 15290 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:23 | Jul 31, 2026 @ 18:23
3608D2 | 3608 | 15285 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3608F3 | 3608 | 15282 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:02 | Jul 17, 2026 @ 16:02
3608C2 | 3608 | 15276 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 31, 2026 @ 18:28 | Jul 31, 2026 @ 18:28
3608D7 | 3608 | 15274 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:25 | May 04, 2026 @ 12:25
3609F2 | 3609 | 15263 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:39 | Jul 21, 2026 @ 14:39
3609D4 | 3609 | 15261 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:23 | Jul 31, 2026 @ 18:23
3609D2 | 3609 | 15256 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:50 | Aug 01, 2026 @ 08:50
3609F3 | 3609 | 15253 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:02 | Jul 17, 2026 @ 16:02
3609C2 | 3609 | 15247 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3609D7 | 3609 | 15245 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 08:42 | Jun 26, 2026 @ 08:41
3610F2 | 3610 | 15234 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:50 | Jul 21, 2026 @ 15:50
3610D4 | 3610 | 15232 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3610 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:37 | Aug 05, 2026 @ 08:37
3610D2 | 3610 | 15227 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3610 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:51 | Aug 01, 2026 @ 08:51
3610F3 | 3610 | 15224 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:02 | Jul 17, 2026 @ 16:02
3610C2 | 3610 | 15218 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3610D7 | 3610 | 15216 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:24 | May 04, 2026 @ 12:24
3701F2 | 3701 | 15205 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 14:39 | Jul 21, 2026 @ 14:39
3701D4 | 3701 | 15203 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:25 | Jul 31, 2026 @ 18:25
3701D2 | 3701 | 15198 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:51 | Aug 01, 2026 @ 08:51
3701F3 | 3701 | 15195 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 14, 2026 @ 10:46 | Jul 14, 2026 @ 10:46
3701C2 | 3701 | 15189 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:56 | Aug 01, 2026 @ 08:56
3701D7 | 3701 | 15187 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:20 | May 04, 2026 @ 12:20
3702F2 | 3702 | 15176 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:50 | Jul 21, 2026 @ 15:50
3702D4 | 3702 | 15174 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:25 | Jul 31, 2026 @ 18:25
3702D2 | 3702 | 15169 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:51 | Aug 01, 2026 @ 08:51
3702F3 | 3702 | 15166 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3702C2 | 3702 | 15160 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3702D7 | 3702 | 15158 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:21 | May 04, 2026 @ 12:21
3703F2 | 3703 | 15147 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:51 | Jul 21, 2026 @ 15:51
3703D4 | 3703 | 15145 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:25 | Jul 31, 2026 @ 18:25
3703D2 | 3703 | 15140 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:52 | Aug 01, 2026 @ 08:52
3703F3 | 3703 | 15137 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3703C2 | 3703 | 15131 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3703D7 | 3703 | 15129 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:21 | May 04, 2026 @ 12:21
3704F2 | 3704 | 15118 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:51 | Jul 21, 2026 @ 15:51
3704D4 | 3704 | 15116 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:26 | Jul 31, 2026 @ 18:26
3704D2 | 3704 | 15111 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:52 | Aug 01, 2026 @ 08:52
3704F3 | 3704 | 15108 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3704C2 | 3704 | 15102 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3704D7 | 3704 | 15100 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:21 | May 04, 2026 @ 12:21
3705F2 | 3705 | 15089 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3705D4 | 3705 | 15087 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:26 | Jul 31, 2026 @ 18:26
3705D2 | 3705 | 15082 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:52 | Aug 01, 2026 @ 08:52
3705F3 | 3705 | 15079 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3705C2 | 3705 | 15073 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3705D7 | 3705 | 15071 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:22 | May 04, 2026 @ 12:22
3706F2 | 3706 | 15060 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:51 | Jul 21, 2026 @ 15:51
3706D4 | 3706 | 15058 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:26 | Jul 31, 2026 @ 18:26
3706D2 | 3706 | 15053 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:52 | Aug 01, 2026 @ 08:52
3706F3 | 3706 | 15050 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3706C2 | 3706 | 15044 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3706D7 | 3706 | 15042 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:22 | May 04, 2026 @ 12:22
3707F2 | 3707 | 15031 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:53 | Jul 21, 2026 @ 15:53
3707D4 | 3707 | 15029 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:26 | Jul 31, 2026 @ 18:26
3707D2 | 3707 | 15024 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:53 | Aug 01, 2026 @ 08:53
3707F3 | 3707 | 15021 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:03 | Jul 17, 2026 @ 16:03
3707C2 | 3707 | 15015 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 11, 2026 @ 19:27 | Aug 01, 2026 @ 08:57
3707D7 | 3707 | 15013 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:22 | May 04, 2026 @ 12:22
3708F2 | 3708 | 15002 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:54 | Jul 21, 2026 @ 15:54
3708D4 | 3708 | 15000 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:26 | Jul 31, 2026 @ 18:26
3708D2 | 3708 | 14995 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:53 | Aug 01, 2026 @ 08:53
3708F3 | 3708 | 14992 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:07 | Jul 17, 2026 @ 16:07
3708C2 | 3708 | 14986 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:57 | Aug 01, 2026 @ 08:57
3708D7 | 3708 | 14984 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 12:23 | May 04, 2026 @ 12:23
3709F2 | 3709 | 14973 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:54 | Jul 21, 2026 @ 15:54
3709D4 | 3709 | 14971 | D4 | D4 Intercom IR | Intercom IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 31, 2026 @ 18:27 | Jul 31, 2026 @ 18:27
3709D2 | 3709 | 14966 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:53 | Aug 01, 2026 @ 08:53
3709F3 | 3709 | 14963 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 17, 2026 @ 16:04 | Jul 17, 2026 @ 16:04
3709C2 | 3709 | 14957 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 09, 2026 @ 04:00 | closed | Planned Work | 3709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 08:58 | Aug 01, 2026 @ 08:58
3709D7 | 3709 | 14955 | D7 | D7 Booster IR | Booster IR | Jan 09, 2026 @ 04:00 | closed | Issue | 3709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 16:09 | May 04, 2026 @ 12:23
3009F2 | 3009 | 14944 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:32 | Jun 24, 2026 @ 13:32
3009D4 | 3009 | 14942 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:00 | Jul 23, 2026 @ 12:00
3009D2 | 3009 | 14937 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:01 | Jul 23, 2026 @ 12:01
3009F3 | 3009 | 14934 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:32 | Jun 24, 2026 @ 13:32
3009C2 | 3009 | 14928 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:01 | Jul 23, 2026 @ 12:01
3009D7 | 3009 | 14926 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:38 | May 04, 2026 @ 17:38
3008F2 | 3008 | 14915 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:35 | Jun 24, 2026 @ 13:35
3008D4 | 3008 | 14913 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 10:48 | Jul 18, 2026 @ 17:44
3008D2 | 3008 | 14908 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 10:48 | Jul 18, 2026 @ 17:43
3008F3 | 3008 | 14905 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:35 | Jun 24, 2026 @ 13:35
3008C2 | 3008 | 14899 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 18, 2026 @ 17:43 | Jul 18, 2026 @ 17:43
3008D7 | 3008 | 14897 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:38 | May 04, 2026 @ 17:38
3007F2 | 3007 | 14886 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:35 | Jun 24, 2026 @ 13:35
3007D4 | 3007 | 14884 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:50 | Jul 20, 2026 @ 17:50
3007D2 | 3007 | 14879 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 17:49 | Jul 20, 2026 @ 17:49
3007F3 | 3007 | 14876 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3007C2 | 3007 | 14870 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 17:49 | Jul 20, 2026 @ 17:49
3007D7 | 3007 | 14868 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:37 | May 04, 2026 @ 17:37
3006F2 | 3006 | 14857 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 16, 2026 @ 16:43 | Jul 16, 2026 @ 16:43
3006D4 | 3006 | 14855 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:04 | Jul 16, 2026 @ 18:04
3006D2 | 3006 | 14850 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:03 | Jul 16, 2026 @ 18:03
3006F3 | 3006 | 14847 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3006C2 | 3006 | 14841 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 18:02 | Jul 16, 2026 @ 18:02
3006D7 | 3006 | 14839 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:37 | May 04, 2026 @ 17:37
3005F2 | 3005 | 14828 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3005D4 | 3005 | 14826 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:03 | Jul 23, 2026 @ 12:02
3005D2 | 3005 | 14821 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:02 | Jul 23, 2026 @ 12:02
3005F3 | 3005 | 14818 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3005C2 | 3005 | 14812 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:03 | Jul 23, 2026 @ 12:03
3005D7 | 3005 | 14810 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:00 | Jun 01, 2026 @ 14:00
3004F2 | 3004 | 14799 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 16, 2026 @ 17:38 | Jul 16, 2026 @ 17:38
3004D4 | 3004 | 14797 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3004_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 14:28 | Jul 17, 2026 @ 14:28
3004D2 | 3004 | 14792 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3004_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 17:38 | Jul 16, 2026 @ 17:38
3004F3 | 3004 | 14789 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3004C2 | 3004 | 14783 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 17:38 | Jul 16, 2026 @ 17:38
3004D7 | 3004 | 14781 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:36 | May 04, 2026 @ 17:36
3002F2 | 3002 | 14770 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:36 | Jun 24, 2026 @ 13:36
3002D4 | 3002 | 14768 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3002_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 17:16 | Jul 24, 2026 @ 17:16
3002D2 | 3002 | 14763 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3002_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:03 | Jul 23, 2026 @ 12:03
3002F3 | 3002 | 14760 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:37 | Jun 24, 2026 @ 13:37
3002C2 | 3002 | 14754 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:04 | Jul 23, 2026 @ 12:04
3002D7 | 3002 | 14752 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:36 | May 04, 2026 @ 17:36
3003F2 | 3003 | 14741 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 16, 2026 @ 17:38 | Jul 16, 2026 @ 17:38
3003D4 | 3003 | 14739 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 17:36 | Jul 16, 2026 @ 17:36
3003D2 | 3003 | 14734 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 17:36 | Jul 16, 2026 @ 17:36
3003F3 | 3003 | 14731 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 24, 2026 @ 13:37 | Jun 24, 2026 @ 13:37
3003C2 | 3003 | 14725 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 17:34 | Jul 16, 2026 @ 16:55
3003D7 | 3003 | 14723 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:36 | May 04, 2026 @ 17:36
3001F2 | 3001 | 14712 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 23, 2026 @ 08:59 | Jun 23, 2026 @ 08:59
3001D4 | 3001 | 14710 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 28, 2026 @ 13:56 | Jul 28, 2026 @ 13:56
3001D2 | 3001 | 14705 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:04 | Jul 23, 2026 @ 12:04
3001F3 | 3001 | 14702 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 23, 2026 @ 09:00 | Jun 23, 2026 @ 09:00
3001C2 | 3001 | 14696 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 3001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:04 | Jul 23, 2026 @ 12:04
3001D7 | 3001 | 14694 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 3001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:35 | May 04, 2026 @ 17:35
2909F2 | 2909 | 14683 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2909 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2909D4 | 2909 | 14681 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2909 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:30 | Jul 16, 2026 @ 18:30
2909D2 | 2909 | 14676 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2909 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:30 | Jul 16, 2026 @ 18:30
2909F3 | 2909 | 14673 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2909 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2909C2 | 2909 | 14667 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2909 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 18:29 | Jul 16, 2026 @ 18:29
2909D7 | 2909 | 14665 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2909 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:35 | May 04, 2026 @ 17:35
2908F2 | 2908 | 14654 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2908 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2908D4 | 2908 | 14652 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2908 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:29 | Jul 16, 2026 @ 18:29
2908D2 | 2908 | 14647 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2908 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 18:29 | Jul 16, 2026 @ 18:29
2908F3 | 2908 | 14644 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2908 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2908C2 | 2908 | 14638 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2908 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 18:29 | Jul 16, 2026 @ 18:29
2908D7 | 2908 | 14636 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2908 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:34 | May 04, 2026 @ 17:34
2907F2 | 2907 | 14625 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2907D4 | 2907 | 14623 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 07:48 | Jul 16, 2026 @ 18:17
2907D2 | 2907 | 14618 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 17:51 | Jul 16, 2026 @ 17:51
2907F3 | 2907 | 14615 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2907C2 | 2907 | 14609 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 17:51 | Jul 16, 2026 @ 17:51
2907D7 | 2907 | 14607 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:34 | May 04, 2026 @ 17:34
2906F2 | 2906 | 14596 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2906D4 | 2906 | 14594 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 07:47 | Jul 16, 2026 @ 18:03
2906D2 | 2906 | 14589 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 17:49 | Jul 16, 2026 @ 17:49
2906F3 | 2906 | 14586 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2906C2 | 2906 | 14580 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 17:49 | Jul 16, 2026 @ 17:49
2906D7 | 2906 | 14578 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:29 | May 04, 2026 @ 17:29
2905F2 | 2905 | 14567 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2905D4 | 2905 | 14565 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2905D2 | 2905 | 14560 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:04 | Jul 23, 2026 @ 12:04
2905F3 | 2905 | 14557 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 10, 2026 @ 10:19 | Jun 10, 2026 @ 10:19
2905C2 | 2905 | 14551 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:21 | Jul 24, 2026 @ 14:21
2905D7 | 2905 | 14549 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:29 | May 04, 2026 @ 17:29
2904F2 | 2904 | 14538 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:02 | Jun 08, 2026 @ 09:02
2904D4 | 2904 | 14536 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 08:46 | Jul 17, 2026 @ 08:46
2904D2 | 2904 | 14531 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 08:46 | Jul 17, 2026 @ 08:46
2904F3 | 2904 | 14528 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:06 | Jun 08, 2026 @ 09:06
2904C2 | 2904 | 14522 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 17, 2026 @ 08:46 | Jul 17, 2026 @ 08:46
2904D7 | 2904 | 14520 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:28 | May 04, 2026 @ 17:28
2903F2 | 2903 | 14509 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:02 | Jun 08, 2026 @ 09:02
2903D4 | 2903 | 14507 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 08:43 | Jul 17, 2026 @ 08:43
2903D2 | 2903 | 14502 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 08:43 | Jul 17, 2026 @ 08:43
2903F3 | 2903 | 14499 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:06 | Jun 08, 2026 @ 09:06
2903C2 | 2903 | 14493 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 17, 2026 @ 08:43 | Jul 17, 2026 @ 08:43
2903D7 | 2903 | 14491 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:28 | May 04, 2026 @ 17:28
2902F2 | 2902 | 14480 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:02 | Jun 08, 2026 @ 09:02
2902D4 | 2902 | 14478 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 17:16 | Jul 24, 2026 @ 17:16
2902D2 | 2902 | 14473 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 25, 2026 @ 08:38 | Jul 25, 2026 @ 08:38
2902F3 | 2902 | 14470 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:06 | Jun 08, 2026 @ 09:06
2902C2 | 2902 | 14464 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 14:21 | Jul 24, 2026 @ 14:21
2902D7 | 2902 | 14462 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:27 | May 04, 2026 @ 17:27
2901F2 | 2901 | 14451 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2901 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:02 | Jun 08, 2026 @ 09:02
2901D4 | 2901 | 14449 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2901 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 17:17 | Jul 24, 2026 @ 17:17
2901D2 | 2901 | 14444 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2901 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 17:22 | Jul 24, 2026 @ 17:22
2901F3 | 2901 | 14441 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2901 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 08, 2026 @ 09:06 | Jun 08, 2026 @ 09:06
2901C2 | 2901 | 14435 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2901 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:04 | Jul 23, 2026 @ 12:04
2901D7 | 2901 | 14433 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2901 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 04, 2026 @ 17:27 | May 04, 2026 @ 17:27
2810F2 | 2810 | 14422 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2810 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:19 | Jun 05, 2026 @ 18:19
2810D4 | 2810 | 14420 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2810 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 12:37 | Jul 17, 2026 @ 12:37
2810D2 | 2810 | 14415 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2810 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 12:37 | Jul 17, 2026 @ 12:37
2810F3 | 2810 | 14412 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2810 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:19 | Jun 05, 2026 @ 18:19
2810C2 | 2810 | 14406 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2810 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 17, 2026 @ 12:36 | Jul 17, 2026 @ 12:36
2810D7 | 2810 | 14404 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2810 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:42 | Jun 06, 2026 @ 12:42
2809F2 | 2809 | 14393 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:19 | Jun 05, 2026 @ 18:19
2809D4 | 2809 | 14391 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2809D2 | 2809 | 14386 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:05 | Jul 23, 2026 @ 12:05
2809F3 | 2809 | 14383 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:19 | Jun 05, 2026 @ 18:19
2809C2 | 2809 | 14377 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 18:18 | Jul 27, 2026 @ 18:18
2809D7 | 2809 | 14375 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:41 | Jun 06, 2026 @ 12:41
2808F2 | 2808 | 14364 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:20 | Jun 05, 2026 @ 18:20
2808D4 | 2808 | 14362 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 16:09 | Jul 16, 2026 @ 16:09
2808D2 | 2808 | 14357 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 16:09 | Jul 16, 2026 @ 16:09
2808F3 | 2808 | 14354 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:20 | Jun 05, 2026 @ 18:20
2808C2 | 2808 | 14348 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 16:08 | Jul 16, 2026 @ 16:08
2808D7 | 2808 | 14346 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:41 | Jun 06, 2026 @ 12:41
2807F2 | 2807 | 14335 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:20 | Jun 05, 2026 @ 18:20
2807D4 | 2807 | 14333 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 08:40 | Jul 16, 2026 @ 08:40
2807D2 | 2807 | 14328 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 08:40 | Jul 16, 2026 @ 08:40
2807F3 | 2807 | 14325 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:21 | Jun 05, 2026 @ 18:21
2807C2 | 2807 | 14319 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 08:40 | Jul 16, 2026 @ 08:40
2807D7 | 2807 | 14317 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:40 | Jun 06, 2026 @ 12:40
2806F2 | 2806 | 14306 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:21 | Jun 05, 2026 @ 18:21
2806D4 | 2806 | 14304 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 13:57 | Jul 16, 2026 @ 13:57
2806D2 | 2806 | 14299 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 16, 2026 @ 13:57 | Jul 16, 2026 @ 13:57
2806F3 | 2806 | 14296 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:21 | Jun 05, 2026 @ 18:21
2806C2 | 2806 | 14290 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 16, 2026 @ 13:57 | Jul 16, 2026 @ 13:57
2806D7 | 2806 | 14288 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:40 | Jun 06, 2026 @ 12:40
2805F2 | 2805 | 14277 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:21 | Jun 05, 2026 @ 18:21
2805D4 | 2805 | 14275 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2805D2 | 2805 | 14270 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 12:05 | Jul 23, 2026 @ 12:05
2805F3 | 2805 | 14267 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:21 | Jun 05, 2026 @ 18:21
2805C2 | 2805 | 14261 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 15:19 | Jul 23, 2026 @ 13:42
2805D7 | 2805 | 14259 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:39 | Jun 06, 2026 @ 12:39
2804F2 | 2804 | 14248 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:22 | Jun 05, 2026 @ 18:22
2804D4 | 2804 | 14246 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:26 | Jul 10, 2026 @ 11:26
2804D2 | 2804 | 14241 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2804F3 | 2804 | 14238 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:22 | Jun 05, 2026 @ 18:22
2804C2 | 2804 | 14232 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2804D7 | 2804 | 14230 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:39 | Jun 06, 2026 @ 12:39
2709F2 | 2709 | 14219 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2709 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:47 | May 21, 2026 @ 16:47
2709D4 | 2709 | 14217 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2709 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 17:16 | Jul 13, 2026 @ 17:16
2709D2 | 2709 | 14212 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2709 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 17:16 | Jul 13, 2026 @ 17:16
2709F3 | 2709 | 14209 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2709 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:47 | May 21, 2026 @ 16:47
2709C2 | 2709 | 14203 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2709 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 17:15 | Jul 13, 2026 @ 17:15
2709D7 | 2709 | 14201 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2709 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:24 | May 11, 2026 @ 10:24
2803F2 | 2803 | 14190 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:22 | Jun 05, 2026 @ 18:22
2803D4 | 2803 | 14188 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2803D2 | 2803 | 14183 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2803F3 | 2803 | 14180 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:22 | Jun 05, 2026 @ 18:22
2803C2 | 2803 | 14174 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2803D7 | 2803 | 14172 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:38 | Jun 06, 2026 @ 12:38
2802F2 | 2802 | 14161 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:22 | Jun 05, 2026 @ 18:22
2802D4 | 2802 | 14159 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2802D2 | 2802 | 14154 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 14:15 | Jul 20, 2026 @ 14:15
2802F3 | 2802 | 14151 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:23 | Jun 05, 2026 @ 18:23
2802C2 | 2802 | 14145 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 14:15 | Jul 20, 2026 @ 14:15
2802D7 | 2802 | 14143 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:41 | Jun 01, 2026 @ 14:41
2801F2 | 2801 | 14132 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:23 | Jun 05, 2026 @ 18:23
2801D4 | 2801 | 14130 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 10:53 | Jul 20, 2026 @ 10:53
2801D2 | 2801 | 14125 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 10:52 | Jul 20, 2026 @ 10:52
2801F3 | 2801 | 14122 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 05, 2026 @ 18:23 | Jun 05, 2026 @ 18:23
2801C2 | 2801 | 14116 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 10:52 | Jul 20, 2026 @ 10:52
2801D7 | 2801 | 14114 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:40 | Jun 01, 2026 @ 14:40
2708F2 | 2708 | 14103 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:48 | May 21, 2026 @ 16:48
2708D4 | 2708 | 14101 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 17:08 | Jul 13, 2026 @ 17:08
2708D2 | 2708 | 14096 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 17:08 | Jul 13, 2026 @ 17:08
2708F3 | 2708 | 14093 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:48 | May 21, 2026 @ 16:48
2708C2 | 2708 | 14087 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 17:08 | Jul 13, 2026 @ 17:08
2708D7 | 2708 | 14085 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:23 | May 11, 2026 @ 10:23
2707F2 | 2707 | 14074 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:48 | May 21, 2026 @ 16:48
2707D4 | 2707 | 14072 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 18:28 | Jul 17, 2026 @ 18:28
2707D2 | 2707 | 14067 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 18:28 | Jul 17, 2026 @ 18:28
2707F3 | 2707 | 14064 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2707C2 | 2707 | 14058 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 17, 2026 @ 18:20 | Jul 17, 2026 @ 18:20
2707D7 | 2707 | 14056 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:22 | May 11, 2026 @ 10:22
2706F2 | 2706 | 14045 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2706D4 | 2706 | 14043 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 16:52 | Jul 13, 2026 @ 16:52
2706D2 | 2706 | 14038 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 16:52 | Jul 13, 2026 @ 16:52
2706F3 | 2706 | 14035 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2706C2 | 2706 | 14029 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 16:51 | Jul 13, 2026 @ 16:51
2706D7 | 2706 | 14027 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:22 | May 11, 2026 @ 10:22
2705F2 | 2705 | 14016 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2705D4 | 2705 | 14014 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2705D2 | 2705 | 14009 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:43 | Jul 23, 2026 @ 09:43
2705F3 | 2705 | 14006 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2705C2 | 2705 | 14000 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:05 | Jul 23, 2026 @ 12:05
2705D7 | 2705 | 13998 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:22 | May 11, 2026 @ 10:22
2704F2 | 2704 | 13987 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:49 | May 21, 2026 @ 16:49
2704D4 | 2704 | 13985 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 18:20 | Jul 22, 2026 @ 18:20
2704D2 | 2704 | 13980 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 09:48 | Jul 14, 2026 @ 09:48
2704F3 | 2704 | 13977 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:50 | May 21, 2026 @ 16:50
2704C2 | 2704 | 13971 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 14, 2026 @ 09:47 | Jul 14, 2026 @ 09:47
2704D7 | 2704 | 13969 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:21 | May 11, 2026 @ 10:21
2703F2 | 2703 | 13958 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:50 | May 21, 2026 @ 16:50
2703D4 | 2703 | 13956 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:32 | Jul 09, 2026 @ 18:32
2703D2 | 2703 | 13951 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:34 | Jul 09, 2026 @ 18:34
2703F3 | 2703 | 13948 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:50 | May 21, 2026 @ 16:50
2703C2 | 2703 | 13942 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 09, 2026 @ 18:32 | Jul 09, 2026 @ 18:32
2703D7 | 2703 | 13940 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:21 | May 11, 2026 @ 10:21
2702F2 | 2702 | 13929 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:50 | May 21, 2026 @ 16:50
2702D4 | 2702 | 13927 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2702D2 | 2702 | 13922 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2702F3 | 2702 | 13919 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:50 | May 21, 2026 @ 16:50
2702C2 | 2702 | 13913 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2702D7 | 2702 | 13911 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:21 | May 11, 2026 @ 10:21
2701F2 | 2701 | 13900 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:51 | May 21, 2026 @ 16:51
2701D4 | 2701 | 13898 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 16:46 | Jul 17, 2026 @ 16:46
2701D2 | 2701 | 13893 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 17, 2026 @ 16:46 | Jul 17, 2026 @ 16:46
2701F3 | 2701 | 13890 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:51 | May 21, 2026 @ 16:51
2701C2 | 2701 | 13884 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 17, 2026 @ 16:45 | Jul 17, 2026 @ 16:45
2701D7 | 2701 | 13882 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:20 | May 11, 2026 @ 10:20
2610F2 | 2610 | 13871 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 09:13 | May 21, 2026 @ 16:51
2610D4 | 2610 | 13869 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2610 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 15, 2026 @ 17:16 | Jul 15, 2026 @ 17:16
2610D2 | 2610 | 13864 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2610 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 15, 2026 @ 17:16 | Jul 15, 2026 @ 17:16
2610F3 | 2610 | 13861 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 16:52 | May 21, 2026 @ 16:52
2610C2 | 2610 | 13855 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 15, 2026 @ 17:15 | Jul 15, 2026 @ 17:15
2610D7 | 2610 | 13853 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2610 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:20 | May 11, 2026 @ 10:20
2609F2 | 2609 | 13842 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 21, 2026 @ 15:56 | Jul 21, 2026 @ 15:56
2609D4 | 2609 | 13840 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:44 | Jul 23, 2026 @ 09:44
2609D2 | 2609 | 13835 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:44 | Jul 23, 2026 @ 09:44
2609F3 | 2609 | 13832 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 17:14 | May 21, 2026 @ 17:14
2609C2 | 2609 | 13826 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:05 | Jul 23, 2026 @ 12:05
2609D7 | 2609 | 13824 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 16:48 | Jun 02, 2026 @ 16:48
2608F2 | 2608 | 13813 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 17:15 | May 21, 2026 @ 17:15
2608D4 | 2608 | 13811 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:07 | Jul 13, 2026 @ 12:07
2608D2 | 2608 | 13806 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:08 | Jul 13, 2026 @ 12:08
2608F3 | 2608 | 13803 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 21, 2026 @ 17:15 | May 21, 2026 @ 17:15
2608C2 | 2608 | 13797 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:15 | Jul 13, 2026 @ 12:15
2608D7 | 2608 | 13795 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:19 | May 11, 2026 @ 10:19
2607F2 | 2607 | 13784 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 22, 2026 @ 14:06 | May 22, 2026 @ 14:06
2607D4 | 2607 | 13782 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:08 | Jul 13, 2026 @ 12:08
2607D2 | 2607 | 13777 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:08 | Jul 13, 2026 @ 12:08
2607F3 | 2607 | 13774 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 22, 2026 @ 14:06 | May 22, 2026 @ 14:06
2607C2 | 2607 | 13768 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:19 | Jul 13, 2026 @ 12:19
2607D7 | 2607 | 13766 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:19 | May 11, 2026 @ 10:19
2606F2 | 2606 | 13755 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 22, 2026 @ 14:07 | May 22, 2026 @ 14:07
2606D4 | 2606 | 13753 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:08 | Jul 13, 2026 @ 12:08
2606D2 | 2606 | 13748 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:09 | Jul 13, 2026 @ 12:09
2606F3 | 2606 | 13745 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 22, 2026 @ 14:07 | May 22, 2026 @ 14:07
2606C2 | 2606 | 13739 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:19 | Jul 13, 2026 @ 12:19
2606D7 | 2606 | 13737 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:19 | May 11, 2026 @ 10:19
2605F2 | 2605 | 13726 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:29 | May 23, 2026 @ 09:29
2605D4 | 2605 | 13724 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:44 | Jul 23, 2026 @ 09:44
2605D2 | 2605 | 13719 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:44 | Jul 23, 2026 @ 09:44
2605F3 | 2605 | 13716 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:29 | May 23, 2026 @ 09:29
2605C2 | 2605 | 13710 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:06 | Jul 23, 2026 @ 12:06
2605D7 | 2605 | 13708 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 16:50 | Jun 02, 2026 @ 16:50
2604F2 | 2604 | 13697 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:30 | May 23, 2026 @ 09:30
2604D4 | 2604 | 13695 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:01 | Jul 08, 2026 @ 13:08
2604D2 | 2604 | 13690 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:02 | Jul 08, 2026 @ 13:07
2604F3 | 2604 | 13687 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:30 | May 23, 2026 @ 09:30
2604C2 | 2604 | 13681 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 08, 2026 @ 18:10 | Jul 08, 2026 @ 13:07
2604D7 | 2604 | 13679 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:17 | May 11, 2026 @ 10:17
2603F2 | 2603 | 13668 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:50 | May 11, 2026 @ 16:50
2603D4 | 2603 | 13666 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 07:15 | Jul 08, 2026 @ 13:07
2603D2 | 2603 | 13661 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:01 | Jul 08, 2026 @ 13:01
2603F3 | 2603 | 13658 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:01 | May 11, 2026 @ 17:01
2603C2 | 2603 | 13652 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 08, 2026 @ 13:00 | Jul 08, 2026 @ 13:00
2603D7 | 2603 | 13650 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:17 | May 11, 2026 @ 10:17
2602F2 | 2602 | 13639 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:50 | May 11, 2026 @ 16:50
2602D4 | 2602 | 13637 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:45 | Jul 23, 2026 @ 09:45
2602D2 | 2602 | 13632 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:45 | Jul 23, 2026 @ 09:45
2602F3 | 2602 | 13629 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:01 | May 11, 2026 @ 17:01
2602C2 | 2602 | 13623 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:06 | Jul 23, 2026 @ 12:06
2602D7 | 2602 | 13621 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:17 | May 11, 2026 @ 10:17
2601F2 | 2601 | 13610 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:50 | May 11, 2026 @ 16:50
2601D4 | 2601 | 13608 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:45 | Jul 23, 2026 @ 09:45
2601D2 | 2601 | 13603 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:45 | Jul 23, 2026 @ 09:45
2601F3 | 2601 | 13600 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:02 | May 11, 2026 @ 17:02
2601C2 | 2601 | 13594 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:06 | Jul 23, 2026 @ 12:06
2601D7 | 2601 | 13592 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 10:16 | May 11, 2026 @ 10:16
2509F2 | 2509 | 13581 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:54 | May 11, 2026 @ 16:51
2509D4 | 2509 | 13579 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2509 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:09 | Jul 13, 2026 @ 12:09
2509D2 | 2509 | 13574 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2509 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:09 | Jul 13, 2026 @ 12:09
2509F3 | 2509 | 13571 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:02 | May 11, 2026 @ 17:02
2509C2 | 2509 | 13565 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:20 | Jul 13, 2026 @ 12:20
2509D7 | 2509 | 13563 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2509 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:59 | May 09, 2026 @ 17:59
2508F2 | 2508 | 13552 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:54 | May 11, 2026 @ 16:54
2508D4 | 2508 | 13550 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2508D2 | 2508 | 13545 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2508F3 | 2508 | 13542 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:02 | May 11, 2026 @ 17:02
2508C2 | 2508 | 13536 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2508D7 | 2508 | 13534 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:58 | May 09, 2026 @ 17:58
2507F2 | 2507 | 13523 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:54 | May 11, 2026 @ 16:54
2507D4 | 2507 | 13521 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:17 | Jul 09, 2026 @ 18:17
2507D2 | 2507 | 13516 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:17 | Jul 09, 2026 @ 18:17
2507F3 | 2507 | 13513 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:02 | May 11, 2026 @ 17:02
2507C2 | 2507 | 13507 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 09, 2026 @ 18:17 | Jul 09, 2026 @ 18:17
2507D7 | 2507 | 13505 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:58 | May 09, 2026 @ 17:58
2506F2 | 2506 | 13494 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:54 | May 11, 2026 @ 16:54
2506D4 | 2506 | 13492 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:09 | Jul 13, 2026 @ 12:09
2506D2 | 2506 | 13487 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 12:09 | Jul 13, 2026 @ 12:09
2506F3 | 2506 | 13484 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:02 | May 11, 2026 @ 17:02
2506C2 | 2506 | 13478 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:20 | Jul 13, 2026 @ 12:20
2506D7 | 2506 | 13476 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:58 | May 09, 2026 @ 17:58
2505F2 | 2505 | 13465 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:55 | May 11, 2026 @ 16:55
2505D4 | 2505 | 13463 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:45 | Jul 23, 2026 @ 09:45
2505D2 | 2505 | 13458 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2505F3 | 2505 | 13455 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:03 | May 11, 2026 @ 17:03
2505C2 | 2505 | 13449 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:06 | Jul 23, 2026 @ 12:06
2505D7 | 2505 | 13447 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:57 | May 09, 2026 @ 17:57
2504F2 | 2504 | 13436 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:56 | May 11, 2026 @ 16:56
2504D4 | 2504 | 13434 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 12:20 | Jul 07, 2026 @ 12:20
2504D2 | 2504 | 13429 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 12:20 | Jul 07, 2026 @ 12:20
2504F3 | 2504 | 13426 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:03 | May 11, 2026 @ 17:03
2504C2 | 2504 | 13420 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 06, 2026 @ 18:55 | Jul 06, 2026 @ 18:55
2504D7 | 2504 | 13418 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:57 | May 09, 2026 @ 17:57
2503F2 | 2503 | 13407 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:56 | May 11, 2026 @ 16:56
2503D4 | 2503 | 13405 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 17:06 | Jul 07, 2026 @ 17:06
2503D2 | 2503 | 13400 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 17:06 | Jul 07, 2026 @ 17:06
2503F3 | 2503 | 13397 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:03 | May 11, 2026 @ 17:03
2503C2 | 2503 | 13391 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 07, 2026 @ 14:17 | Jul 07, 2026 @ 14:17
2503D7 | 2503 | 13389 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:57 | May 09, 2026 @ 17:57
2502F2 | 2502 | 13378 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 16:57 | May 11, 2026 @ 16:57
2502D4 | 2502 | 13376 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2502D2 | 2502 | 13371 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2502F3 | 2502 | 13368 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:03 | May 11, 2026 @ 17:03
2502C2 | 2502 | 13362 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:07 | Jul 23, 2026 @ 12:07
2502D7 | 2502 | 13360 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:56 | May 09, 2026 @ 17:56
2501F2 | 2501 | 13349 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:00 | May 11, 2026 @ 16:57
2501D4 | 2501 | 13347 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2501D2 | 2501 | 13342 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2501F3 | 2501 | 13339 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 11, 2026 @ 17:03 | May 11, 2026 @ 17:03
2501C2 | 2501 | 13333 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 25, 2026 @ 17:01 | Jul 25, 2026 @ 17:01
2501D7 | 2501 | 13331 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 17:56 | May 09, 2026 @ 17:56
2410F2 | 2410 | 13320 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:32 | May 09, 2026 @ 13:32
2410D4 | 2410 | 13318 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2410 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 08:36 | Jul 13, 2026 @ 08:36
2410D2 | 2410 | 13313 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2410 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 13, 2026 @ 08:37 | Jul 13, 2026 @ 08:37
2410F3 | 2410 | 13310 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:39 | May 09, 2026 @ 13:39
2410C2 | 2410 | 13304 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:20 | Jul 13, 2026 @ 12:20
2410D7 | 2410 | 13302 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2410 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:44 | May 09, 2026 @ 12:44
2409F2 | 2409 | 13291 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 11 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:33 | May 09, 2026 @ 13:33
2409D4 | 2409 | 13289 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2409D2 | 2409 | 13284 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2409F3 | 2409 | 13281 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 02, 2026 @ 15:36 | Jun 02, 2026 @ 15:36
2409C2 | 2409 | 13275 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:14 | Jul 23, 2026 @ 12:14
2409D7 | 2409 | 13273 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:43 | May 09, 2026 @ 12:43
2408F2 | 2408 | 13262 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:33 | May 09, 2026 @ 13:33
2408D4 | 2408 | 13260 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2408D2 | 2408 | 13255 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2408F3 | 2408 | 13252 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:40 | May 09, 2026 @ 13:40
2408C2 | 2408 | 13246 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2408D7 | 2408 | 13244 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:43 | May 09, 2026 @ 12:41
2407F2 | 2407 | 13233 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:33 | May 09, 2026 @ 13:33
2407D4 | 2407 | 13231 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:26 | Jul 10, 2026 @ 11:26
2407D2 | 2407 | 13226 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2407F3 | 2407 | 13223 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:40 | May 09, 2026 @ 13:40
2407C2 | 2407 | 13217 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 10, 2026 @ 11:26 | Jul 10, 2026 @ 11:26
2407D7 | 2407 | 13215 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:41 | May 09, 2026 @ 12:41
2406F2 | 2406 | 13204 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:33 | May 09, 2026 @ 13:33
2406D4 | 2406 | 13202 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:00 | Jul 08, 2026 @ 17:01
2406D2 | 2406 | 13197 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:00 | Jul 08, 2026 @ 17:01
2406F3 | 2406 | 13194 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2406C2 | 2406 | 13188 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 08, 2026 @ 17:01 | Jul 08, 2026 @ 17:01
2406D7 | 2406 | 13186 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:40 | May 09, 2026 @ 12:40
2405F2 | 2405 | 13175 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:34 | May 09, 2026 @ 13:34
2405D4 | 2405 | 13173 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:46 | Jul 23, 2026 @ 09:46
2405D2 | 2405 | 13168 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:50 | Jul 23, 2026 @ 09:50
2405F3 | 2405 | 13165 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2405C2 | 2405 | 13159 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:09 | Jul 23, 2026 @ 12:09
2405D7 | 2405 | 13157 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:40 | May 09, 2026 @ 12:40
2309F2 | 2309 | 13146 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:30 | May 23, 2026 @ 09:30
2309D4 | 2309 | 13144 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2309 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 17:58 | Jul 10, 2026 @ 17:58
2309D2 | 2309 | 13139 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2309 _Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 17:59 | Jul 10, 2026 @ 17:59
2309F3 | 2309 | 13136 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 23, 2026 @ 09:30 | May 23, 2026 @ 09:30
2309D7 | 2309 | 13128 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:42 | May 09, 2026 @ 11:42
2404F2 | 2404 | 13117 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:34 | May 09, 2026 @ 13:34
2404D4 | 2404 | 13115 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 17:07 | Jul 07, 2026 @ 17:07
2404D2 | 2404 | 13110 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 14:53 | Jul 07, 2026 @ 17:07
2404F3 | 2404 | 13107 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2404C2 | 2404 | 13101 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 07, 2026 @ 14:18 | Jul 07, 2026 @ 14:18
2404D7 | 2404 | 13099 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:39 | May 09, 2026 @ 12:39
2403F2 | 2403 | 13087 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:34 | May 09, 2026 @ 13:34
2403D4 | 2403 | 13085 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 17:07 | Jul 07, 2026 @ 17:07
2403D2 | 2403 | 13080 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 14:53 | Jul 07, 2026 @ 17:07
2403F3 | 2403 | 13077 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2403C2 | 2403 | 13071 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 07, 2026 @ 14:19 | Jul 07, 2026 @ 14:19
2403D7 | 2403 | 13069 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:39 | May 09, 2026 @ 12:39
2402F2 | 2402 | 13058 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:34 | May 09, 2026 @ 13:34
2402D4 | 2402 | 13056 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:25 | Jul 09, 2026 @ 18:25
2402D2 | 2402 | 13051 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 18:24 | Jul 09, 2026 @ 18:24
2402F3 | 2402 | 13048 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2402C2 | 2402 | 13042 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 09, 2026 @ 18:24 | Jul 09, 2026 @ 18:24
2402D7 | 2402 | 13040 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 12:38 | May 09, 2026 @ 12:38
2401F2 | 2401 | 13029 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:34 | May 09, 2026 @ 13:34
2401D4 | 2401 | 13027 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:52 | Jul 23, 2026 @ 09:52
2401D2 | 2401 | 13022 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:52 | Jul 23, 2026 @ 09:52
2401F3 | 2401 | 13019 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:41 | May 09, 2026 @ 13:41
2401C2 | 2401 | 13013 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 18:18 | Jul 27, 2026 @ 18:18
2401D7 | 2401 | 13011 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:43 | May 09, 2026 @ 11:43
2010F2 | 2010 | 13000 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:36 | May 04, 2026 @ 09:36
2010D4 | 2010 | 12998 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2010_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:05 | Jul 20, 2026 @ 18:05
2010D2 | 2010 | 12993 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2010_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:05 | Jul 20, 2026 @ 18:05
2010F3 | 2010 | 12990 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:50 | May 05, 2026 @ 08:50
2010C2 | 2010 | 12984 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:06 | Jul 20, 2026 @ 18:06
2010D7 | 2010 | 12982 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:16 | Apr 29, 2026 @ 12:16
2009F2 | 2009 | 12971 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 14:57 | Jun 06, 2026 @ 14:57
2009D4 | 2009 | 12969 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2009D2 | 2009 | 12964 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:52 | Jul 23, 2026 @ 09:52
2009F3 | 2009 | 12961 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:43 | May 05, 2026 @ 08:43
2009C2 | 2009 | 12955 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:13 | Jul 23, 2026 @ 12:13
2009D7 | 2009 | 12953 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 08:32 | Jun 23, 2026 @ 08:32
2008F2 | 2008 | 12942 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:36 | May 04, 2026 @ 09:36
2008D4 | 2008 | 12940 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 17:17 | Jul 24, 2026 @ 17:17
2008D2 | 2008 | 12935 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:53 | Jul 23, 2026 @ 09:53
2008F3 | 2008 | 12932 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:42 | May 05, 2026 @ 08:42
2008C2 | 2008 | 12926 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:13 | Jul 23, 2026 @ 12:13
2008D7 | 2008 | 12924 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:15 | Apr 29, 2026 @ 12:15
2007F2 | 2007 | 12913 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:36 | May 04, 2026 @ 09:36
2007D4 | 2007 | 12911 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:07 | Jul 20, 2026 @ 18:07
2007D2 | 2007 | 12906 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:07 | Jul 20, 2026 @ 18:07
2007F3 | 2007 | 12903 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:42 | May 05, 2026 @ 08:42
2007C2 | 2007 | 12897 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:08 | Jul 20, 2026 @ 18:08
2007D7 | 2007 | 12895 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:14 | Apr 29, 2026 @ 12:14
2006F2 | 2006 | 12884 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 14:57 | Jun 06, 2026 @ 14:57
2006D4 | 2006 | 12882 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:08 | Jul 20, 2026 @ 18:08
2006D2 | 2006 | 12877 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 20, 2026 @ 18:08 | Jul 20, 2026 @ 18:08
2006F3 | 2006 | 12874 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:41 | May 05, 2026 @ 08:41
2006C2 | 2006 | 12868 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 20, 2026 @ 18:08 | Jul 20, 2026 @ 18:08
2006D7 | 2006 | 12866 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 16:51 | Jun 02, 2026 @ 16:51
2005F2 | 2005 | 12855 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:37 | May 04, 2026 @ 09:37
2005D4 | 2005 | 12853 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2005D2 | 2005 | 12848 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:54 | Jul 23, 2026 @ 09:54
2005F3 | 2005 | 12845 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:40 | May 05, 2026 @ 08:40
2005C2 | 2005 | 12839 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:13 | Jul 23, 2026 @ 12:13
2005D7 | 2005 | 12837 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:21 | Apr 29, 2026 @ 12:13
2003F2 | 2003 | 12826 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:37 | May 04, 2026 @ 09:37
2003D4 | 2003 | 12824 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2003D2 | 2003 | 12819 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:54 | Jul 23, 2026 @ 09:54
2003F3 | 2003 | 12816 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:40 | May 05, 2026 @ 08:40
2003C2 | 2003 | 12810 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:13 | Jul 23, 2026 @ 12:13
2003D7 | 2003 | 12808 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:13 | Apr 29, 2026 @ 12:13
2309C2 | 2309 | 12781 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2309 _Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 18:34 | Jul 13, 2026 @ 18:34
2308F2 | 2308 | 12768 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:35 | May 09, 2026 @ 13:35
2308D4 | 2308 | 12766 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2308D2 | 2308 | 12761 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 11:15 | Jul 09, 2026 @ 11:15
2308F3 | 2308 | 12758 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2308C2 | 2308 | 12752 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 09, 2026 @ 11:31 | Jul 09, 2026 @ 11:31
2308D7 | 2308 | 12750 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:42 | May 09, 2026 @ 11:42
2307F2 | 2307 | 12739 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:35 | May 09, 2026 @ 13:35
2307D4 | 2307 | 12737 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 17:59 | Jul 10, 2026 @ 17:59
2307D2 | 2307 | 12732 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 17:59 | Jul 10, 2026 @ 17:59
2307F3 | 2307 | 12729 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2307C2 | 2307 | 12723 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:21 | Jul 13, 2026 @ 12:21
2307D7 | 2307 | 12721 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:42 | May 09, 2026 @ 11:42
2306F2 | 2306 | 12710 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:35 | May 09, 2026 @ 13:35
2306D4 | 2306 | 12708 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:00 | Jul 10, 2026 @ 18:00
2306D2 | 2306 | 12703 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:00 | Jul 10, 2026 @ 18:00
2306F3 | 2306 | 12700 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2306C2 | 2306 | 12694 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:21 | Jul 13, 2026 @ 12:21
2306D7 | 2306 | 12692 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:41 | May 09, 2026 @ 11:41
2305F2 | 2305 | 12681 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:35 | May 09, 2026 @ 13:35
2305D4 | 2305 | 12679 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:00 | Jul 10, 2026 @ 18:00
2305D2 | 2305 | 12674 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:01 | Jul 10, 2026 @ 18:01
2305F3 | 2305 | 12671 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2305C2 | 2305 | 12665 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:22 | Jul 13, 2026 @ 12:22
2305D7 | 2305 | 12663 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:41 | May 09, 2026 @ 11:41
2304F2 | 2304 | 12652 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:35 | May 09, 2026 @ 13:35
2304D4 | 2304 | 12650 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 17:08 | Jul 07, 2026 @ 17:08
2304D2 | 2304 | 12645 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 14:37 | Jul 07, 2026 @ 14:37
2304F3 | 2304 | 12642 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2304C2 | 2304 | 12636 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 07, 2026 @ 17:08 | Jul 07, 2026 @ 17:08
2304D7 | 2304 | 12634 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:41 | May 09, 2026 @ 11:41
2303F2 | 2303 | 12623 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:36 | May 09, 2026 @ 13:36
2303D4 | 2303 | 12621 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 12:19 | Jul 07, 2026 @ 12:19
2303D2 | 2303 | 12616 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 12:19 | Jul 07, 2026 @ 12:19
2303F3 | 2303 | 12613 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:42 | May 09, 2026 @ 13:42
2303C2 | 2303 | 12607 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 07, 2026 @ 12:19 | Jul 07, 2026 @ 12:19
2303D7 | 2303 | 12605 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:39 | May 09, 2026 @ 11:39
2302F2 | 2302 | 12594 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:36 | May 09, 2026 @ 13:36
2302D4 | 2302 | 12592 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:01 | Jul 10, 2026 @ 18:01
2302D2 | 2302 | 12587 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:02 | Jul 10, 2026 @ 18:02
2302F3 | 2302 | 12584 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
2302C2 | 2302 | 12578 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 21, 2026 @ 09:02 | Jul 13, 2026 @ 12:22
2302D7 | 2302 | 12576 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:39 | May 09, 2026 @ 11:39
2301F2 | 2301 | 12565 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:35 | May 09, 2026 @ 08:35
2301D4 | 2301 | 12563 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:02 | Jul 10, 2026 @ 18:02
2301D2 | 2301 | 12558 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:02 | Jul 10, 2026 @ 18:02
2301F3 | 2301 | 12555 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:52 | May 08, 2026 @ 17:52
2301C2 | 2301 | 12549 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 13, 2026 @ 12:23 | Jul 13, 2026 @ 12:23
2301D7 | 2301 | 12547 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:38 | May 09, 2026 @ 11:38
2210F2 | 2210 | 12536 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:50 | May 08, 2026 @ 17:50
2210D4 | 2210 | 12534 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2210D2 | 2210 | 12529 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2210F3 | 2210 | 12526 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:51 | May 08, 2026 @ 17:51
2210C2 | 2210 | 12520 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2210D7 | 2210 | 12518 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:38 | May 09, 2026 @ 11:38
2209F2 | 2209 | 12507 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 14:58 | Jun 06, 2026 @ 14:58
2209D4 | 2209 | 12505 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:03 | Jul 10, 2026 @ 18:03
2209D2 | 2209 | 12500 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:03 | Jul 10, 2026 @ 18:03
2209F3 | 2209 | 12497 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 14:58 | Jun 06, 2026 @ 14:58
2209C2 | 2209 | 12491 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2209D7 | 2209 | 12489 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:40 | May 09, 2026 @ 11:38
2208F2 | 2208 | 12478 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:51 | May 08, 2026 @ 17:51
2208D4 | 2208 | 12476 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 16:50 | Jul 08, 2026 @ 16:50
2208D2 | 2208 | 12471 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 16:49 | Jul 08, 2026 @ 16:49
2208F3 | 2208 | 12468 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:35 | May 09, 2026 @ 08:35
2208C2 | 2208 | 12462 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2208D7 | 2208 | 12460 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:37 | May 09, 2026 @ 11:37
2207F2 | 2207 | 12449 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:37 | May 09, 2026 @ 08:37
2207D4 | 2207 | 12447 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 16:32 | Jul 08, 2026 @ 16:32
2207D2 | 2207 | 12442 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 16:31 | Jul 08, 2026 @ 16:31
2207F3 | 2207 | 12439 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:38 | May 09, 2026 @ 08:38
2207C2 | 2207 | 12433 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2207D7 | 2207 | 12431 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:37 | May 09, 2026 @ 11:37
2206F2 | 2206 | 12420 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:41 | May 09, 2026 @ 08:41
2206D4 | 2206 | 12418 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:07 | Jul 08, 2026 @ 18:07
2206D2 | 2206 | 12413 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:06 | Jul 08, 2026 @ 18:06
2206F3 | 2206 | 12410 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:43 | May 09, 2026 @ 08:43
2206C2 | 2206 | 12404 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2206D7 | 2206 | 12402 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:36 | May 09, 2026 @ 11:36
2205F2 | 2205 | 12391 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:43 | May 09, 2026 @ 08:43
2205D4 | 2205 | 12389 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:03 | Jul 10, 2026 @ 18:03
2205D2 | 2205 | 12384 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:03 | Jul 10, 2026 @ 18:03
2205F3 | 2205 | 12381 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:44 | May 09, 2026 @ 08:44
2205C2 | 2205 | 12375 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2205D7 | 2205 | 12373 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:36 | May 09, 2026 @ 11:36
2204F2 | 2204 | 12362 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:44 | May 09, 2026 @ 08:44
2204D4 | 2204 | 12360 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 17:12 | Jul 08, 2026 @ 17:12
2204D2 | 2204 | 12355 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 17:12 | Jul 08, 2026 @ 17:12
2204F3 | 2204 | 12352 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:44 | May 09, 2026 @ 08:44
2204C2 | 2204 | 12346 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2204D7 | 2204 | 12344 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:35 | May 09, 2026 @ 11:35
2203F2 | 2203 | 12333 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:45 | May 09, 2026 @ 08:45
2203D4 | 2203 | 12331 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:51 | Jul 04, 2026 @ 12:51
2203D2 | 2203 | 12326 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:51 | Jul 04, 2026 @ 12:51
2203F3 | 2203 | 12323 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:45 | May 09, 2026 @ 08:45
2203C2 | 2203 | 12317 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2203D7 | 2203 | 12315 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:35 | May 09, 2026 @ 11:35
2202F2 | 2202 | 12304 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:45 | May 09, 2026 @ 08:45
2202D4 | 2202 | 12302 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:51 | Jul 04, 2026 @ 12:51
2202D2 | 2202 | 12297 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:51 | Jul 04, 2026 @ 12:52
2202F3 | 2202 | 12294 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:46 | May 09, 2026 @ 08:46
2202C2 | 2202 | 12288 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 12:39 | Jul 03, 2026 @ 12:39
2202D7 | 2202 | 12286 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:34 | May 09, 2026 @ 11:34
2201F2 | 2201 | 12275 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:46 | May 09, 2026 @ 08:46
2201D4 | 2201 | 12273 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:04 | Jul 10, 2026 @ 18:04
2201D2 | 2201 | 12268 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:04 | Jul 10, 2026 @ 18:04
2201F3 | 2201 | 12265 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:46 | May 09, 2026 @ 08:46
2201C2 | 2201 | 12259 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2201D7 | 2201 | 12257 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 09, 2026 @ 11:25 | May 09, 2026 @ 11:25
2109F2 | 2109 | 12246 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:40 | May 08, 2026 @ 17:39
2109D4 | 2109 | 12244 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:22 | Jul 08, 2026 @ 18:22
2109D2 | 2109 | 12239 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:22 | Jul 08, 2026 @ 18:22
2109F3 | 2109 | 12236 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 08, 2026 @ 17:40 | May 08, 2026 @ 17:40
2109C2 | 2109 | 12230 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2109D7 | 2109 | 12228 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:20 | Apr 29, 2026 @ 12:20
2108F2 | 2108 | 12217 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:38 | May 04, 2026 @ 09:38
2108D4 | 2108 | 12215 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:50 | Jul 07, 2026 @ 17:08
2108D2 | 2108 | 12210 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:50 | Jul 07, 2026 @ 17:08
2108F3 | 2108 | 12207 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:49 | May 05, 2026 @ 08:49
2108C2 | 2108 | 12201 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2108D7 | 2108 | 12199 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:19 | Apr 29, 2026 @ 12:19
2107F2 | 2107 | 12188 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:38 | May 04, 2026 @ 09:38
2107D4 | 2107 | 12186 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:04 | Jul 10, 2026 @ 18:04
2107D2 | 2107 | 12181 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 18:04 | Jul 10, 2026 @ 18:04
2107F3 | 2107 | 12178 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:48 | May 05, 2026 @ 08:48
2107C2 | 2107 | 12172 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2107D7 | 2107 | 12170 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:19 | Apr 29, 2026 @ 12:19
2106F2 | 2106 | 12159 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:39 | May 04, 2026 @ 09:39
2106D4 | 2106 | 12157 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:50 | Jul 07, 2026 @ 17:09
2106D2 | 2106 | 12152 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 12:50 | Jul 07, 2026 @ 17:11
2106F3 | 2106 | 12149 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:48 | May 05, 2026 @ 08:48
2106C2 | 2106 | 12143 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2106D7 | 2106 | 12141 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:19 | Apr 29, 2026 @ 12:19
2105F2 | 2105 | 12130 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:39 | May 04, 2026 @ 09:39
2105D4 | 2105 | 12128 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2105D2 | 2105 | 12123 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
2105F3 | 2105 | 12120 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:47 | May 05, 2026 @ 08:47
2105C2 | 2105 | 12114 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2105D7 | 2105 | 12112 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:18 | Apr 29, 2026 @ 12:18
2104F2 | 2104 | 12101 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:39 | May 04, 2026 @ 09:39
2104D4 | 2104 | 12099 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 11:30 | Jul 09, 2026 @ 11:30
2104D2 | 2104 | 12094 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 11:30 | Jul 09, 2026 @ 11:30
2104F3 | 2104 | 12091 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:46 | May 05, 2026 @ 08:46
2104C2 | 2104 | 12085 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2104D7 | 2104 | 12083 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:18 | Apr 29, 2026 @ 12:18
2103F2 | 2103 | 12072 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:40 | May 04, 2026 @ 09:40
2103D4 | 2103 | 12070 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 15:12 | Jul 08, 2026 @ 15:12
2103D2 | 2103 | 12065 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 15:11 | Jul 08, 2026 @ 15:11
2103F3 | 2103 | 12062 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:46 | May 05, 2026 @ 08:46
2103C2 | 2103 | 12056 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 12:35 | Jul 03, 2026 @ 12:35
2103D7 | 2103 | 12054 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:18 | Apr 29, 2026 @ 12:18
2102F2 | 2102 | 12043 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:40 | May 04, 2026 @ 09:40
2102D4 | 2102 | 12041 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:52 | Jul 08, 2026 @ 18:52
2102D2 | 2102 | 12036 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 08, 2026 @ 18:52 | Jul 08, 2026 @ 18:52
2102F3 | 2102 | 12033 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:45 | May 05, 2026 @ 08:45
2102C2 | 2102 | 12027 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 09:03 | Jul 03, 2026 @ 09:03
2102D7 | 2102 | 12025 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:17 | Apr 29, 2026 @ 12:17
2101F2 | 2101 | 12014 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:40 | May 04, 2026 @ 09:40
2101D4 | 2101 | 12012 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2101_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 09:48 | Jul 10, 2026 @ 09:48
2101D2 | 2101 | 12007 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 09, 2026 @ 11:30 | Jul 09, 2026 @ 11:30
2101F3 | 2101 | 12004 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:45 | May 05, 2026 @ 08:45
2101C2 | 2101 | 11998 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
2101D7 | 2101 | 11996 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:17 | Apr 29, 2026 @ 12:17
2001F2 | 2001 | 11985 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:41 | May 04, 2026 @ 09:41
2001D4 | 2001 | 11983 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
2001D2 | 2001 | 11978 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:54 | Jul 23, 2026 @ 09:54
2001F3 | 2001 | 11975 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:39 | May 05, 2026 @ 08:39
2001C2 | 2001 | 11969 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 2001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 23, 2026 @ 12:14 | Jul 23, 2026 @ 12:14
2001D7 | 2001 | 11967 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 2001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:12 | Apr 29, 2026 @ 12:12
1908F2 | 1908 | 11956 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 12, 2026 @ 17:59 | May 12, 2026 @ 17:59
1908D4 | 1908 | 11954 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1908_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1908D2 | 1908 | 11949 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1908_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1908F3 | 1908 | 11946 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 12, 2026 @ 18:00 | May 12, 2026 @ 18:00
1908C2 | 1908 | 11940 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1908D7 | 1908 | 11938 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 12, 2026 @ 13:39 | May 12, 2026 @ 13:39
1907F2 | 1907 | 11927 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 12, 2026 @ 18:00 | May 12, 2026 @ 18:00
1907D4 | 1907 | 11925 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 14:45 | Jun 03, 2026 @ 14:45
1907D2 | 1907 | 11920 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 14:45 | Jun 03, 2026 @ 14:45
1907F3 | 1907 | 11917 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:17 | May 04, 2026 @ 18:17
1907C2 | 1907 | 11911 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 03, 2026 @ 12:05 | Jun 03, 2026 @ 12:05
1907D7 | 1907 | 11909 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 12, 2026 @ 13:39 | May 12, 2026 @ 13:39
1906F2 | 1906 | 11898 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:41 | May 04, 2026 @ 09:41
1906D4 | 1906 | 11896 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1906D2 | 1906 | 11891 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1906F3 | 1906 | 11888 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:17 | May 04, 2026 @ 18:17
1906C2 | 1906 | 11882 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1906D7 | 1906 | 11880 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:24 | Apr 29, 2026 @ 12:24
1905F2 | 1905 | 11869 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:41 | May 04, 2026 @ 09:41
1905D4 | 1905 | 11867 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1905D2 | 1905 | 11862 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1905F3 | 1905 | 11859 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 08:52 | May 05, 2026 @ 08:52
1905C2 | 1905 | 11853 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1905D7 | 1905 | 11851 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:24 | Apr 29, 2026 @ 12:24
1904F2 | 1904 | 11840 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:42 | May 04, 2026 @ 09:42
1904D4 | 1904 | 11838 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1904D2 | 1904 | 11833 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1904F3 | 1904 | 11830 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:16 | May 04, 2026 @ 18:16
1904C2 | 1904 | 11824 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1904D7 | 1904 | 11822 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:23 | Apr 29, 2026 @ 12:23
1903F2 | 1903 | 11811 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:42 | May 04, 2026 @ 09:42
1903D4 | 1903 | 11809 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1903D2 | 1903 | 11804 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1903F3 | 1903 | 11801 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:16 | May 04, 2026 @ 18:16
1903C2 | 1903 | 11795 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 24, 2026 @ 14:06 | Jun 04, 2026 @ 18:20
1903D7 | 1903 | 11793 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:23 | Apr 29, 2026 @ 12:23
1902F2 | 1902 | 11782 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:43 | May 04, 2026 @ 09:43
1902D4 | 1902 | 11780 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1902D2 | 1902 | 11775 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1902F3 | 1902 | 11772 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:15 | May 04, 2026 @ 18:15
1902C2 | 1902 | 11766 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 02, 2026 @ 15:21 | Jun 02, 2026 @ 15:21
1902D7 | 1902 | 11764 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:23 | Apr 29, 2026 @ 12:23
1901F2 | 1901 | 11753 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:43 | May 04, 2026 @ 09:43
1901D4 | 1901 | 11751 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1901_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1901D2 | 1901 | 11746 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1901_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1901F3 | 1901 | 11743 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:15 | May 04, 2026 @ 18:15
1901C2 | 1901 | 11737 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 24, 2026 @ 14:23 | Jun 24, 2026 @ 14:23
1901D7 | 1901 | 11735 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 29, 2026 @ 12:22 | Apr 29, 2026 @ 12:22
1810F2 | 1810 | 11697 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:43 | May 04, 2026 @ 09:43
1810D4 | 1810 | 11694 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1810_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1810D2 | 1810 | 11684 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1810_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 15:03 | Jun 06, 2026 @ 15:03
1810F3 | 1810 | 11678 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:04 | May 04, 2026 @ 18:04
1810C2 | 1810 | 11667 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 17:39 | Jun 05, 2026 @ 17:39
1810D7 | 1810 | 11662 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:44 | Apr 24, 2026 @ 17:44
1809F2 | 1809 | 11650 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:43 | May 04, 2026 @ 09:43
1809D4 | 1809 | 11648 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1809D2 | 1809 | 11643 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 09, 2026 @ 09:15 | Jun 09, 2026 @ 09:15
1809F3 | 1809 | 11640 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:03 | May 04, 2026 @ 18:03
1809C2 | 1809 | 11634 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 11:04 | Jun 05, 2026 @ 11:04
1809D7 | 1809 | 11632 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 12:14 | Jun 02, 2026 @ 12:13
1808F2 | 1808 | 11621 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:44 | May 04, 2026 @ 09:44
1808D4 | 1808 | 11619 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1808D2 | 1808 | 11614 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1808F3 | 1808 | 11611 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:03 | May 04, 2026 @ 18:03
1808C2 | 1808 | 11605 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1808D7 | 1808 | 11603 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:43 | Apr 24, 2026 @ 17:43
1807F2 | 1807 | 11592 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:44 | May 04, 2026 @ 09:44
1807D4 | 1807 | 11590 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1807D2 | 1807 | 11585 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1807F3 | 1807 | 11582 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:02 | May 04, 2026 @ 18:02
1807C2 | 1807 | 11576 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1807D7 | 1807 | 11574 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:44 | Apr 24, 2026 @ 17:44
1010F3 | 1010 | 11558 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:54 | Apr 24, 2026 @ 14:54
1010F2 | 1010 | 11539 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:54 | Apr 24, 2026 @ 14:54
1010C2 | 1010 | 11536 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 09:03 | Jun 11, 2026 @ 09:03
1806F2 | 1806 | 11531 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:44 | May 04, 2026 @ 09:44
1806D4 | 1806 | 11528 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1010D2 | 1010 | 11525 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 09:02 | Jun 11, 2026 @ 09:02
1010D7 | 1010 | 11520 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:03 | Apr 22, 2026 @ 18:03
1010D4 | 1010 | 11518 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1010_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1806D2 | 1806 | 11517 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1806F3 | 1806 | 11512 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:02 | May 04, 2026 @ 18:02
1009F3 | 1009 | 11506 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:02 | Apr 24, 2026 @ 14:02
1806C2 | 1806 | 11501 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1806D7 | 1806 | 11497 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:39 | Apr 24, 2026 @ 17:39
1009F2 | 1009 | 11486 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 11 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:02 | Apr 24, 2026 @ 14:02
1009C2 | 1009 | 11485 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 09:01 | Jun 11, 2026 @ 09:01
1009D2 | 1009 | 11480 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | review | Planned Work | 1009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 0 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 08:15
1009D7 | 1009 | 11477 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1009_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:03 | Apr 22, 2026 @ 18:03
1009D4 | 1009 | 11476 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1009_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:14 | Aug 07, 2026 @ 13:14
1008F3 | 1008 | 11471 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:03 | Apr 24, 2026 @ 14:03
1805F2 | 1805 | 11451 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:44 | May 04, 2026 @ 09:44
1805D4 | 1805 | 11447 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1008F2 | 1008 | 11443 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:04 | Apr 24, 2026 @ 14:04
1008C2 | 1008 | 11441 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 09:01 | Jun 11, 2026 @ 09:01
1805D2 | 1805 | 11438 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 09, 2026 @ 09:17 | Jun 09, 2026 @ 09:17
1805F3 | 1805 | 11433 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:01 | May 04, 2026 @ 18:01
1008D2 | 1008 | 11429 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:21 | Jun 23, 2026 @ 10:21
1008D7 | 1008 | 11423 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:02 | Apr 22, 2026 @ 18:02
1805C2 | 1805 | 11422 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1008D4 | 1008 | 11421 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1008_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1805D7 | 1805 | 11418 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:57 | Jun 01, 2026 @ 14:57
1007F3 | 1007 | 11413 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:04 | Apr 24, 2026 @ 14:04
1007F2 | 1007 | 11399 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:01 | Apr 24, 2026 @ 14:01
1007C2 | 1007 | 11398 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 10, 2026 @ 15:13 | Jun 10, 2026 @ 15:13
1007D2 | 1007 | 11393 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 17:54 | Jun 12, 2026 @ 17:54
1007D7 | 1007 | 11390 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:02 | Apr 22, 2026 @ 18:02
1007D4 | 1007 | 11388 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1007_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1006F3 | 1006 | 11377 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:52 | Apr 24, 2026 @ 13:52
1804F2 | 1804 | 11372 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:45 | May 04, 2026 @ 09:45
1804D4 | 1804 | 11368 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1804D2 | 1804 | 11359 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1804F3 | 1804 | 11353 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:00 | May 04, 2026 @ 18:00
1006F2 | 1006 | 11348 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:51 | Apr 24, 2026 @ 13:51
1006C2 | 1006 | 11346 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 13:48 | Jun 10, 2026 @ 15:13
1804C2 | 1804 | 11342 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1804D7 | 1804 | 11337 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:38 | Apr 24, 2026 @ 17:38
1006D2 | 1006 | 11336 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:48 | Jun 11, 2026 @ 09:26
1006D7 | 1006 | 11332 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:02 | Apr 22, 2026 @ 18:02
1006D4 | 1006 | 11331 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1006_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 17:29 | Jun 11, 2026 @ 17:29
1005F3 | 1005 | 11326 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:51 | Apr 24, 2026 @ 13:51
1005F2 | 1005 | 11312 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:50 | Apr 24, 2026 @ 13:50
1005C2 | 1005 | 11311 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 10, 2026 @ 15:13 | Jun 10, 2026 @ 15:13
1005D2 | 1005 | 11305 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 10:46 | Jul 14, 2026 @ 10:46
1005D7 | 1005 | 11299 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 08:32 | Jun 06, 2026 @ 08:32
1005D4 | 1005 | 11297 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1005_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1803F2 | 1803 | 11289 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:45 | May 04, 2026 @ 09:45
1004F3 | 1004 | 11286 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:50 | Apr 24, 2026 @ 13:50
1803D4 | 1803 | 11285 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1803D2 | 1803 | 11275 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1803F3 | 1803 | 11269 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 18:00 | May 04, 2026 @ 18:00
1803C2 | 1803 | 11260 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1803D7 | 1803 | 11258 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:38 | Apr 24, 2026 @ 17:38
1004F2 | 1004 | 11254 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:49 | Apr 24, 2026 @ 13:49
1004C2 | 1004 | 11253 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 13:43 | Jun 10, 2026 @ 15:14
1004D2 | 1004 | 11248 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:39 | Jun 10, 2026 @ 17:07
1004D7 | 1004 | 11245 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:01 | Apr 22, 2026 @ 18:01
1004D4 | 1004 | 11244 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1004_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:43 | Jun 10, 2026 @ 17:10
1003F3 | 1003 | 11239 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:49 | Apr 24, 2026 @ 13:49
1003F2 | 1003 | 11216 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:48 | Apr 24, 2026 @ 13:48
1802F2 | 1802 | 11215 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:45 | May 04, 2026 @ 09:45
1003C2 | 1003 | 11213 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 13:43 | Jun 10, 2026 @ 15:15
1802D4 | 1802 | 11212 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1003D2 | 1003 | 11203 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 17:53 | Jun 12, 2026 @ 17:53
1802D2 | 1802 | 11202 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1003D7 | 1003 | 11197 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:00 | Apr 22, 2026 @ 18:00
1802F3 | 1802 | 11196 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:59 | May 04, 2026 @ 17:59
1003D4 | 1003 | 11195 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1003_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1802C2 | 1802 | 11185 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1002F3 | 1002 | 11184 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:48 | Apr 24, 2026 @ 13:48
1802D7 | 1802 | 11180 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:38 | Apr 24, 2026 @ 17:38
1002F2 | 1002 | 11167 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:44 | Apr 24, 2026 @ 13:44
1002C2 | 1002 | 11166 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 10, 2026 @ 15:16 | Jun 10, 2026 @ 15:16
1002D2 | 1002 | 11161 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:21 | Jun 23, 2026 @ 10:21
1002D7 | 1002 | 11158 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:00 | Apr 22, 2026 @ 18:00
1002D4 | 1002 | 11157 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1002_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 09:01 | Jun 23, 2026 @ 09:01
1001F3 | 1001 | 11152 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:46 | Apr 24, 2026 @ 13:46
1801F2 | 1801 | 11133 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:46 | May 04, 2026 @ 09:46
1801D4 | 1801 | 11129 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:34 | Jun 03, 2026 @ 15:34
1001F2 | 1001 | 11123 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 13:46 | Apr 24, 2026 @ 13:46
1001C2 | 1001 | 11122 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 09:23 | Jun 26, 2026 @ 09:23
1801D2 | 1801 | 11119 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 03, 2026 @ 15:24 | Jun 03, 2026 @ 15:24
1801F3 | 1801 | 11114 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:58 | May 04, 2026 @ 17:58
1001D2 | 1001 | 11111 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:21 | Jun 23, 2026 @ 10:21
1001D7 | 1001 | 11104 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 17:58 | Apr 22, 2026 @ 17:58
1801C2 | 1801 | 11103 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1001D4 | 1001 | 11102 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1001_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 08:59 | Jun 12, 2026 @ 09:44
1801D7 | 1801 | 11099 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:37 | Apr 24, 2026 @ 17:37
909_F3 | 909_ | 11094 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
909_F2 | 909_ | 11080 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:36 | May 09, 2026 @ 13:36
909_C2 | 909_ | 11079 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 16, 2026 @ 18:20 | Jun 16, 2026 @ 18:20
909_D2 | 909_ | 11074 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 18:21 | Jun 16, 2026 @ 18:21
909_D7 | 909_ | 11071 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:47 | Apr 24, 2026 @ 11:47
909_D4 | 909_ | 11068 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 909_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 18:21 | Jun 16, 2026 @ 18:21
908_F3 | 908_ | 11059 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
1709F2 | 1709 | 11053 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:46 | May 04, 2026 @ 09:46
1709D4 | 1709 | 11049 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:29 | Jun 01, 2026 @ 14:29
1709D2 | 1709 | 11040 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 15:31 | Jun 02, 2026 @ 15:31
1709F3 | 1709 | 11034 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:57 | May 04, 2026 @ 17:57
908_F2 | 908_ | 11029 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:37 | May 09, 2026 @ 13:37
908_C2 | 908_ | 11027 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 13, 2026 @ 12:43 | Jun 13, 2026 @ 12:37
1709C2 | 1709 | 11022 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 30, 2026 @ 08:59 | May 30, 2026 @ 08:59
1709D7 | 1709 | 11019 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:56 | Jun 01, 2026 @ 14:56
908_D2 | 908_ | 11016 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 18:19 | Jun 16, 2026 @ 18:19
908_D7 | 908_ | 11013 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:47 | Apr 24, 2026 @ 11:47
908_D4 | 908_ | 11012 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 908_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 18:19 | Jun 16, 2026 @ 18:19
907_F3 | 907_ | 11007 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
907_F2 | 907_ | 10993 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:37 | May 09, 2026 @ 13:37
907_C2 | 907_ | 10992 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
907_D2 | 907_ | 10982 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 09:46 | Jun 18, 2026 @ 09:46
907_D7 | 907_ | 10976 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:47 | Apr 24, 2026 @ 11:47
1708F2 | 1708 | 10974 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:46 | May 04, 2026 @ 09:46
1708D4 | 1708 | 10972 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 29, 2026 @ 02:08 | May 29, 2026 @ 02:08
1708D2 | 1708 | 10967 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 29, 2026 @ 02:06 | May 29, 2026 @ 02:06
1708F3 | 1708 | 10964 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:57 | May 04, 2026 @ 17:57
1708C2 | 1708 | 10958 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 29, 2026 @ 12:31 | May 29, 2026 @ 02:04
1708D7 | 1708 | 10956 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:34 | Apr 24, 2026 @ 17:34
1707F2 | 1707 | 10945 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:46 | May 04, 2026 @ 09:46
1707D4 | 1707 | 10943 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:29 | Jun 01, 2026 @ 14:29
1707D2 | 1707 | 10938 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 09:31 | May 30, 2026 @ 09:31
1707F3 | 1707 | 10935 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:56 | May 04, 2026 @ 17:56
1707C2 | 1707 | 10929 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 30, 2026 @ 09:30 | May 30, 2026 @ 09:30
1707D7 | 1707 | 10927 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:37 | Apr 24, 2026 @ 17:34
1706F2 | 1706 | 10916 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:47 | May 04, 2026 @ 09:47
1706D4 | 1706 | 10914 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 09, 2026 @ 09:38 | Jun 09, 2026 @ 09:38
1706D2 | 1706 | 10909 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 02, 2026 @ 15:31 | Jun 02, 2026 @ 15:31
1706F3 | 1706 | 10906 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:56 | May 04, 2026 @ 17:56
1706C2 | 1706 | 10900 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1706D7 | 1706 | 10898 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:31 | Apr 24, 2026 @ 17:31
1705F2 | 1705 | 10887 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:47 | May 04, 2026 @ 09:47
1705D4 | 1705 | 10885 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 15:00 | Jun 06, 2026 @ 15:00
1705D2 | 1705 | 10880 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 03, 2026 @ 18:13 | Jul 03, 2026 @ 18:13
1705F3 | 1705 | 10877 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:56 | May 04, 2026 @ 17:56
1705C2 | 1705 | 10871 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 11:38 | Jun 05, 2026 @ 11:38
1705D7 | 1705 | 10869 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:54 | Jun 01, 2026 @ 14:54
907_D4 | 907_ | 10867 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 907_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
906_F3 | 906_ | 10862 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
906_F2 | 906_ | 10848 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:37 | May 09, 2026 @ 13:37
906_C2 | 906_ | 10847 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
906_D2 | 906_ | 10837 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 09:46 | Jun 18, 2026 @ 09:46
906_D7 | 906_ | 10831 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:46 | Apr 24, 2026 @ 11:46
906_D4 | 906_ | 10829 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 906_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
1704F2 | 1704 | 10828 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:47 | May 04, 2026 @ 09:47
1704D4 | 1704 | 10824 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 23, 2026 @ 14:32 | May 23, 2026 @ 14:32
905_F3 | 905_ | 10818 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:43 | May 09, 2026 @ 13:43
1704D2 | 1704 | 10814 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 23, 2026 @ 14:32 | May 23, 2026 @ 14:32
1704F3 | 1704 | 10808 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:55 | May 04, 2026 @ 17:55
1704C2 | 1704 | 10798 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 29, 2026 @ 12:29 | May 23, 2026 @ 14:34
1704D7 | 1704 | 10792 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:30 | Apr 24, 2026 @ 17:30
905_F2 | 905_ | 10791 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:38 | May 09, 2026 @ 13:38
905_C2 | 905_ | 10789 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 18, 2026 @ 12:10 | Jun 18, 2026 @ 12:10
905_D2 | 905_ | 10784 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 10:47 | Jul 14, 2026 @ 10:47
905_D7 | 905_ | 10781 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:50 | Apr 24, 2026 @ 11:46
905_D4 | 905_ | 10780 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 905_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 14:31 | Jun 23, 2026 @ 14:31
904_F3 | 904_ | 10775 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:44 | May 09, 2026 @ 13:44
904_F2 | 904_ | 10756 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:38 | May 09, 2026 @ 13:38
904_C2 | 904_ | 10754 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 20, 2026 @ 08:23 | Jun 17, 2026 @ 09:01
1703F2 | 1703 | 10748 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:48 | May 04, 2026 @ 09:48
904_D2 | 904_ | 10744 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 18:22 | Jun 16, 2026 @ 18:22
1703D4 | 1703 | 10743 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 21, 2026 @ 17:40 | May 21, 2026 @ 17:40
904_D7 | 904_ | 10738 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:45 | Apr 24, 2026 @ 11:45
904_D4 | 904_ | 10736 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 904_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 14:12 | Jun 16, 2026 @ 18:22
1703D2 | 1703 | 10733 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 21, 2026 @ 17:40 | May 21, 2026 @ 17:40
1703F3 | 1703 | 10729 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:54 | May 04, 2026 @ 17:54
903_F3 | 903_ | 10724 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:44 | May 09, 2026 @ 13:44
1703C2 | 1703 | 10718 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 29, 2026 @ 12:28 | May 21, 2026 @ 17:50
1703D7 | 1703 | 10714 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:28 | Apr 24, 2026 @ 17:28
903_F2 | 903_ | 10703 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:38 | May 09, 2026 @ 13:38
903_C2 | 903_ | 10702 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
903_D2 | 903_ | 10697 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 09:46 | Jun 18, 2026 @ 09:46
903_D7 | 903_ | 10694 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:45 | Apr 24, 2026 @ 11:45
903_D4 | 903_ | 10693 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 903_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
902_F3 | 902_ | 10688 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:44 | May 09, 2026 @ 13:44
1702F2 | 1702 | 10666 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:48 | May 04, 2026 @ 09:48
902_F2 | 902_ | 10663 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 13:38 | May 09, 2026 @ 13:38
1702D4 | 1702 | 10662 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 05, 2026 @ 11:39 | Jun 05, 2026 @ 11:39
902_C2 | 902_ | 10660 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 18, 2026 @ 12:10 | Jun 18, 2026 @ 12:10
1702D2 | 1702 | 10653 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:37 | Jun 01, 2026 @ 14:37
902_D2 | 902_ | 10649 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 09:46 | Jun 18, 2026 @ 09:46
1702F3 | 1702 | 10648 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:54 | May 04, 2026 @ 17:54
902_D7 | 902_ | 10643 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:45 | Apr 24, 2026 @ 11:45
902_D4 | 902_ | 10640 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 902_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
1702C2 | 1702 | 10638 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1702D7 | 1702 | 10634 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:27 | Apr 24, 2026 @ 17:27
901_F3 | 901_ | 10630 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:47 | May 09, 2026 @ 08:47
901_F2 | 901_ | 10616 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:47 | May 09, 2026 @ 08:47
901_C2 | 901_ | 10615 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 23, 2026 @ 09:01 | Jun 23, 2026 @ 09:01
901_D2 | 901_ | 10610 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 09:46 | Jun 18, 2026 @ 09:46
901_D7 | 901_ | 10607 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:44 | Apr 24, 2026 @ 11:44
901_D4 | 901_ | 10606 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 901_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
810_F3 | 810_ | 10600 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:47 | May 09, 2026 @ 08:47
1701F2 | 1701 | 10584 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:48 | May 04, 2026 @ 09:48
1701D4 | 1701 | 10581 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 05, 2026 @ 11:39 | Jun 05, 2026 @ 11:39
1701D2 | 1701 | 10571 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:37 | Jun 01, 2026 @ 14:37
810_F2 | 810_ | 10570 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:48 | May 09, 2026 @ 08:48
810_C2 | 810_ | 10568 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 20, 2026 @ 09:19 | Jun 20, 2026 @ 09:19
1701F3 | 1701 | 10565 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:52 | May 04, 2026 @ 17:52
810_D2 | 810_ | 10557 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:24 | Jun 23, 2026 @ 10:24
1701C2 | 1701 | 10554 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
810_D7 | 810_ | 10551 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:44 | Apr 24, 2026 @ 11:44
1701D7 | 1701 | 10550 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 17:26 | Apr 24, 2026 @ 17:26
810_D4 | 810_ | 10548 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 810_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
809_F3 | 809_ | 10543 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 09:42 | Jun 06, 2026 @ 09:42
809_F2 | 809_ | 10529 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 06, 2026 @ 09:43 | Jun 06, 2026 @ 09:43
809_C2 | 809_ | 10528 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 09:26 | Jun 26, 2026 @ 09:26
809_D2 | 809_ | 10523 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | review | Planned Work | 809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 16, 2026 @ 17:39
809_D7 | 809_ | 10520 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 809_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 08:26 | Jun 06, 2026 @ 08:26
809_D4 | 809_ | 10518 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 809_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
808_F3 | 808_ | 10508 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
1610F2 | 1610 | 10501 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1610_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:49 | May 04, 2026 @ 09:49
1610D4 | 1610 | 10497 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1610_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 09:10 | May 30, 2026 @ 09:10
1610D2 | 1610 | 10488 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1610_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 09:10 | May 30, 2026 @ 09:10
1610F3 | 1610 | 10482 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1610_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:50 | May 04, 2026 @ 17:50
808_F2 | 808_ | 10478 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:48 | May 09, 2026 @ 08:48
808_C2 | 808_ | 10476 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 20, 2026 @ 09:21 | Jun 20, 2026 @ 09:21
1610C2 | 1610 | 10471 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1610_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 08:40 | Jun 04, 2026 @ 18:18
1610D7 | 1610 | 10468 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1610_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:30 | Apr 23, 2026 @ 13:30
808_D2 | 808_ | 10466 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:41 | Jun 19, 2026 @ 11:41
808_D7 | 808_ | 10462 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:43 | Apr 24, 2026 @ 11:43
808_D4 | 808_ | 10461 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 808_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
807_F3 | 807_ | 10456 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
807_F2 | 807_ | 10442 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:25 | Apr 25, 2026 @ 08:25
807_C2 | 807_ | 10441 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 17, 2026 @ 17:18 | Jun 17, 2026 @ 17:18
807_D2 | 807_ | 10435 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
807_D7 | 807_ | 10429 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:43 | Apr 24, 2026 @ 11:43
807_D4 | 807_ | 10427 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 807_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
1609F2 | 1609 | 10418 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 03, 2026 @ 09:37 | Jun 03, 2026 @ 09:36
806_F3 | 806_ | 10417 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
1609D4 | 1609 | 10415 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:24 | Jun 23, 2026 @ 10:24
1609D2 | 1609 | 10404 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | review | Issue | 1609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 04, 2026 @ 08:33
1609F3 | 1609 | 10399 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:50 | May 04, 2026 @ 17:50
1609C2 | 1609 | 10390 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 09:26 | Jun 26, 2026 @ 09:26
806_F2 | 806_ | 10386 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:25 | Apr 25, 2026 @ 08:25
1609D7 | 1609 | 10385 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:53 | Jun 01, 2026 @ 14:53
806_C2 | 806_ | 10383 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 17, 2026 @ 12:31 | Jun 17, 2026 @ 12:31
806_D2 | 806_ | 10378 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 09:29 | Jun 23, 2026 @ 09:29
806_D7 | 806_ | 10375 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:42 | Apr 24, 2026 @ 11:42
806_D4 | 806_ | 10374 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 806_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
805_F3 | 805_ | 10369 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
805_F2 | 805_ | 10353 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:26 | Apr 25, 2026 @ 08:26
805_C2 | 805_ | 10350 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 09:26 | Jun 26, 2026 @ 09:26
805_D2 | 805_ | 10340 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 10:47 | Jul 14, 2026 @ 10:47
1608F2 | 1608 | 10338 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:49 | May 04, 2026 @ 09:49
805_D7 | 805_ | 10335 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 08:25 | Jun 06, 2026 @ 08:25
1608D4 | 1608 | 10334 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 29, 2026 @ 11:09 | May 29, 2026 @ 11:09
805_D4 | 805_ | 10332 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 805_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
1608D2 | 1608 | 10326 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 29, 2026 @ 11:08 | May 29, 2026 @ 11:08
804_F3 | 804_ | 10321 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
1608F3 | 1608 | 10320 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:49 | May 04, 2026 @ 17:49
1608C2 | 1608 | 10309 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 16:48 | May 25, 2026 @ 16:48
1608D7 | 1608 | 10305 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:29 | Apr 23, 2026 @ 13:29
804_F2 | 804_ | 10297 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:26 | Apr 25, 2026 @ 08:26
804_C2 | 804_ | 10296 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 19, 2026 @ 18:20 | Jun 19, 2026 @ 18:20
804_D2 | 804_ | 10291 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 10:34 | Jun 19, 2026 @ 10:34
804_D7 | 804_ | 10288 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:41 | Apr 24, 2026 @ 11:41
804_D4 | 804_ | 10287 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 804_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
803_F3 | 803_ | 10282 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
1607F2 | 1607 | 10259 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:50 | May 04, 2026 @ 09:50
803_F2 | 803_ | 10258 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:26 | Apr 25, 2026 @ 08:26
1607D4 | 1607 | 10256 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 09:25 | May 30, 2026 @ 09:25
803_C2 | 803_ | 10255 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 18, 2026 @ 12:11 | Jun 18, 2026 @ 12:11
1607D2 | 1607 | 10247 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:37 | Jun 01, 2026 @ 14:37
803_D2 | 803_ | 10244 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
1607F3 | 1607 | 10241 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:49 | May 04, 2026 @ 17:49
803_D7 | 803_ | 10238 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:41 | Apr 24, 2026 @ 11:41
803_D4 | 803_ | 10235 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 803_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
1607C2 | 1607 | 10230 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 16:49 | May 25, 2026 @ 16:49
1607D7 | 1607 | 10226 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:29 | Apr 23, 2026 @ 13:29
802_F3 | 802_ | 10225 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:27 | Apr 25, 2026 @ 08:27
802_F2 | 802_ | 10210 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:26 | Apr 25, 2026 @ 08:26
802_C2 | 802_ | 10209 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 18, 2026 @ 12:11 | Jun 18, 2026 @ 12:11
802_D2 | 802_ | 10204 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
802_D7 | 802_ | 10201 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 24, 2026 @ 11:40 | Apr 24, 2026 @ 11:40
802_D4 | 802_ | 10200 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 802_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
801_F3 | 801_ | 10192 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:28 | Apr 25, 2026 @ 08:28
1606F2 | 1606 | 10180 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:50 | May 04, 2026 @ 09:50
1606D4 | 1606 | 10176 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 14:45 | May 30, 2026 @ 14:45
1606D2 | 1606 | 10166 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 30, 2026 @ 14:44 | May 30, 2026 @ 14:44
801_F2 | 801_ | 10162 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 25, 2026 @ 08:26 | Apr 25, 2026 @ 08:26
1606F3 | 1606 | 10161 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:48 | May 04, 2026 @ 17:48
801_C2 | 801_ | 10160 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 18, 2026 @ 12:11 | Jun 18, 2026 @ 12:11
1606C2 | 1606 | 10151 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 16:50 | May 25, 2026 @ 16:50
801_D2 | 801_ | 10148 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
1606D7 | 1606 | 10146 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:28 | Apr 23, 2026 @ 13:28
801_D7 | 801_ | 10143 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 15:44 | Apr 23, 2026 @ 15:44
801_D4 | 801_ | 10142 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 801_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 10:00 | Jun 18, 2026 @ 10:00
709_F3 | 709_ | 10137 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:39 | Jun 16, 2026 @ 11:39
709_F2 | 709_ | 10123 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:40 | Jun 16, 2026 @ 11:40
709_C2 | 709_ | 10122 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:17 | Jun 26, 2026 @ 16:17
709_D2 | 709_ | 10117 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:14 | Jun 26, 2026 @ 18:14
709_D7 | 709_ | 10112 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 12:56 | Jun 06, 2026 @ 12:56
709_D4 | 709_ | 10110 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 709_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:14 | Jun 26, 2026 @ 18:14
708_F3 | 708_ | 10099 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:42 | Jun 16, 2026 @ 11:42
1605F2 | 1605 | 10098 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:50 | May 04, 2026 @ 09:50
1605D4 | 1605 | 10095 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:24 | Jun 23, 2026 @ 10:24
1605D2 | 1605 | 10084 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 03, 2026 @ 18:13 | Jul 03, 2026 @ 18:13
1605F3 | 1605 | 10080 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:48 | May 04, 2026 @ 17:48
708_F2 | 708_ | 10069 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:43 | Jun 16, 2026 @ 11:43
1605C2 | 1605 | 10068 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
708_C2 | 708_ | 10066 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 30, 2026 @ 14:44 | Jun 30, 2026 @ 14:44
1605D7 | 1605 | 10064 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 07, 2026 @ 17:42 | May 07, 2026 @ 17:42
708_D2 | 708_ | 10059 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:30 | Jun 30, 2026 @ 18:30
708_D7 | 708_ | 10056 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:15 | Jun 06, 2026 @ 13:15
708_D4 | 708_ | 10055 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 708_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 29, 2026 @ 11:04 | Jun 29, 2026 @ 11:04
1604F2 | 1604 | 10042 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:51 | May 04, 2026 @ 09:51
1604D4 | 1604 | 10040 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 19, 2026 @ 16:15 | May 19, 2026 @ 16:15
1604D2 | 1604 | 10035 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 19, 2026 @ 16:11 | May 19, 2026 @ 16:11
1604F3 | 1604 | 10032 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:47 | May 04, 2026 @ 17:47
1604C2 | 1604 | 10026 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 19, 2026 @ 09:12 | May 19, 2026 @ 09:12
1604D7 | 1604 | 10024 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:27 | Apr 23, 2026 @ 13:27
707_F3 | 707_ | 10021 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:46 | Jun 16, 2026 @ 11:46
707_F2 | 707_ | 10007 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:46 | Jun 16, 2026 @ 11:46
707_C2 | 707_ | 10006 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:17 | Jun 26, 2026 @ 16:17
707_D2 | 707_ | 10000 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:13 | Jun 26, 2026 @ 18:13
707_D7 | 707_ | 9994 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:18 | Jun 06, 2026 @ 13:18
707_D4 | 707_ | 9992 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 707_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:13 | Jun 26, 2026 @ 18:13
1603F2 | 1603 | 9983 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:51 | May 04, 2026 @ 09:51
706_F3 | 706_ | 9981 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:47 | Jun 16, 2026 @ 11:47
1603D4 | 1603 | 9979 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 19, 2026 @ 17:29 | May 19, 2026 @ 17:29
1603D2 | 1603 | 9968 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 19, 2026 @ 17:30 | May 19, 2026 @ 17:30
1603F3 | 1603 | 9963 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:46 | May 04, 2026 @ 17:46
706_F2 | 706_ | 9953 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:47 | Jun 16, 2026 @ 11:47
1603C2 | 1603 | 9952 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 20, 2026 @ 09:33 | May 20, 2026 @ 09:33
706_C2 | 706_ | 9951 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:19 | Jun 26, 2026 @ 16:19
1603D7 | 1603 | 9948 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:26 | Apr 23, 2026 @ 13:26
706_D2 | 706_ | 9943 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 10:47 | Jul 14, 2026 @ 10:47
706_D7 | 706_ | 9940 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:19 | Jun 06, 2026 @ 13:19
706_D4 | 706_ | 9939 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 706_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 29, 2026 @ 11:04 | Jun 29, 2026 @ 11:04
705_F3 | 705_ | 9934 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:47 | Jun 16, 2026 @ 11:47
705_F2 | 705_ | 9920 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:47 | Jun 16, 2026 @ 11:47
705_C2 | 705_ | 9919 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:19 | Jun 26, 2026 @ 16:19
705_D2 | 705_ | 9909 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 14, 2026 @ 10:48 | Jul 14, 2026 @ 10:48
705_D7 | 705_ | 9903 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:19 | Jun 06, 2026 @ 13:19
1602F2 | 1602 | 9901 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:51 | May 04, 2026 @ 09:51
705_D4 | 705_ | 9900 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 705_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 27, 2026 @ 09:17 | Jul 27, 2026 @ 09:17
1602D4 | 1602 | 9897 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:29 | Jun 01, 2026 @ 14:29
704_F3 | 704_ | 9890 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:47 | Jun 16, 2026 @ 11:47
1602D2 | 1602 | 9888 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:37 | Jun 01, 2026 @ 14:37
1602F3 | 1602 | 9882 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:46 | May 04, 2026 @ 17:46
1602C2 | 1602 | 9871 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 20, 2026 @ 09:33 | May 20, 2026 @ 09:33
1602D7 | 1602 | 9868 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:26 | Apr 23, 2026 @ 13:26
704_F2 | 704_ | 9862 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:48 | Jun 16, 2026 @ 11:48
704_C2 | 704_ | 9861 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:19 | Jun 26, 2026 @ 16:19
704_D2 | 704_ | 9856 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:20 | Jun 30, 2026 @ 18:20
704_D7 | 704_ | 9853 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:19 | Jun 06, 2026 @ 13:19
704_D4 | 704_ | 9852 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 704_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 29, 2026 @ 11:05 | Jun 29, 2026 @ 11:05
703_F3 | 703_ | 9847 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:14 | Jun 18, 2026 @ 12:14
1601F2 | 1601 | 9824 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:52 | May 04, 2026 @ 09:52
703_F2 | 703_ | 9823 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:48 | Jun 16, 2026 @ 11:48
1601D4 | 1601 | 9821 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:29 | Jun 01, 2026 @ 14:29
703_C2 | 703_ | 9820 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:20 | Jun 26, 2026 @ 16:20
1601D2 | 1601 | 9812 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:37 | Jun 01, 2026 @ 14:37
703_D2 | 703_ | 9809 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:10 | Jun 26, 2026 @ 18:10
1601F3 | 1601 | 9806 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:45 | May 04, 2026 @ 17:45
703_D7 | 703_ | 9802 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:20 | Jun 06, 2026 @ 13:20
703_D4 | 703_ | 9800 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 703_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 26, 2026 @ 18:10 | Jun 26, 2026 @ 18:10
1601C2 | 1601 | 9796 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 20, 2026 @ 09:35 | May 20, 2026 @ 09:35
1601D7 | 1601 | 9792 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:26 | Apr 23, 2026 @ 13:25
702_F3 | 702_ | 9789 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:14 | Jun 18, 2026 @ 12:14
702_F2 | 702_ | 9775 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:53 | Jun 16, 2026 @ 11:53
702_C2 | 702_ | 9774 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:20 | Jun 26, 2026 @ 16:20
702_D2 | 702_ | 9769 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:15 | Jun 30, 2026 @ 18:15
702_D7 | 702_ | 9766 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:20 | Jun 06, 2026 @ 13:20
702_D4 | 702_ | 9765 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 702_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 29, 2026 @ 11:06 | Jun 29, 2026 @ 11:06
701_F3 | 701_ | 9755 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:14 | Jun 18, 2026 @ 12:14
1509F2 | 1509 | 9745 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:52 | May 04, 2026 @ 09:52
1509D4 | 1509 | 9740 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1509_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 14, 2026 @ 08:47 | May 14, 2026 @ 08:47
1509D2 | 1509 | 9731 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1509_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:35 | May 20, 2026 @ 09:35
701_F2 | 701_ | 9728 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:54 | Jun 16, 2026 @ 11:54
1509F3 | 1509 | 9726 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:44 | May 04, 2026 @ 17:44
701_C2 | 701_ | 9725 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:20 | Jun 26, 2026 @ 16:20
1509C2 | 1509 | 9715 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 08:35 | Jun 04, 2026 @ 16:48
701_D2 | 701_ | 9713 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 01, 2026 @ 08:43 | Jul 01, 2026 @ 08:43
1509D7 | 1509 | 9711 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:25 | Apr 23, 2026 @ 13:25
701_D7 | 701_ | 9708 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 06, 2026 @ 13:21 | Jun 06, 2026 @ 13:21
701_D4 | 701_ | 9707 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 701_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 29, 2026 @ 11:07 | Jun 29, 2026 @ 11:07
609_F3 | 609_ | 9702 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 26, 2026 @ 16:24 | Jun 26, 2026 @ 16:24
609_F2 | 609_ | 9688 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 26, 2026 @ 16:24 | Jun 26, 2026 @ 16:24
609_C2 | 609_ | 9687 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 03, 2026 @ 17:12 | Jul 03, 2026 @ 17:12
609_D2 | 609_ | 9682 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:54 | Jul 23, 2026 @ 09:54
609_D7 | 609_ | 9676 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:47 | Jun 19, 2026 @ 11:47
609_D4 | 609_ | 9674 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 609_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 30, 2026 @ 16:47 | Jul 30, 2026 @ 16:47
608_F3 | 608_ | 9664 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 26, 2026 @ 16:25 | Jun 26, 2026 @ 16:25
1508F2 | 1508 | 9663 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:52 | May 04, 2026 @ 09:52
1508D4 | 1508 | 9660 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 14, 2026 @ 08:47 | May 14, 2026 @ 08:47
1508D2 | 1508 | 9650 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:36 | May 20, 2026 @ 09:36
1508F3 | 1508 | 9645 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:44 | May 04, 2026 @ 17:44
1508C2 | 1508 | 9634 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 30, 2026 @ 14:48 | May 30, 2026 @ 14:48
608_F2 | 608_ | 9633 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 26, 2026 @ 16:25 | Jun 26, 2026 @ 16:25
608_C2 | 608_ | 9631 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:27 | Jun 26, 2026 @ 16:27
1508D7 | 1508 | 9630 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:25 | Apr 23, 2026 @ 13:25
608_D2 | 608_ | 9624 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:54 | Jul 23, 2026 @ 09:54
608_D7 | 608_ | 9621 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 18, 2026 @ 11:46 | Jun 17, 2026 @ 12:54
608_D4 | 608_ | 9620 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 608_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:14 | Aug 07, 2026 @ 13:14
607_F3 | 607_ | 9615 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 09:04 | Jun 19, 2026 @ 09:04
607_F2 | 607_ | 9600 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:43 | Jun 19, 2026 @ 11:43
607_C2 | 607_ | 9598 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:27 | Jun 26, 2026 @ 16:27
607_D2 | 607_ | 9587 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 17:43 | Aug 04, 2026 @ 17:43
1507F2 | 1507 | 9584 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:53 | May 04, 2026 @ 09:53
607_D7 | 607_ | 9581 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:54 | Jun 17, 2026 @ 12:54
1507D4 | 1507 | 9580 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 14:29 | Jun 01, 2026 @ 14:29
607_D4 | 607_ | 9578 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 607_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 17:43 | Aug 04, 2026 @ 17:43
1507D2 | 1507 | 9572 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:37 | May 20, 2026 @ 09:37
606_F3 | 606_ | 9567 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:43 | Jun 19, 2026 @ 11:43
1507F3 | 1507 | 9566 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:43 | May 04, 2026 @ 17:43
1507C2 | 1507 | 9554 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1507D7 | 1507 | 9550 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:24 | Apr 23, 2026 @ 13:24
606_F2 | 606_ | 9543 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:15 | Jun 18, 2026 @ 12:15
606_C2 | 606_ | 9542 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:28 | Jun 26, 2026 @ 16:28
606_D2 | 606_ | 9537 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 23, 2026 @ 09:55 | Jul 23, 2026 @ 09:55
606_D7 | 606_ | 9534 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:54 | Jun 17, 2026 @ 12:54
606_D4 | 606_ | 9533 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 606_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:28 | Aug 07, 2026 @ 09:28
605_F3 | 605_ | 9528 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:15 | Jun 18, 2026 @ 12:15
605_F2 | 605_ | 9506 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:15 | Jun 18, 2026 @ 12:15
1506F2 | 1506 | 9504 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:57 | May 04, 2026 @ 09:57
605_C2 | 605_ | 9503 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:28 | Jun 26, 2026 @ 16:28
1506D4 | 1506 | 9500 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:22 | May 13, 2026 @ 17:22
605_D2 | 605_ | 9493 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:38 | Aug 05, 2026 @ 08:38
1506D2 | 1506 | 9490 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:37 | May 20, 2026 @ 09:37
605_D7 | 605_ | 9486 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:53 | Jun 17, 2026 @ 12:53
1506F3 | 1506 | 9485 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:42 | May 04, 2026 @ 17:42
605_D4 | 605_ | 9483 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 605_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:28 | Aug 07, 2026 @ 09:28
1506C2 | 1506 | 9475 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 16:25 | May 25, 2026 @ 16:25
604_F3 | 604_ | 9472 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:15 | Jun 18, 2026 @ 12:15
1506D7 | 1506 | 9471 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:24 | Apr 23, 2026 @ 13:24
604_F2 | 604_ | 9456 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:16 | Jun 18, 2026 @ 12:16
604_C2 | 604_ | 9455 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:28 | Jun 26, 2026 @ 16:28
604_D2 | 604_ | 9450 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:54 | Jun 30, 2026 @ 18:54
604_D7 | 604_ | 9447 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:53 | Jun 17, 2026 @ 12:53
604_D4 | 604_ | 9446 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 604_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 14:45 | Jun 30, 2026 @ 14:45
603_F3 | 603_ | 9440 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:54 | Jun 16, 2026 @ 11:54
1505F2 | 1505 | 9424 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:57 | May 04, 2026 @ 09:57
1505D4 | 1505 | 9421 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:22 | May 13, 2026 @ 17:22
603_F2 | 603_ | 9411 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 18, 2026 @ 12:16 | Jun 18, 2026 @ 12:16
1505D2 | 1505 | 9410 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 03, 2026 @ 18:02 | Jul 03, 2026 @ 18:02
603_C2 | 603_ | 9408 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 08, 2026 @ 09:43 | Jun 26, 2026 @ 16:28
1505F3 | 1505 | 9405 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:42 | May 04, 2026 @ 17:42
603_D2 | 603_ | 9397 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:26 | Jun 30, 2026 @ 18:26
1505C2 | 1505 | 9394 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
603_D7 | 603_ | 9392 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:53 | Jun 17, 2026 @ 12:53
1505D7 | 1505 | 9390 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 07, 2026 @ 17:42 | May 07, 2026 @ 17:42
603_D4 | 603_ | 9389 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 603_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 30, 2026 @ 18:22 | Jun 30, 2026 @ 18:22
602_F3 | 602_ | 9383 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:54 | Jun 16, 2026 @ 11:54
602_F2 | 602_ | 9369 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:55 | Jun 16, 2026 @ 11:55
602_C2 | 602_ | 9368 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:29 | Jun 26, 2026 @ 16:29
602_D2 | 602_ | 9363 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 01, 2026 @ 17:17 | Jul 01, 2026 @ 17:16
602_D7 | 602_ | 9360 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:52 | Jun 17, 2026 @ 12:52
602_D4 | 602_ | 9358 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 602_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 01, 2026 @ 17:17 | Jul 01, 2026 @ 17:17
601_F3 | 601_ | 9347 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:55 | Jun 16, 2026 @ 11:55
1504F2 | 1504 | 9341 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:58 | May 04, 2026 @ 09:58
1504D4 | 1504 | 9337 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:23 | May 13, 2026 @ 17:23
1504D2 | 1504 | 9329 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 15, 2026 @ 14:15 | May 15, 2026 @ 14:15
1504F3 | 1504 | 9324 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:41 | May 04, 2026 @ 17:41
601_F2 | 601_ | 9317 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 16, 2026 @ 11:55 | Jun 16, 2026 @ 11:55
601_C2 | 601_ | 9315 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 26, 2026 @ 16:33 | Jun 26, 2026 @ 16:33
1504C2 | 1504 | 9312 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 14, 2026 @ 17:56 | May 14, 2026 @ 17:56
1504D7 | 1504 | 9308 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:23 | Apr 23, 2026 @ 13:23
601_D2 | 601_ | 9305 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
601_D7 | 601_ | 9302 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 17, 2026 @ 12:53 | Jun 17, 2026 @ 12:53
601_D4 | 601_ | 9301 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 601_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 10, 2026 @ 11:25 | Jul 10, 2026 @ 11:25
512_F3 | 512_ | 9296 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:08 | Jul 27, 2026 @ 18:08
512_F2 | 512_ | 9282 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:09 | Jul 27, 2026 @ 18:09
512_C2 | 512_ | 9281 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 05, 2026 @ 08:43 | Aug 05, 2026 @ 08:43
512_D2 | 512_ | 9274 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:38 | Aug 05, 2026 @ 08:38
512_D7 | 512_ | 9268 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 17:03 | Jun 01, 2026 @ 17:03
512_D4 | 512_ | 9265 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 512_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:19 | Aug 04, 2026 @ 14:03
1503F2 | 1503 | 9261 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:58 | May 04, 2026 @ 09:58
1503D4 | 1503 | 9257 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:23 | May 13, 2026 @ 17:23
511_F3 | 511_ | 9254 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:09 | Jul 27, 2026 @ 18:09
1503D2 | 1503 | 9246 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 15, 2026 @ 13:17 | May 15, 2026 @ 13:17
1503F3 | 1503 | 9240 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:41 | May 04, 2026 @ 17:40
1503C2 | 1503 | 9231 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 14, 2026 @ 17:01 | May 14, 2026 @ 17:01
1503D7 | 1503 | 9227 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:22 | Apr 23, 2026 @ 13:22
511_F2 | 511_ | 9224 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:09 | Jul 27, 2026 @ 18:09
511_C2 | 511_ | 9223 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 05, 2026 @ 08:43 | Aug 05, 2026 @ 08:43
511_D2 | 511_ | 9218 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:39 | Aug 05, 2026 @ 08:39
511_D7 | 511_ | 9215 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 14:15 | Jun 01, 2026 @ 17:03
511_D4 | 511_ | 9214 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 511_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:18 | Aug 04, 2026 @ 14:03
510_F3 | 510_ | 9209 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:09 | Jul 27, 2026 @ 18:09
510_F2 | 510_ | 9194 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
510_C2 | 510_ | 9192 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 05, 2026 @ 08:44 | Aug 05, 2026 @ 08:44
510_D2 | 510_ | 9182 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:39 | Aug 05, 2026 @ 08:39
1502F2 | 1502 | 9177 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:58 | May 04, 2026 @ 09:58
510_D7 | 510_ | 9176 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 14:13 | Jun 01, 2026 @ 17:02
1502D4 | 1502 | 9174 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:23 | May 13, 2026 @ 17:23
510_D4 | 510_ | 9173 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 510_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:17 | Aug 04, 2026 @ 14:03
1502D2 | 1502 | 9165 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:38 | May 20, 2026 @ 09:38
509_F3 | 509_ | 9162 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
1502F3 | 1502 | 9160 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:38 | May 04, 2026 @ 17:38
1502C2 | 1502 | 9149 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 15, 2026 @ 10:25 | May 15, 2026 @ 10:25
1502D7 | 1502 | 9145 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:22 | Apr 23, 2026 @ 13:22
509_F2 | 509_ | 9137 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
509_C2 | 509_ | 9136 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 08:36 | Aug 10, 2026 @ 08:36
509_D2 | 509_ | 9131 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:39 | Aug 05, 2026 @ 08:39
509_D7 | 509_ | 9128 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 14:12 | Jun 01, 2026 @ 17:02
509_D4 | 509_ | 9127 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 509_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:16 | Aug 04, 2026 @ 14:03
508_F3 | 508_ | 9122 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
508_F2 | 508_ | 9100 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
508_C2 | 508_ | 9098 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 05, 2026 @ 08:44 | Aug 05, 2026 @ 08:44
1501F2 | 1501 | 9097 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 09:59 | May 04, 2026 @ 09:59
1501D4 | 1501 | 9093 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:24 | May 13, 2026 @ 17:24
508_D2 | 508_ | 9088 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:39 | Aug 05, 2026 @ 08:39
508_D7 | 508_ | 9083 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 17:02 | Jun 01, 2026 @ 17:02
1501D2 | 1501 | 9082 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 20, 2026 @ 09:38 | May 20, 2026 @ 09:38
508_D4 | 508_ | 9081 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 508_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:15 | Aug 04, 2026 @ 14:03
1501F3 | 1501 | 9077 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 17:37 | May 04, 2026 @ 17:37
507_F3 | 507_ | 9069 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:43 | Jun 19, 2026 @ 11:43
1501C2 | 1501 | 9067 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 15, 2026 @ 17:23 | May 15, 2026 @ 17:23
1501D7 | 1501 | 9063 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:22 | Apr 23, 2026 @ 13:22
507_F2 | 507_ | 9050 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:43 | Jun 19, 2026 @ 11:43
507_C2 | 507_ | 9049 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 01, 2026 @ 18:33 | Aug 01, 2026 @ 18:33
507_D2 | 507_ | 9044 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:58 | Aug 01, 2026 @ 08:58
507_D7 | 507_ | 9041 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 09:44 | Jun 19, 2026 @ 11:39
507_D4 | 507_ | 9040 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 507_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:14 | Aug 01, 2026 @ 15:52
506_F3 | 506_ | 9035 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:44 | Jun 19, 2026 @ 11:44
1410F2 | 1410 | 9017 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:00 | May 04, 2026 @ 10:00
1410D4 | 1410 | 9013 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1410_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:24 | May 13, 2026 @ 17:24
506_F2 | 506_ | 9006 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 11 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:44 | Jun 19, 2026 @ 11:44
1410D2 | 1410 | 9004 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1410_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:13 | May 11, 2026 @ 12:13
506_C2 | 506_ | 9003 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 14:05 | Aug 04, 2026 @ 14:05
1410F3 | 1410 | 8998 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 09, 2026 @ 08:48 | May 09, 2026 @ 08:48
506_D2 | 506_ | 8991 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:54 | Aug 01, 2026 @ 08:54
1410C2 | 1410 | 8988 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 30, 2026 @ 09:11 | May 30, 2026 @ 09:11
506_D7 | 506_ | 8985 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:38 | Jun 19, 2026 @ 11:38
1410D7 | 1410 | 8984 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:20 | Apr 22, 2026 @ 18:20
506_D4 | 506_ | 8983 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 506_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:14 | Aug 04, 2026 @ 14:04
505_F3 | 505_ | 8977 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:45 | Jun 19, 2026 @ 11:45
505_F2 | 505_ | 8963 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:45 | Jun 19, 2026 @ 11:45
505_C2 | 505_ | 8962 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 14:05 | Aug 04, 2026 @ 14:05
505_D2 | 505_ | 8957 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:40 | Aug 05, 2026 @ 08:40
505_D7 | 505_ | 8953 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 13:45 | Jun 19, 2026 @ 11:38
505_D4 | 505_ | 8951 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 505_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:14 | Aug 04, 2026 @ 14:04
504_F3 | 504_ | 8940 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:45 | Jun 19, 2026 @ 11:45
1409F2 | 1409 | 8937 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:00 | May 04, 2026 @ 10:00
1409D4 | 1409 | 8933 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:25 | May 13, 2026 @ 17:25
1409D2 | 1409 | 8924 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | review | Issue | 1409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 04, 2026 @ 08:20
1409F3 | 1409 | 8920 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:03 | May 05, 2026 @ 09:03
504_F2 | 504_ | 8909 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:45 | Jun 19, 2026 @ 11:45
1409C2 | 1409 | 8908 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 11:40 | Jun 05, 2026 @ 11:40
504_C2 | 504_ | 8907 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 14:05 | Aug 04, 2026 @ 14:05
1409D7 | 1409 | 8904 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 25, 2026 @ 14:04 | May 25, 2026 @ 14:04
504_D2 | 504_ | 8899 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:41 | Aug 05, 2026 @ 08:41
504_D7 | 504_ | 8896 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:38 | Jun 19, 2026 @ 11:38
504_D4 | 504_ | 8895 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 504_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:13 | Aug 04, 2026 @ 14:04
503_F3 | 503_ | 8890 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:46 | Jun 19, 2026 @ 11:46
503_F2 | 503_ | 8876 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:46 | Jun 19, 2026 @ 11:46
503_C2 | 503_ | 8874 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 12:45 | Aug 04, 2026 @ 12:45
503_D2 | 503_ | 8862 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 17:04 | Aug 04, 2026 @ 17:04
1408F2 | 1408 | 8859 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:00 | May 04, 2026 @ 10:00
503_D7 | 503_ | 8856 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:38 | Jun 19, 2026 @ 11:38
1408D4 | 1408 | 8855 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:25 | May 13, 2026 @ 17:25
503_D4 | 503_ | 8853 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 503_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:12 | Aug 04, 2026 @ 12:45
1408D2 | 1408 | 8845 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:13 | May 11, 2026 @ 12:13
502_F3 | 502_ | 8844 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:46 | Jun 19, 2026 @ 11:46
1408F3 | 1408 | 8837 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:04 | May 05, 2026 @ 09:04
1408C2 | 1408 | 8825 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 30, 2026 @ 15:00 | May 30, 2026 @ 15:00
1408D7 | 1408 | 8821 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:19 | Apr 22, 2026 @ 18:19
502_F2 | 502_ | 8818 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:46 | Jun 19, 2026 @ 11:46
502_C2 | 502_ | 8817 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 14:05 | Aug 04, 2026 @ 14:05
502_D2 | 502_ | 8812 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 08:54 | Aug 01, 2026 @ 08:54
502_D7 | 502_ | 8809 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:37 | Jun 19, 2026 @ 11:37
502_D4 | 502_ | 8808 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 502_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 08:41 | Aug 05, 2026 @ 08:41
501_F3 | 501_ | 8803 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:46 | Jun 19, 2026 @ 11:46
501_F2 | 501_ | 8787 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:47 | Jun 19, 2026 @ 11:47
501_C2 | 501_ | 8785 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 04, 2026 @ 09:53 | Aug 04, 2026 @ 09:53
501_D2 | 501_ | 8774 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 09:53 | Aug 04, 2026 @ 09:53
1407F2 | 1407 | 8772 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:01 | May 04, 2026 @ 10:01
501_D7 | 501_ | 8769 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:37 | Jun 19, 2026 @ 11:37
1407D4 | 1407 | 8768 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:25 | May 13, 2026 @ 17:25
501_D4 | 501_ | 8766 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 501_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 04, 2026 @ 16:11 | Aug 04, 2026 @ 09:53
1407D2 | 1407 | 8758 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:14 | May 11, 2026 @ 12:14
412_F3 | 412_ | 8757 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
1407F3 | 1407 | 8752 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:04 | May 05, 2026 @ 09:04
1407C2 | 1407 | 8741 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 17:34 | May 23, 2026 @ 17:23
1407D7 | 1407 | 8738 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:19 | Apr 22, 2026 @ 18:19
412_F2 | 412_ | 8731 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
412_C2 | 412_ | 8730 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 17:11 | Aug 07, 2026 @ 17:11
412_D2 | 412_ | 8725 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:03 | Jul 22, 2026 @ 13:03
412_D7 | 412_ | 8722 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 17:02 | Jun 01, 2026 @ 17:02
412_D4 | 412_ | 8721 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 412_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
411_F3 | 411_ | 8716 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
411_F2 | 411_ | 8695 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:10 | Jul 27, 2026 @ 18:10
411_C2 | 411_ | 8693 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 08:20 | Aug 07, 2026 @ 08:20
1406F2 | 1406 | 8690 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:01 | May 04, 2026 @ 10:01
1406D4 | 1406 | 8687 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:26 | May 13, 2026 @ 17:26
411_D2 | 411_ | 8682 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:03 | Jul 22, 2026 @ 13:03
411_D7 | 411_ | 8677 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 17:01 | Jun 01, 2026 @ 17:01
1406D2 | 1406 | 8676 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:14 | May 11, 2026 @ 12:14
411_D4 | 411_ | 8674 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 411_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
1406F3 | 1406 | 8671 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:05 | May 05, 2026 @ 09:05
410_F3 | 410_ | 8663 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
1406C2 | 1406 | 8661 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 14:00 | May 22, 2026 @ 18:01
1406D7 | 1406 | 8657 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:18 | Apr 22, 2026 @ 18:18
410_F2 | 410_ | 8644 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
410_C2 | 410_ | 8643 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 06, 2026 @ 17:53 | Aug 06, 2026 @ 17:53
410_D2 | 410_ | 8638 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:04 | Jul 22, 2026 @ 13:04
410_D7 | 410_ | 8635 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 07:56 | Jun 01, 2026 @ 17:01
410_D4 | 410_ | 8633 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 410_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
409_F3 | 409_ | 8623 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
1405F2 | 1405 | 8617 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:01 | May 04, 2026 @ 10:01
1405D4 | 1405 | 8613 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:27 | May 13, 2026 @ 17:27
1405D2 | 1405 | 8603 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 03, 2026 @ 18:13 | Jul 03, 2026 @ 18:13
1405F3 | 1405 | 8598 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:05 | May 05, 2026 @ 09:05
409_F2 | 409_ | 8593 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
409_C2 | 409_ | 8591 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 16:58 | Aug 07, 2026 @ 16:53
1405C2 | 1405 | 8587 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 11:40 | Jun 05, 2026 @ 11:40
1405D7 | 1405 | 8584 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:49 | Apr 22, 2026 @ 18:17
409_D2 | 409_ | 8580 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:04 | Jul 22, 2026 @ 13:04
409_D7 | 409_ | 8577 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 17:00 | Jun 01, 2026 @ 17:00
409_D4 | 409_ | 8576 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 409_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
408_F3 | 408_ | 8571 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
408_F2 | 408_ | 8557 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
408_C2 | 408_ | 8556 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 08:37 | Aug 10, 2026 @ 08:37
408_D2 | 408_ | 8550 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:04 | Jul 22, 2026 @ 13:04
408_D7 | 408_ | 8544 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:53 | Jun 01, 2026 @ 16:53
408_D4 | 408_ | 8542 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 408_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
1404F2 | 1404 | 8533 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:01 | May 04, 2026 @ 10:01
1404D4 | 1404 | 8531 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 12:19 | May 13, 2026 @ 12:19
407_F3 | 407_ | 8527 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 23, 2026 @ 10:09 | Jun 19, 2026 @ 13:45
1404D2 | 1404 | 8524 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:15 | May 11, 2026 @ 12:15
1404F3 | 1404 | 8518 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:06 | May 05, 2026 @ 09:06
1404C2 | 1404 | 8507 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 09, 2026 @ 16:30 | May 09, 2026 @ 16:30
1404D7 | 1404 | 8503 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:17 | Apr 22, 2026 @ 18:17
407_F2 | 407_ | 8499 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:45 | Jun 19, 2026 @ 13:45
407_C2 | 407_ | 8498 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 24, 2026 @ 09:47 | Jul 24, 2026 @ 09:47
407_D2 | 407_ | 8493 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:04 | Jul 22, 2026 @ 13:04
407_D7 | 407_ | 8490 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 10:09 | Jun 19, 2026 @ 11:43
407_D4 | 407_ | 8489 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 407_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 24, 2026 @ 09:47 | Jul 24, 2026 @ 09:47
406_F3 | 406_ | 8484 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:47 | Jun 19, 2026 @ 11:47
406_F2 | 406_ | 8461 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 11 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:47 | Jun 19, 2026 @ 11:47
1403F2 | 1403 | 8460 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:02 | May 04, 2026 @ 10:02
406_C2 | 406_ | 8458 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 13:05 | Jul 22, 2026 @ 13:05
1403D4 | 1403 | 8457 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 12:18 | May 13, 2026 @ 12:18
1403D2 | 1403 | 8448 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:15 | May 11, 2026 @ 12:15
406_D2 | 406_ | 8447 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:05 | Jul 22, 2026 @ 13:05
406_D7 | 406_ | 8442 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
1403F3 | 1403 | 8441 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:07 | May 05, 2026 @ 09:07
406_D4 | 406_ | 8439 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 406_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:58 | Aug 05, 2026 @ 13:58
1403C2 | 1403 | 8432 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 09, 2026 @ 16:31 | May 09, 2026 @ 16:31
1403D7 | 1403 | 8430 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:17 | Apr 22, 2026 @ 18:17
405_F3 | 405_ | 8426 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:47 | Jun 19, 2026 @ 11:47
1402F2 | 1402 | 8407 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:02 | May 04, 2026 @ 10:02
1402D4 | 1402 | 8403 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:29 | May 13, 2026 @ 17:29
405_F2 | 405_ | 8398 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:48 | Jun 19, 2026 @ 11:48
405_C2 | 405_ | 8396 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 13:05 | Jul 22, 2026 @ 13:05
1402D2 | 1402 | 8392 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:15 | May 11, 2026 @ 12:15
1402F3 | 1402 | 8388 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:08 | May 05, 2026 @ 09:08
405_D2 | 405_ | 8385 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:05 | Jul 22, 2026 @ 13:05
405_D7 | 405_ | 8379 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:42 | Jun 19, 2026 @ 11:42
405_D4 | 405_ | 8377 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 405_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 05, 2026 @ 13:59 | Aug 05, 2026 @ 13:59
1402C2 | 1402 | 8376 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1402D7 | 1402 | 8372 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:16 | Apr 22, 2026 @ 18:16
404_F3 | 404_ | 8365 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:48 | Jun 19, 2026 @ 11:48
1401F2 | 1401 | 8352 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:02 | May 04, 2026 @ 10:02
1401D4 | 1401 | 8348 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 13, 2026 @ 17:30 | May 13, 2026 @ 17:30
404_F2 | 404_ | 8338 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:48 | Jun 19, 2026 @ 11:48
1401D2 | 1401 | 8337 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:16 | May 11, 2026 @ 12:16
404_C2 | 404_ | 8335 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 13:06 | Jul 22, 2026 @ 13:06
1401F3 | 1401 | 8332 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:08 | May 05, 2026 @ 09:08
404_D2 | 404_ | 8325 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:06 | Jul 22, 2026 @ 13:06
404_D7 | 404_ | 8320 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:41 | Jun 19, 2026 @ 11:41
1401C2 | 1401 | 8319 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 15, 2026 @ 17:23 | May 15, 2026 @ 17:23
404_D4 | 404_ | 8317 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 404_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:06 | Jul 22, 2026 @ 13:06
1401D7 | 1401 | 8315 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:16 | Apr 22, 2026 @ 18:16
403_F3 | 403_ | 8310 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:48 | Jun 19, 2026 @ 11:48
1308F2 | 1308 | 8292 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 25, 2026 @ 18:15 | May 25, 2026 @ 18:15
1308D4 | 1308 | 8289 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:16 | May 11, 2026 @ 12:16
403_F2 | 403_ | 8281 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:48 | Jun 19, 2026 @ 11:48
1308D2 | 1308 | 8279 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 08:18 | May 05, 2026 @ 08:18
403_C2 | 403_ | 8278 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 13:06 | Jul 22, 2026 @ 13:06
1308F3 | 1308 | 8273 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:49 | Apr 23, 2026 @ 12:49
403_D2 | 403_ | 8268 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:06 | Jul 22, 2026 @ 13:06
403_D7 | 403_ | 8263 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:41 | Jun 19, 2026 @ 11:41
1308C2 | 1308 | 8261 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 16:21 | May 25, 2026 @ 16:21
403_D4 | 403_ | 8260 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 403_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:07 | Jul 22, 2026 @ 13:07
1308D7 | 1308 | 8256 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:46 | Apr 22, 2026 @ 18:10
402_F3 | 402_ | 8252 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:49 | Jun 19, 2026 @ 11:49
402_F2 | 402_ | 8231 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 11:49 | Jun 19, 2026 @ 11:49
402_C2 | 402_ | 8229 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 22, 2026 @ 13:07 | Jul 22, 2026 @ 13:07
1307F2 | 1307 | 8226 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:42 | Apr 23, 2026 @ 12:42
1307D4 | 1307 | 8222 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:16 | May 11, 2026 @ 12:16
402_D2 | 402_ | 8219 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:07 | Jul 22, 2026 @ 13:07
402_D7 | 402_ | 8214 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:41 | Jun 19, 2026 @ 11:41
402_D4 | 402_ | 8212 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 402_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:07 | Jul 22, 2026 @ 13:07
1307D2 | 1307 | 8211 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:16 | May 05, 2026 @ 09:16
1307F3 | 1307 | 8206 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:49 | Apr 23, 2026 @ 12:49
1307C2 | 1307 | 8200 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 23, 2026 @ 17:23 | May 23, 2026 @ 17:23
1307D7 | 1307 | 8198 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:10 | Apr 22, 2026 @ 18:10
401_F3 | 401_ | 8194 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:45 | Jun 19, 2026 @ 13:45
401_F2 | 401_ | 8180 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:46 | Jun 19, 2026 @ 13:46
401_C2 | 401_ | 8179 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jul 27, 2026 @ 18:19 | Jul 27, 2026 @ 18:19
401_D2 | 401_ | 8169 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:07 | Jul 22, 2026 @ 13:07
401_D7 | 401_ | 8163 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:40 | Jun 19, 2026 @ 11:40
401_D4 | 401_ | 8161 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 401_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 22, 2026 @ 13:08 | Jul 22, 2026 @ 13:08
1306F2 | 1306 | 8160 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:42 | Apr 23, 2026 @ 12:42
1306D4 | 1306 | 8156 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:17 | May 11, 2026 @ 12:17
1306D2 | 1306 | 8151 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:17 | May 05, 2026 @ 09:17
1306F3 | 1306 | 8148 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:49 | Apr 23, 2026 @ 12:49
1306C2 | 1306 | 8142 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 25, 2026 @ 13:46 | May 22, 2026 @ 17:55
1306D7 | 1306 | 8140 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:09 | Apr 22, 2026 @ 18:09
312_F3 | 312_ | 8136 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
312_F2 | 312_ | 8122 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
312_C2 | 312_ | 8121 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:47 | Aug 10, 2026 @ 17:47
312_D2 | 312_ | 8116 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:45 | Aug 08, 2026 @ 08:45
312_D7 | 312_ | 8111 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 11:58 | Jun 01, 2026 @ 16:52
312_D4 | 312_ | 8109 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 312_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:46 | Aug 08, 2026 @ 08:46
1305F2 | 1305 | 8100 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:45 | Apr 23, 2026 @ 12:45
1305D4 | 1305 | 8098 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:17 | May 11, 2026 @ 12:17
1305D2 | 1305 | 8093 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 03, 2026 @ 18:13 | Jul 03, 2026 @ 18:13
1305F3 | 1305 | 8090 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:49 | Apr 23, 2026 @ 12:49
1305C2 | 1305 | 8084 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 05, 2026 @ 11:41 | Jun 05, 2026 @ 11:41
1305D7 | 1305 | 8082 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:09 | Apr 22, 2026 @ 18:09
311_F3 | 311_ | 8078 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
311_F2 | 311_ | 8064 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:11 | Jul 27, 2026 @ 18:11
311_C2 | 311_ | 8063 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 10:21 | Aug 10, 2026 @ 10:21
311_D2 | 311_ | 8058 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:47 | Aug 08, 2026 @ 08:47
311_D7 | 311_ | 8055 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:51 | Jun 01, 2026 @ 16:51
311_D4 | 311_ | 8053 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 311_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:47 | Aug 08, 2026 @ 08:47
1304F2 | 1304 | 8042 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:45 | Apr 23, 2026 @ 12:45
1304D4 | 1304 | 8040 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:17 | May 11, 2026 @ 12:17
1304D2 | 1304 | 8035 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:18 | May 05, 2026 @ 09:18
1304F3 | 1304 | 8032 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1304C2 | 1304 | 8026 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 09, 2026 @ 16:31 | May 09, 2026 @ 16:31
1304D7 | 1304 | 8024 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:44 | Apr 23, 2026 @ 13:44
310_F3 | 310_ | 8020 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
310_F2 | 310_ | 8006 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
310_C2 | 310_ | 8005 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:47 | Aug 10, 2026 @ 17:47
310_D2 | 310_ | 8000 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:49 | Aug 08, 2026 @ 08:49
310_D7 | 310_ | 7997 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:51 | Jun 01, 2026 @ 16:51
310_D4 | 310_ | 7996 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 310_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:49 | Aug 08, 2026 @ 08:49
1303F2 | 1303 | 7984 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:45 | Apr 23, 2026 @ 12:45
1303D4 | 1303 | 7982 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:18 | May 11, 2026 @ 12:18
1303D2 | 1303 | 7977 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:18 | May 05, 2026 @ 09:18
1303F3 | 1303 | 7974 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1303C2 | 1303 | 7967 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 09, 2026 @ 16:32 | May 09, 2026 @ 16:32
309_F3 | 309_ | 7965 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
1303D7 | 1303 | 7963 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:08 | Apr 22, 2026 @ 18:08
309_F2 | 309_ | 7948 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
309_C2 | 309_ | 7947 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 10:16 | Aug 10, 2026 @ 10:16
309_D2 | 309_ | 7942 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:49 | Aug 08, 2026 @ 08:49
309_D7 | 309_ | 7939 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 11:25 | Jun 01, 2026 @ 16:51
309_D4 | 309_ | 7938 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 309_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:49 | Aug 08, 2026 @ 08:49
1302F2 | 1302 | 7926 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:46 | Apr 23, 2026 @ 12:46
1302D4 | 1302 | 7924 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:18 | May 11, 2026 @ 12:18
1302D2 | 1302 | 7919 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 18:00 | May 11, 2026 @ 18:00
1302F3 | 1302 | 7916 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1302C2 | 1302 | 7910 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 01, 2026 @ 14:24 | Jun 01, 2026 @ 14:24
1302D7 | 1302 | 7908 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:08 | Apr 22, 2026 @ 18:08
308_F3 | 308_ | 7904 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
308_F2 | 308_ | 7890 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
308_C2 | 308_ | 7889 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:47 | Aug 10, 2026 @ 17:47
308_D2 | 308_ | 7884 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:50 | Aug 08, 2026 @ 08:50
308_D7 | 308_ | 7881 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:50 | Jun 01, 2026 @ 16:50
308_D4 | 308_ | 7880 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 308_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:50 | Aug 08, 2026 @ 08:50
1301F2 | 1301 | 7868 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:46 | Apr 23, 2026 @ 12:46
1301D4 | 1301 | 7866 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 11, 2026 @ 12:18 | May 11, 2026 @ 12:18
1301D2 | 1301 | 7861 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:19 | May 05, 2026 @ 09:19
1301F3 | 1301 | 7858 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1301C2 | 1301 | 7852 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 09, 2026 @ 16:33 | May 09, 2026 @ 16:33
1301D7 | 1301 | 7850 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:08 | Apr 22, 2026 @ 18:08
307_F3 | 307_ | 7846 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:46 | Jun 19, 2026 @ 13:46
307_F2 | 307_ | 7832 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:46 | Jun 19, 2026 @ 13:46
307_C2 | 307_ | 7831 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:34 | Aug 07, 2026 @ 09:34
307_D2 | 307_ | 7826 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:50 | Aug 08, 2026 @ 08:50
307_D7 | 307_ | 7823 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:50 | Jun 19, 2026 @ 11:50
307_D4 | 307_ | 7822 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 307_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1210F2 | 1210 | 7810 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:46 | Apr 23, 2026 @ 12:46
1210D4 | 1210 | 7808 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:22 | May 05, 2026 @ 09:22
1210D2 | 1210 | 7803 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:47 | Apr 23, 2026 @ 13:47
1210F3 | 1210 | 7800 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1210C2 | 1210 | 7794 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:28 | May 05, 2026 @ 09:28
1210D7 | 1210 | 7792 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:48 | Apr 15, 2026 @ 17:48
306_F3 | 306_ | 7788 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:46 | Jun 19, 2026 @ 13:46
306_F2 | 306_ | 7774 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 11 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:47 | Jun 19, 2026 @ 13:47
306_C2 | 306_ | 7773 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:33 | Aug 07, 2026 @ 09:33
306_D2 | 306_ | 7767 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:50 | Aug 08, 2026 @ 08:50
306_D7 | 306_ | 7760 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:50 | Jun 19, 2026 @ 11:50
306_D4 | 306_ | 7758 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 306_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1209F2 | 1209 | 7752 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 13 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:46 | Apr 23, 2026 @ 12:46
1209D4 | 1209 | 7750 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:23 | May 05, 2026 @ 09:23
1209D2 | 1209 | 7745 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:52 | Apr 23, 2026 @ 13:52
1209F3 | 1209 | 7742 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:50 | Apr 23, 2026 @ 12:50
1209C2 | 1209 | 7736 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:29 | May 05, 2026 @ 09:29
1209D7 | 1209 | 7734 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 4 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:48 | Apr 15, 2026 @ 17:48
305_F3 | 305_ | 7730 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:47 | Jun 19, 2026 @ 13:47
305_F2 | 305_ | 7715 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 13:47 | Jun 19, 2026 @ 13:47
305_C2 | 305_ | 7712 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:33 | Aug 07, 2026 @ 09:33
305_D2 | 305_ | 7702 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:51 | Aug 08, 2026 @ 08:51
1208F2 | 1208 | 7699 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:47 | Apr 23, 2026 @ 12:47
1208D4 | 1208 | 7696 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:23 | May 05, 2026 @ 09:23
305_D7 | 305_ | 7695 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:51 | Jun 19, 2026 @ 11:51
305_D4 | 305_ | 7693 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 305_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1208D2 | 1208 | 7687 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:56 | Apr 23, 2026 @ 13:56
1208F3 | 1208 | 7684 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:51 | Apr 23, 2026 @ 12:51
1208C2 | 1208 | 7678 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:29 | May 05, 2026 @ 09:29
1208D7 | 1208 | 7676 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:48 | Apr 15, 2026 @ 17:48
304_F3 | 304_ | 7672 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
304_F2 | 304_ | 7653 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 19, 2026 @ 15:50 | Jun 19, 2026 @ 15:50
304_C2 | 304_ | 7651 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:33 | Aug 07, 2026 @ 09:33
1207F2 | 1207 | 7644 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:47 | Apr 23, 2026 @ 12:47
304_D2 | 304_ | 7641 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:51 | Aug 08, 2026 @ 08:51
1207D4 | 1207 | 7640 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 14, 2026 @ 08:59 | May 14, 2026 @ 08:59
304_D7 | 304_ | 7635 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:51 | Jun 19, 2026 @ 11:51
304_D4 | 304_ | 7633 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 304_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1207D2 | 1207 | 7629 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:52 | Apr 23, 2026 @ 13:52
1207F3 | 1207 | 7626 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:51 | Apr 23, 2026 @ 12:51
1207C2 | 1207 | 7620 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:30 | May 05, 2026 @ 09:30
1207D7 | 1207 | 7618 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:47 | Apr 15, 2026 @ 17:47
303_F3 | 303_ | 7614 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
303_F2 | 303_ | 7595 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
303_C2 | 303_ | 7593 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:32 | Aug 07, 2026 @ 09:32
1206F2 | 1206 | 7587 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:47 | Apr 23, 2026 @ 12:47
1206D4 | 1206 | 7583 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:25 | May 05, 2026 @ 09:25
303_D2 | 303_ | 7581 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:51 | Aug 08, 2026 @ 08:51
303_D7 | 303_ | 7576 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:51 | Jun 19, 2026 @ 11:51
303_D4 | 303_ | 7574 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 303_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1206D2 | 1206 | 7573 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:53 | Apr 23, 2026 @ 13:53
1206F3 | 1206 | 7568 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:51 | Apr 23, 2026 @ 12:51
1206C2 | 1206 | 7562 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:30 | May 05, 2026 @ 09:30
1206D7 | 1206 | 7560 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:47 | Apr 15, 2026 @ 17:47
302_F3 | 302_ | 7556 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
302_F2 | 302_ | 7537 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
302_C2 | 302_ | 7534 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:32 | Aug 07, 2026 @ 09:32
1205F2 | 1205 | 7529 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:47 | Apr 23, 2026 @ 12:47
1205D4 | 1205 | 7525 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:25 | May 05, 2026 @ 09:25
302_D2 | 302_ | 7524 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:51 | Aug 08, 2026 @ 08:51
302_D7 | 302_ | 7518 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 11:15 | Jun 19, 2026 @ 11:52
302_D4 | 302_ | 7516 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 302_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:29 | Aug 07, 2026 @ 09:29
1205D2 | 1205 | 7515 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 08:19 | May 05, 2026 @ 08:19
1205F3 | 1205 | 7510 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:52 | Apr 23, 2026 @ 12:52
1205C2 | 1205 | 7504 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 02, 2026 @ 08:14 | May 02, 2026 @ 08:14
1205D7 | 1205 | 7502 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:46 | Apr 15, 2026 @ 17:46
301_F3 | 301_ | 7498 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
301_F2 | 301_ | 7477 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 09:28 | Jun 20, 2026 @ 09:28
301_C2 | 301_ | 7474 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
1204F2 | 1204 | 7472 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 01, 2026 @ 17:30 | May 01, 2026 @ 17:30
1204D4 | 1204 | 7469 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 03, 2026 @ 09:53 | May 03, 2026 @ 09:53
301_D2 | 301_ | 7463 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:52 | Aug 08, 2026 @ 08:52
1204D2 | 1204 | 7459 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 03, 2026 @ 09:52 | May 03, 2026 @ 09:52
301_D7 | 301_ | 7458 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:52 | Jun 19, 2026 @ 11:52
301_D4 | 301_ | 7456 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 301_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:30 | Aug 07, 2026 @ 09:30
1204F3 | 1204 | 7453 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 03, 2026 @ 09:56 | May 03, 2026 @ 09:56
1204D7 | 1204 | 7444 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:46 | Apr 15, 2026 @ 17:46
212_F3 | 212_ | 7440 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:12 | Jul 27, 2026 @ 18:12
212_F2 | 212_ | 7421 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
212_C2 | 212_ | 7419 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 09, 2026 @ 17:12 | Aug 08, 2026 @ 17:02
1203F2 | 1203 | 7413 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 04, 2026 @ 10:03 | May 04, 2026 @ 10:03
1203D4 | 1203 | 7409 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:26 | May 05, 2026 @ 09:26
212_D2 | 212_ | 7408 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:07 | Aug 12, 2026 @ 09:07
212_D7 | 212_ | 7402 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:50 | Jun 01, 2026 @ 16:50
212_D4 | 212_ | 7401 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 212_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:54 | Aug 08, 2026 @ 08:54
1203D2 | 1203 | 7398 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 08:19 | May 05, 2026 @ 08:19
1203F3 | 1203 | 7394 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | May 05, 2026 @ 09:12 | May 05, 2026 @ 09:12
1203C2 | 1203 | 7388 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:30 | May 05, 2026 @ 09:30
1203D7 | 1203 | 7386 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:46 | Apr 15, 2026 @ 17:45
211_F3 | 211_ | 7382 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
211_F2 | 211_ | 7361 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
211_C2 | 211_ | 7359 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 09, 2026 @ 17:13 | Aug 08, 2026 @ 18:08
1202F2 | 1202 | 7356 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:48 | Apr 23, 2026 @ 12:48
1202D4 | 1202 | 7353 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:26 | May 05, 2026 @ 09:26
211_D2 | 211_ | 7349 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:07 | Aug 12, 2026 @ 09:07
211_D7 | 211_ | 7344 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 11:09 | Jun 01, 2026 @ 16:50
1202D2 | 1202 | 7342 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1202_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:54 | Apr 23, 2026 @ 13:54
211_D4 | 211_ | 7341 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 211_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:55 | Aug 08, 2026 @ 08:55
1202F3 | 1202 | 7337 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:52 | Apr 23, 2026 @ 12:52
1202C2 | 1202 | 7330 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:31 | May 05, 2026 @ 09:31
1202D7 | 1202 | 7328 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1202_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:45 | Apr 15, 2026 @ 17:45
210_F3 | 210_ | 7324 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
210_F2 | 210_ | 7304 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
210_C2 | 210_ | 7302 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:49 | Aug 10, 2026 @ 17:49
1201F2 | 1201 | 7297 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:48 | Apr 23, 2026 @ 12:48
1201D4 | 1201 | 7294 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | May 05, 2026 @ 09:27 | May 05, 2026 @ 09:27
210_D2 | 210_ | 7291 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:08 | Aug 12, 2026 @ 09:08
210_D7 | 210_ | 7286 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:49 | Jun 01, 2026 @ 16:49
210_D4 | 210_ | 7284 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 210_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:55 | Aug 08, 2026 @ 08:55
1201D2 | 1201 | 7283 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 23, 2026 @ 13:55 | Apr 23, 2026 @ 13:55
1201F3 | 1201 | 7278 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 23, 2026 @ 12:52 | Apr 23, 2026 @ 12:52
1201C2 | 1201 | 7272 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | May 05, 2026 @ 09:31 | May 05, 2026 @ 09:31
1201D7 | 1201 | 7270 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 15, 2026 @ 17:44 | Apr 15, 2026 @ 17:44
209_F3 | 209_ | 7266 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
209_F2 | 209_ | 7249 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
209_C2 | 209_ | 7247 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:49 | Aug 10, 2026 @ 17:49
1109F2 | 1109 | 7237 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:54 | Apr 24, 2026 @ 14:54
209_D2 | 209_ | 7236 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:08 | Aug 12, 2026 @ 09:08
1109D4 | 1109 | 7233 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
209_D7 | 209_ | 7230 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:49 | Jun 01, 2026 @ 16:49
209_D4 | 209_ | 7228 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 209_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:55 | Aug 08, 2026 @ 08:55
1109D2 | 1109 | 7223 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 17:44 | Jun 12, 2026 @ 17:44
1109F3 | 1109 | 7220 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:55 | Apr 24, 2026 @ 14:55
1109C2 | 1109 | 7214 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
1109D7 | 1109 | 7212 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:06 | Apr 22, 2026 @ 18:06
208_F3 | 208_ | 7208 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
208_F2 | 208_ | 7194 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:13 | Jul 27, 2026 @ 18:13
208_C2 | 208_ | 7192 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:49 | Aug 10, 2026 @ 17:49
208_D2 | 208_ | 7182 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 11, 2026 @ 16:57 | Aug 11, 2026 @ 16:57
208_D7 | 208_ | 7177 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 01, 2026 @ 11:04 | Jun 01, 2026 @ 16:49
1108F2 | 1108 | 7175 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:55 | Apr 24, 2026 @ 14:55
208_D4 | 208_ | 7174 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 208_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:56 | Aug 08, 2026 @ 08:56
1108D4 | 1108 | 7171 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1108D2 | 1108 | 7165 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1108F3 | 1108 | 7162 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:55 | Apr 24, 2026 @ 14:55
1108C2 | 1108 | 7156 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
1108D7 | 1108 | 7154 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:06 | Apr 22, 2026 @ 18:06
207_F3 | 207_ | 7150 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:37 | Jun 20, 2026 @ 14:37
207_F2 | 207_ | 7133 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:38 | Jun 20, 2026 @ 14:38
207_C2 | 207_ | 7130 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
1107F2 | 1107 | 7121 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:55 | Apr 24, 2026 @ 14:55
207_D2 | 207_ | 7120 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 11, 2026 @ 16:48 | Aug 11, 2026 @ 16:48
1107D4 | 1107 | 7117 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
207_D7 | 207_ | 7114 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:52 | Jun 19, 2026 @ 11:52
207_D4 | 207_ | 7112 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 207_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:12 | Aug 07, 2026 @ 13:12
1107D2 | 1107 | 7107 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1107_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1107F3 | 1107 | 7104 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:56 | Apr 24, 2026 @ 14:56
1107C2 | 1107 | 7098 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 12, 2026 @ 10:15 | Jun 12, 2026 @ 10:15
1107D7 | 1107 | 7096 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1107_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:06 | Apr 22, 2026 @ 18:06
206_F3 | 206_ | 7092 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:38 | Jun 20, 2026 @ 14:38
206_F2 | 206_ | 7073 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:39 | Jun 20, 2026 @ 14:39
206_C2 | 206_ | 7070 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
1106F2 | 1106 | 7065 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 5 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:56 | Apr 24, 2026 @ 14:56
1106D4 | 1106 | 7061 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 14:06 | Jun 11, 2026 @ 09:15
206_D2 | 206_ | 7060 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:08 | Aug 12, 2026 @ 09:08
206_D7 | 206_ | 7054 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:53 | Jun 19, 2026 @ 11:53
206_D4 | 206_ | 7052 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 206_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:12 | Aug 07, 2026 @ 13:12
1106D2 | 1106 | 7051 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1106_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:57 | Jun 11, 2026 @ 09:15
1106F3 | 1106 | 7046 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:56 | Apr 24, 2026 @ 14:56
1106C2 | 1106 | 7040 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 14:29 | Jun 11, 2026 @ 14:29
1106D7 | 1106 | 7038 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1106_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:05 | Apr 22, 2026 @ 18:05
205_F3 | 205_ | 7034 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:39 | Jun 20, 2026 @ 14:39
205_F2 | 205_ | 7013 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:39 | Jun 20, 2026 @ 14:39
205_C2 | 205_ | 7011 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
1105F2 | 1105 | 7007 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:57 | Apr 24, 2026 @ 14:57
1105D4 | 1105 | 7004 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
205_D2 | 205_ | 7001 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:09 | Aug 12, 2026 @ 09:09
205_D7 | 205_ | 6996 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:53 | Jun 19, 2026 @ 11:53
1105D2 | 1105 | 6994 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1105_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jul 07, 2026 @ 12:21 | Jul 07, 2026 @ 12:21
205_D4 | 205_ | 6993 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 205_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:11 | Aug 07, 2026 @ 13:11
1105F3 | 1105 | 6988 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:57 | Apr 24, 2026 @ 14:57
1105C2 | 1105 | 6982 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 12:54 | Jun 10, 2026 @ 15:26
1105D7 | 1105 | 6980 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1105_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:05 | Apr 22, 2026 @ 18:05
204_F3 | 204_ | 6976 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:40 | Jun 20, 2026 @ 14:40
204_F2 | 204_ | 6955 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:40 | Jun 20, 2026 @ 14:40
204_C2 | 204_ | 6953 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
1104F2 | 1104 | 6950 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:57 | Apr 24, 2026 @ 14:57
1104D4 | 1104 | 6947 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:00 | Jun 10, 2026 @ 18:35
204_D2 | 204_ | 6942 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:09 | Aug 12, 2026 @ 09:09
204_D7 | 204_ | 6937 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:53 | Jun 19, 2026 @ 11:53
1104D2 | 1104 | 6936 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1104_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:56 | Jun 10, 2026 @ 18:35
204_D4 | 204_ | 6935 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 204_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:11 | Aug 07, 2026 @ 13:11
1104F3 | 1104 | 6930 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:58 | Apr 24, 2026 @ 14:58
1104C2 | 1104 | 6924 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 12:53 | Jun 10, 2026 @ 15:27
1104D7 | 1104 | 6922 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1104_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:04 | Apr 22, 2026 @ 18:04
203_F3 | 203_ | 6918 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:40 | Jun 20, 2026 @ 14:40
203_F2 | 203_ | 6904 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 7 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:55 | Jun 20, 2026 @ 14:55
203_C2 | 203_ | 6903 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
203_D2 | 203_ | 6897 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 11, 2026 @ 17:50 | Aug 11, 2026 @ 17:50
203_D7 | 203_ | 6892 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:53 | Jun 19, 2026 @ 11:53
203_D4 | 203_ | 6889 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 203_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:11 | Aug 07, 2026 @ 13:11
1103F2 | 1103 | 6882 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:58 | Apr 24, 2026 @ 14:58
1103D4 | 1103 | 6880 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 14:22 | Jun 11, 2026 @ 14:22
1103D2 | 1103 | 6875 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1103_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 14:20 | Jun 11, 2026 @ 14:20
1103F3 | 1103 | 6872 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:58 | Apr 24, 2026 @ 14:58
1103C2 | 1103 | 6866 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 14:20 | Jun 11, 2026 @ 14:20
1103D7 | 1103 | 6864 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1103_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:04 | Apr 22, 2026 @ 18:04
201_F3 | 201_ | 6860 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:55 | Jun 20, 2026 @ 14:55
201_F2 | 201_ | 6845 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 20, 2026 @ 14:56 | Jun 20, 2026 @ 14:56
201_C2 | 201_ | 6843 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:31 | Aug 07, 2026 @ 09:31
201_D2 | 201_ | 6832 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:09 | Aug 12, 2026 @ 09:09
1102F2 | 1102 | 6829 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:58 | Apr 24, 2026 @ 14:58
201_D7 | 201_ | 6826 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 19, 2026 @ 11:53 | Jun 19, 2026 @ 11:53
1102D4 | 1102 | 6825 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 10, 2026 @ 17:49 | Jun 10, 2026 @ 17:49
201_D4 | 201_ | 6824 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 201_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:11 | Aug 07, 2026 @ 13:11
1102D2 | 1102 | 6817 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1102_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 11, 2026 @ 13:55 | Jun 10, 2026 @ 17:49
1102F3 | 1102 | 6814 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 14:59 | Apr 24, 2026 @ 14:59
1102C2 | 1102 | 6808 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 12:53 | Jun 10, 2026 @ 15:28
1102D7 | 1102 | 6806 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1102_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:04 | Apr 22, 2026 @ 18:04
112_F3 | 112_ | 6802 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
112_F2 | 112_ | 6788 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
112_C2 | 112_ | 6787 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:37 | Aug 07, 2026 @ 09:37
112_D2 | 112_ | 6777 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 13, 2026 @ 08:23 | Aug 13, 2026 @ 08:23
112_D7 | 112_ | 6771 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:42 | Jun 01, 2026 @ 16:42
112_D4 | 112_ | 6769 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 112_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:30 | Aug 07, 2026 @ 09:30
1101F2 | 1101 | 6767 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 8 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 15:00 | Apr 24, 2026 @ 15:00
1101D4 | 1101 | 6764 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1101_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1101D2 | 1101 | 6759 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1101_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 12, 2026 @ 09:44 | Jun 12, 2026 @ 09:44
1101F3 | 1101 | 6756 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Apr 24, 2026 @ 15:00 | Apr 24, 2026 @ 15:00
1101C2 | 1101 | 6750 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 1101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Jun 11, 2026 @ 12:52 | Jun 10, 2026 @ 15:30
1101D7 | 1101 | 6748 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Issue | 1101_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Apr 22, 2026 @ 18:03 | Apr 22, 2026 @ 18:03
111_F3 | 111_ | 6744 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
111_F2 | 111_ | 6730 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
111_C2 | 111_ | 6729 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 10, 2026 @ 17:49 | Aug 10, 2026 @ 17:49
111_D2 | 111_ | 6724 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 18:11 | Aug 12, 2026 @ 18:11
111_D7 | 111_ | 6721 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:42 | Jun 01, 2026 @ 16:42
111_D4 | 111_ | 6720 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 111_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:30 | Aug 07, 2026 @ 09:30
110_F3 | 110_ | 6715 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
110_F2 | 110_ | 6701 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 6 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
110_C2 | 110_ | 6700 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:37 | Aug 07, 2026 @ 09:37
110_D2 | 110_ | 6695 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 13, 2026 @ 08:23 | Aug 13, 2026 @ 08:23
110_D7 | 110_ | 6692 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:41 | Jun 01, 2026 @ 16:41
110_D4 | 110_ | 6691 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 110_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 09:30 | Aug 07, 2026 @ 09:30
109_F3 | 109_ | 6686 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
109_F2 | 109_ | 6672 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 9 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
109_C2 | 109_ | 6671 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:37 | Aug 07, 2026 @ 09:37
109_D2 | 109_ | 6666 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 18:09 | Aug 12, 2026 @ 18:09
109_D7 | 109_ | 6663 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:40 | Jun 01, 2026 @ 16:40
109_D4 | 109_ | 6662 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 109_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:57 | Aug 08, 2026 @ 08:57
108_F3 | 108_ | 6657 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
108_F2 | 108_ | 6643 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 12 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:14 | Jul 27, 2026 @ 18:14
108_C2 | 108_ | 6642 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 09:37 | Aug 07, 2026 @ 09:37
108_D2 | 108_ | 6637 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 13, 2026 @ 08:24 | Aug 13, 2026 @ 08:24
108_D7 | 108_ | 6634 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F |  |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 01, 2026 @ 16:40 | Jun 01, 2026 @ 16:39
108_D4 | 108_ | 6633 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 04:00 | closed | Planned Work | 108_Main 1 Sub B C D E F | 202 |  | sathvik@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 08, 2026 @ 08:59 | Aug 08, 2026 @ 08:59
202_C2 | 202_ | 6629 | C2 | C2 Gas Detector/FAS Integration IR | Gas Detector/FAS Integration IR | Jan 08, 2026 @ 16:13 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 3 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub C - LPG T&C | Aug 07, 2026 @ 13:10 | Aug 07, 2026 @ 13:10
202_F3 | 202_ | 6609 | F3 | F3 FAS Integration IR | FAS Integration IR | Jan 08, 2026 @ 15:50 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jun 23, 2026 @ 09:01 | Jun 23, 2026 @ 09:01
202_F2 | 202_ | 6608 | F2 | F2 Heat/Smoke Detector IR | Heat/Smoke Detector IR | Jan 08, 2026 @ 15:49 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 10 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub F - Fire Fighting T&C | Jul 27, 2026 @ 18:15 | Jul 27, 2026 @ 18:15
202_D7 | 202_ | 6594 | D7 | D7 Booster IR | Booster IR | Jan 08, 2026 @ 15:30 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 1 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Jun 23, 2026 @ 08:32 | Jun 23, 2026 @ 08:31
202_D4 | 202_ | 6591 | D4 | D4 Intercom IR | Intercom IR | Jan 08, 2026 @ 15:29 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 07, 2026 @ 13:10 | Aug 07, 2026 @ 13:10
202_D2 | 202_ | 6589 | D2 | D2 ONU Panel/Data Points IR | ONU Panel/Data Points IR | Jan 08, 2026 @ 15:29 | closed | Planned Work | 202_M:1 S:B C D E F | Mockup-202 |  | dharmaraja.kalimuthu@sobhaconst.com |  |  | 2 | blue | No |  |  |  | Unspecified |  | Unspecified | Sub D - Electrical T&C | Aug 12, 2026 @ 09:12 | Aug 12, 2026 @ 09:12
APROVED
NOT APROVED
IN PROCESS
REJECT

## SUMMARY
SUMMARY | STAMS : | LPG | ONU | INTERCOM | BOOSTER | SMOKE | SMOKE
|  | C2 | D2 | D4 | D7 | F2 | F3
| TOTAL | 355 | 355 | 355 | 355 | 355 | 355
| OPEN | 0 | 0 | 0 | 0 | 0 | 0
| REVIEW | 0 | 4 | 0 | 0 | 0 | 0
| PENDING | 0 | 0 | 0 | 0 | 0 | 0
| CLOSED | 355 | 351 | 355 | 355 | 355 | 355
| % | 100% | 98.87% | 100% | 100% | 100% | 100%

## STAMP
FLAT NO | C2 | D2 | D4 | D7 | F2 | F3 | REMARK
1609 | closed | review | closed | closed | closed | closed | D2 (WIR)
809_ | closed | review | closed | closed | closed | closed | D2 (WIR)
1009 | closed | review | closed | closed | closed | closed | D2 (WIR)
1409 | closed | review | closed | closed | closed | closed | D2 (WIR)
108_ | closed | closed | closed | closed | closed | closed
109_ | closed | closed | closed | closed | closed | closed
110_ | closed | closed | closed | closed | closed | closed
112_ | closed | closed | closed | closed | closed | closed
201_ | closed | closed | closed | closed | closed | closed
202_ | closed | closed | closed | closed | closed | closed
203_ | closed | closed | closed | closed | closed | closed
204_ | closed | closed | closed | closed | closed | closed
205_ | closed | closed | closed | closed | closed | closed
206_ | closed | closed | closed | closed | closed | closed
207_ | closed | closed | closed | closed | closed | closed
111_ | closed | closed | closed | closed | closed | closed
208_ | closed | closed | closed | closed | closed | closed
209_ | closed | closed | closed | closed | closed | closed
210_ | closed | closed | closed | closed | closed | closed
211_ | closed | closed | closed | closed | closed | closed
212_ | closed | closed | closed | closed | closed | closed
308_ | closed | closed | closed | closed | closed | closed
309_ | closed | closed | closed | closed | closed | closed
310_ | closed | closed | closed | closed | closed | closed
311_ | closed | closed | closed | closed | closed | closed
312_ | closed | closed | closed | closed | closed | closed
408_ | closed | closed | closed | closed | closed | closed
509_ | closed | closed | closed | closed | closed | closed
301_ | closed | closed | closed | closed | closed | closed
302_ | closed | closed | closed | closed | closed | closed
303_ | closed | closed | closed | closed | closed | closed
304_ | closed | closed | closed | closed | closed | closed
305_ | closed | closed | closed | closed | closed | closed
306_ | closed | closed | closed | closed | closed | closed
307_ | closed | closed | closed | closed | closed | closed
405_ | closed | closed | closed | closed | closed | closed
406_ | closed | closed | closed | closed | closed | closed
409_ | closed | closed | closed | closed | closed | closed
410_ | closed | closed | closed | closed | closed | closed
411_ | closed | closed | closed | closed | closed | closed
412_ | closed | closed | closed | closed | closed | closed
501_ | closed | closed | closed | closed | closed | closed
502_ | closed | closed | closed | closed | closed | closed
503_ | closed | closed | closed | closed | closed | closed
504_ | closed | closed | closed | closed | closed | closed
505_ | closed | closed | closed | closed | closed | closed
506_ | closed | closed | closed | closed | closed | closed
507_ | closed | closed | closed | closed | closed | closed
508_ | closed | closed | closed | closed | closed | closed
510_ | closed | closed | closed | closed | closed | closed
511_ | closed | closed | closed | closed | closed | closed
512_ | closed | closed | closed | closed | closed | closed
605_ | closed | closed | closed | closed | closed | closed
606_ | closed | closed | closed | closed | closed | closed
607_ | closed | closed | closed | closed | closed | closed
608_ | closed | closed | closed | closed | closed | closed
401_ | closed | closed | closed | closed | closed | closed
402_ | closed | closed | closed | closed | closed | closed
403_ | closed | closed | closed | closed | closed | closed
404_ | closed | closed | closed | closed | closed | closed
407_ | closed | closed | closed | closed | closed | closed
601_ | closed | closed | closed | closed | closed | closed
602_ | closed | closed | closed | closed | closed | closed
603_ | closed | closed | closed | closed | closed | closed
604_ | closed | closed | closed | closed | closed | closed
609_ | closed | closed | closed | closed | closed | closed
701_ | closed | closed | closed | closed | closed | closed
702_ | closed | closed | closed | closed | closed | closed
703_ | closed | closed | closed | closed | closed | closed
704_ | closed | closed | closed | closed | closed | closed
705_ | closed | closed | closed | closed | closed | closed
706_ | closed | closed | closed | closed | closed | closed
707_ | closed | closed | closed | closed | closed | closed
708_ | closed | closed | closed | closed | closed | closed
709_ | closed | closed | closed | closed | closed | closed
801_ | closed | closed | closed | closed | closed | closed
802_ | closed | closed | closed | closed | closed | closed
803_ | closed | closed | closed | closed | closed | closed
804_ | closed | closed | closed | closed | closed | closed
805_ | closed | closed | closed | closed | closed | closed
806_ | closed | closed | closed | closed | closed | closed
807_ | closed | closed | closed | closed | closed | closed
808_ | closed | closed | closed | closed | closed | closed
810_ | closed | closed | closed | closed | closed | closed
901_ | closed | closed | closed | closed | closed | closed
902_ | closed | closed | closed | closed | closed | closed
903_ | closed | closed | closed | closed | closed | closed
904_ | closed | closed | closed | closed | closed | closed
905_ | closed | closed | closed | closed | closed | closed
906_ | closed | closed | closed | closed | closed | closed
907_ | closed | closed | closed | closed | closed | closed
908_ | closed | closed | closed | closed | closed | closed
909_ | closed | closed | closed | closed | closed | closed
1001 | closed | closed | closed | closed | closed | closed
1002 | closed | closed | closed | closed | closed | closed
1003 | closed | closed | closed | closed | closed | closed
1004 | closed | closed | closed | closed | closed | closed
1005 | closed | closed | closed | closed | closed | closed
1006 | closed | closed | closed | closed | closed | closed
1007 | closed | closed | closed | closed | closed | closed
1008 | closed | closed | closed | closed | closed | closed
1010 | closed | closed | closed | closed | closed | closed
1101 | closed | closed | closed | closed | closed | closed
1102 | closed | closed | closed | closed | closed | closed
1103 | closed | closed | closed | closed | closed | closed
1104 | closed | closed | closed | closed | closed | closed
1105 | closed | closed | closed | closed | closed | closed
1106 | closed | closed | closed | closed | closed | closed
1107 | closed | closed | closed | closed | closed | closed
1108 | closed | closed | closed | closed | closed | closed
1109 | closed | closed | closed | closed | closed | closed
1201 | closed | closed | closed | closed | closed | closed
1202 | closed | closed | closed | closed | closed | closed
1203 | closed | closed | closed | closed | closed | closed
1204 | closed | closed | closed | closed | closed | closed
1205 | closed | closed | closed | closed | closed | closed
1206 | closed | closed | closed | closed | closed | closed
1207 | closed | closed | closed | closed | closed | closed
1208 | closed | closed | closed | closed | closed | closed
1209 | closed | closed | closed | closed | closed | closed
1210 | closed | closed | closed | closed | closed | closed
1301 | closed | closed | closed | closed | closed | closed
1302 | closed | closed | closed | closed | closed | closed
1303 | closed | closed | closed | closed | closed | closed
1304 | closed | closed | closed | closed | closed | closed
1305 | closed | closed | closed | closed | closed | closed
1306 | closed | closed | closed | closed | closed | closed
1307 | closed | closed | closed | closed | closed | closed
1308 | closed | closed | closed | closed | closed | closed
1309 | closed | closed | closed | closed | closed | closed
1401 | closed | closed | closed | closed | closed | closed
1402 | closed | closed | closed | closed | closed | closed
1403 | closed | closed | closed | closed | closed | closed
1404 | closed | closed | closed | closed | closed | closed
1405 | closed | closed | closed | closed | closed | closed
1406 | closed | closed | closed | closed | closed | closed
1407 | closed | closed | closed | closed | closed | closed
1408 | closed | closed | closed | closed | closed | closed
1410 | closed | closed | closed | closed | closed | closed
1501 | closed | closed | closed | closed | closed | closed
1502 | closed | closed | closed | closed | closed | closed
1503 | closed | closed | closed | closed | closed | closed
1504 | closed | closed | closed | closed | closed | closed
1505 | closed | closed | closed | closed | closed | closed
1506 | closed | closed | closed | closed | closed | closed
1507 | closed | closed | closed | closed | closed | closed
1508 | closed | closed | closed | closed | closed | closed
1509 | closed | closed | closed | closed | closed | closed
1601 | closed | closed | closed | closed | closed | closed
1602 | closed | closed | closed | closed | closed | closed
1603 | closed | closed | closed | closed | closed | closed
1604 | closed | closed | closed | closed | closed | closed
1605 | closed | closed | closed | closed | closed | closed
1606 | closed | closed | closed | closed | closed | closed
1607 | closed | closed | closed | closed | closed | closed
1608 | closed | closed | closed | closed | closed | closed
1610 | closed | closed | closed | closed | closed | closed
1701 | closed | closed | closed | closed | closed | closed
1702 | closed | closed | closed | closed | closed | closed
1703 | closed | closed | closed | closed | closed | closed
1704 | closed | closed | closed | closed | closed | closed
1705 | closed | closed | closed | closed | closed | closed
1706 | closed | closed | closed | closed | closed | closed
1707 | closed | closed | closed | closed | closed | closed
1708 | closed | closed | closed | closed | closed | closed
1709 | closed | closed | closed | closed | closed | closed
1801 | closed | closed | closed | closed | closed | closed
1802 | closed | closed | closed | closed | closed | closed
1803 | closed | closed | closed | closed | closed | closed
1804 | closed | closed | closed | closed | closed | closed
1805 | closed | closed | closed | closed | closed | closed
1806 | closed | closed | closed | closed | closed | closed
1807 | closed | closed | closed | closed | closed | closed
1808 | closed | closed | closed | closed | closed | closed
1809 | closed | closed | closed | closed | closed | closed
1810 | closed | closed | closed | closed | closed | closed
1901 | closed | closed | closed | closed | closed | closed
1902 | closed | closed | closed | closed | closed | closed
1903 | closed | closed | closed | closed | closed | closed
1904 | closed | closed | closed | closed | closed | closed
1905 | closed | closed | closed | closed | closed | closed
1906 | closed | closed | closed | closed | closed | closed
1907 | closed | closed | closed | closed | closed | closed
1908 | closed | closed | closed | closed | closed | closed
1909 | closed | closed | closed | closed | closed | closed
2001 | closed | closed | closed | closed | closed | closed
2002 | closed | closed | closed | closed | closed | closed
2003 | closed | closed | closed | closed | closed | closed
2005 | closed | closed | closed | closed | closed | closed
2006 | closed | closed | closed | closed | closed | closed
2007 | closed | closed | closed | closed | closed | closed
2008 | closed | closed | closed | closed | closed | closed
2009 | closed | closed | closed | closed | closed | closed
2010 | closed | closed | closed | closed | closed | closed
2101 | closed | closed | closed | closed | closed | closed
2102 | closed | closed | closed | closed | closed | closed
2103 | closed | closed | closed | closed | closed | closed
2104 | closed | closed | closed | closed | closed | closed
2105 | closed | closed | closed | closed | closed | closed
2106 | closed | closed | closed | closed | closed | closed
2107 | closed | closed | closed | closed | closed | closed
2108 | closed | closed | closed | closed | closed | closed
2109 | closed | closed | closed | closed | closed | closed
2201 | closed | closed | closed | closed | closed | closed
2202 | closed | closed | closed | closed | closed | closed
2203 | closed | closed | closed | closed | closed | closed
2204 | closed | closed | closed | closed | closed | closed
2205 | closed | closed | closed | closed | closed | closed
2206 | closed | closed | closed | closed | closed | closed
2207 | closed | closed | closed | closed | closed | closed
2208 | closed | closed | closed | closed | closed | closed
2209 | closed | closed | closed | closed | closed | closed
2210 | closed | closed | closed | closed | closed | closed
2301 | closed | closed | closed | closed | closed | closed
2302 | closed | closed | closed | closed | closed | closed
2303 | closed | closed | closed | closed | closed | closed
2304 | closed | closed | closed | closed | closed | closed
2305 | closed | closed | closed | closed | closed | closed
2306 | closed | closed | closed | closed | closed | closed
2307 | closed | closed | closed | closed | closed | closed
2308 | closed | closed | closed | closed | closed | closed
2309 | closed | closed | closed | closed | closed | closed
2401 | closed | closed | closed | closed | closed | closed
2402 | closed | closed | closed | closed | closed | closed
2403 | closed | closed | closed | closed | closed | closed
2404 | closed | closed | closed | closed | closed | closed
2405 | closed | closed | closed | closed | closed | closed
2406 | closed | closed | closed | closed | closed | closed
2407 | closed | closed | closed | closed | closed | closed
2408 | closed | closed | closed | closed | closed | closed
2409 | closed | closed | closed | closed | closed | closed
2410 | closed | closed | closed | closed | closed | closed
2501 | closed | closed | closed | closed | closed | closed
2502 | closed | closed | closed | closed | closed | closed
2503 | closed | closed | closed | closed | closed | closed
2504 | closed | closed | closed | closed | closed | closed
2505 | closed | closed | closed | closed | closed | closed
2506 | closed | closed | closed | closed | closed | closed
2507 | closed | closed | closed | closed | closed | closed
2508 | closed | closed | closed | closed | closed | closed
2509 | closed | closed | closed | closed | closed | closed
2601 | closed | closed | closed | closed | closed | closed
2602 | closed | closed | closed | closed | closed | closed
2603 | closed | closed | closed | closed | closed | closed
2604 | closed | closed | closed | closed | closed | closed
2605 | closed | closed | closed | closed | closed | closed
2606 | closed | closed | closed | closed | closed | closed
2607 | closed | closed | closed | closed | closed | closed
2608 | closed | closed | closed | closed | closed | closed
2609 | closed | closed | closed | closed | closed | closed
2610 | closed | closed | closed | closed | closed | closed
2701 | closed | closed | closed | closed | closed | closed
2702 | closed | closed | closed | closed | closed | closed
2703 | closed | closed | closed | closed | closed | closed
2704 | closed | closed | closed | closed | closed | closed
2705 | closed | closed | closed | closed | closed | closed
2706 | closed | closed | closed | closed | closed | closed
2707 | closed | closed | closed | closed | closed | closed
2708 | closed | closed | closed | closed | closed | closed
2709 | closed | closed | closed | closed | closed | closed
2801 | closed | closed | closed | closed | closed | closed
2802 | closed | closed | closed | closed | closed | closed
2803 | closed | closed | closed | closed | closed | closed
2804 | closed | closed | closed | closed | closed | closed
2805 | closed | closed | closed | closed | closed | closed
2806 | closed | closed | closed | closed | closed | closed
2807 | closed | closed | closed | closed | closed | closed
2808 | closed | closed | closed | closed | closed | closed
2809 | closed | closed | closed | closed | closed | closed
2810 | closed | closed | closed | closed | closed | closed
2901 | closed | closed | closed | closed | closed | closed
2902 | closed | closed | closed | closed | closed | closed
2903 | closed | closed | closed | closed | closed | closed
2904 | closed | closed | closed | closed | closed | closed
2905 | closed | closed | closed | closed | closed | closed
2906 | closed | closed | closed | closed | closed | closed
2907 | closed | closed | closed | closed | closed | closed
2908 | closed | closed | closed | closed | closed | closed
2909 | closed | closed | closed | closed | closed | closed
3001 | closed | closed | closed | closed | closed | closed
3002 | closed | closed | closed | closed | closed | closed
3003 | closed | closed | closed | closed | closed | closed
3004 | closed | closed | closed | closed | closed | closed
3005 | closed | closed | closed | closed | closed | closed
3006 | closed | closed | closed | closed | closed | closed
3007 | closed | closed | closed | closed | closed | closed
3008 | closed | closed | closed | closed | closed | closed
3009 | closed | closed | closed | closed | closed | closed
3010 | closed | closed | closed | closed | closed | closed
3101 | closed | closed | closed | closed | closed | closed
3102 | closed | closed | closed | closed | closed | closed
3103 | closed | closed | closed | closed | closed | closed
3104 | closed | closed | closed | closed | closed | closed
3105 | closed | closed | closed | closed | closed | closed
3106 | closed | closed | closed | closed | closed | closed
3107 | closed | closed | closed | closed | closed | closed
3108 | closed | closed | closed | closed | closed | closed
3109 | closed | closed | closed | closed | closed | closed
3201 | closed | closed | closed | closed | closed | closed
3202 | closed | closed | closed | closed | closed | closed
3203 | closed | closed | closed | closed | closed | closed
3204 | closed | closed | closed | closed | closed | closed
3205 | closed | closed | closed | closed | closed | closed
3206 | closed | closed | closed | closed | closed | closed
3207 | closed | closed | closed | closed | closed | closed
3208 | closed | closed | closed | closed | closed | closed
3209 | closed | closed | closed | closed | closed | closed
3210 | closed | closed | closed | closed | closed | closed
3301 | closed | closed | closed | closed | closed | closed
3302 | closed | closed | closed | closed | closed | closed
3303 | closed | closed | closed | closed | closed | closed
3304 | closed | closed | closed | closed | closed | closed
3305 | closed | closed | closed | closed | closed | closed
3306 | closed | closed | closed | closed | closed | closed
3307 | closed | closed | closed | closed | closed | closed
3308 | closed | closed | closed | closed | closed | closed
3309 | closed | closed | closed | closed | closed | closed
3401 | closed | closed | closed | closed | closed | closed
3402 | closed | closed | closed | closed | closed | closed
3403 | closed | closed | closed | closed | closed | closed
3404 | closed | closed | closed | closed | closed | closed
3405 | closed | closed | closed | closed | closed | closed
3406 | closed | closed | closed | closed | closed | closed
3407 | closed | closed | closed | closed | closed | closed
3408 | closed | closed | closed | closed | closed | closed
3409 | closed | closed | closed | closed | closed | closed
3410 | closed | closed | closed | closed | closed | closed
3501 | closed | closed | closed | closed | closed | closed
3502 | closed | closed | closed | closed | closed | closed
3503 | closed | closed | closed | closed | closed | closed
3504 | closed | closed | closed | closed | closed | closed
3505 | closed | closed | closed | closed | closed | closed
3506 | closed | closed | closed | closed | closed | closed
3507 | closed | closed | closed | closed | closed | closed
3508 | closed | closed | closed | closed | closed | closed
3509 | closed | closed | closed | closed | closed | closed
3601 | closed | closed | closed | closed | closed | closed
3602 | closed | closed | closed | closed | closed | closed
3603 | closed | closed | closed | closed | closed | closed
3604 | closed | closed | closed | closed | closed | closed
3605 | closed | closed | closed | closed | closed | closed
3606 | closed | closed | closed | closed | closed | closed
3607 | closed | closed | closed | closed | closed | closed
3608 | closed | closed | closed | closed | closed | closed
3609 | closed | closed | closed | closed | closed | closed
3610 | closed | closed | closed | closed | closed | closed
3701 | closed | closed | closed | closed | closed | closed
3702 | closed | closed | closed | closed | closed | closed
3703 | closed | closed | closed | closed | closed | closed
3704 | closed | closed | closed | closed | closed | closed
3705 | closed | closed | closed | closed | closed | closed
3706 | closed | closed | closed | closed | closed | closed
3707 | closed | closed | closed | closed | closed | closed
3708 | closed | closed | closed | closed | closed | closed
3709 | closed | closed | closed | closed | closed | closed

## ELV WIRS
WIR Ref. No. | # ID | Level/ Apartment | Description | PlanGrid Link | STUTES | CONSULTANT COMMENT | REV - 01
WIR-WAO-EL-2957 | #2495 | Level 7,8,9,10 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartment’s 705,706,805,905,1005 | PlanGrid | APROVED
WIR-WAO-EL-2960 | #2508 | Level 29 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 2901,2902,2903,2904,2905,2906,2907,2908,2909. | PlanGrid | APROVED
WIR-WAO-EL-2961 | #2509 | Level 30 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3001,3002,3003,3004,3005,3006,3007,3008,3009,3010. | PlanGrid | APROVED
WIR-WAO-EL-2962 | #2510 | Level 31 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3101,3102,3103,3104,3105,3106,3107,3108,3109. | PlanGrid | APROVED
WIR-WAO-EL-2963 | #2511 | Level 32 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3201,3202,3203,3204,3205,3206,3207,3208,3209,3210. | PlanGrid | APROVED
WIR-WAO-EL-2964 | #2512 | Level 29 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 2903,2904,2905,2906,2907,2908,2909. | PlanGrid | APROVED
WIR-WAO-EL-2965 | #2513 | Level 30 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3001,3002,3003,3004,3005,3006,3007,3009,3009,3010. | PlanGrid | APROVED
WIR-WAO-EL-2966 | #2514 | Level 29 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 2901,2902,2903,2904,2905,2906,2907,2908,2909,2909. | PlanGrid | APROVED
WIR-WAO-EL-2967 | #2516 | Level 30 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 3001,3002,3003,3004,3005,3006,3007,3008,3009,3009,3010. | PlanGrid | APROVED
WIR-WAO-EL-2976 | #2587 | Level 20 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 2001,2002,2003,2005,2006,2007,2008,2009,2010. | PlanGrid | APROVED
WIR-WAO-EL-2977 | #2588 | Level 31 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3101,3102,3103,3104,3105,3106,3107,3108,3109,3109. | PlanGrid | APROVED
WIR-WAO-EL-2978 | #2589 | Level 20 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 2001,2002,2003,2005,2006,2007,2008,2009. | PlanGrid | APROVED
WIR-WAO-EL-2979 | #2590 | Level 31 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 3101,3102,3103,3104,3105,3106,3107,3108,3109. | PlanGrid | APROVED
WIR-WAO-EL-2983 | #2601 | Level 32 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 3201,3202,3203,3204,3205,3206,3207,3208,3209,3210. | PlanGrid | APROVED
WIR-WAO-EL-2984 | #2608 | Level 32 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3201,3202,3203,3204,3205,3206,3207,3208,3209,3209,3210. | PlanGrid | APROVED
WIR-WAO-EL-2985 | #2609 | Level 33 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 3301,3302,3303,3304,3305,3306,3307,3308,3309 | PlanGrid | APROVED
WIR-WAO-EL-2986 | #2610 | Level 04 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 401,402,403,404,405,406,407,408,409,410,411,412. | PlanGrid | APROVED
WIR-WAO-EL-2987 | #2611 | Level 04 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 401,402,403,404,405,406,407,408,409,410,411,412. | PlanGrid | APROVED
WIR-WAO-EL-2988 | #2612 | Level 33 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3301,3302,3303,3304,3305,3306,3307,3308,3309 | PlanGrid | APROVED
WIR-WAO-EL-2989 | #2613 | Level 04 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 401,402,403,404,405,406,407,408,409,410,411,412. | PlanGrid | APROVED
WIR-WAO-EL-2990 | #2614 | Level 33 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 3301,3302,3303,3304,3305,3306,3307,3308,3309. | PlanGrid | APROVED
WIR-WAO-EL-2991 | #2632 | Level 34 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3401,3402,3403,3404,3405,3406,3407,3408,3409,3410. | PlanGrid | APROVED
WIR-WAO-EL-2992 | #2633 | Level 35 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3501,3502,3503,3504,3505,3506,3507,3508,3509. | PlanGrid | APROVED
WIR-WAO-EL-2993 | #2634 | Level 36 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3601,3602,3603,3604,3605,3606,3607,3608,3609,3610. | PlanGrid | APROVED
WIR-WAO-EL-2994 | #2635 | Level 34 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3401,3402,3403,3404,3405,3406,3407,3408,3409,3410. | PlanGrid | APROVED
WIR-WAO-EL-2997 | #2648 | Level 34 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 3401,3402,3403,3404,3405,3406,3407,3408,3409,3410. | PlanGrid | APROVED
WIR-WAO-EL-3001 | #2680 | Level 29 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 2901,2902. | PlanGrid | APROVED
WIR-WAO-EL-3002 | #2681 | Level 35 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 3501,3502,3503,3504,3505,3506,3507,3508,3509. | PlanGrid | APROVED
WIR-WAO-EL-3003 | #2682 | Level 35 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3501,3502,3503,3504,3505,3506,3507,3508,3509. | PlanGrid | APROVED
WIR-WAO-EL-3014 | #2701 | Level 5 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 5. As per the attached schematic drawing and checklist, Test report. | PlanGrid | NOT APROVED
WIR-WAO-EL-3014 | #63 | Level GF to 06 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PlanGrid | NOT APROVED
WIR-WAO-EL-3014 | #64 | Level GF to 06 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PlanGrid | IN PROCESS
WIR-WAO-EL-3016 | #2703 | Level 7 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartment -705. | PlanGrid | APROVED
WIR-WAO-EL-3023 | #2723 | Level 37 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid | APROVED
WIR-WAO-EL-3024 | #2724 | Level 37 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid | APROVED
WIR-WAO-EL-3025 | #2725 | Level 36 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 3601,3602,3603,3604,3605,3606,3607,3608,3609,3610. | PlanGrid | APROVED
WIR-WAO-EL-3026 | #2726 | Level 37 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid | APROVED
WIR-WAO-EL-3027 | #2727 | Level 02 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 201,202,203,204,205,206,207,208,209,210,211,212. | PlanGrid | APROVED
WIR-WAO-EL-3028 | #2738 | Level 36 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 3601,3602,3603,3604,3605,3606,3607,3608,3609. | PlanGrid | APROVED
WIR-WAO-EL-3035 | #2762 | All Level | Witnessing of Final Testing and Commission of Fire Alarm System as per the attached reports. | PlanGrid | NOT APROVED | Site not ready for inspection | APROVED
WIR-WAO-EL-3039 | #2784 | Level 05 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 501,502,506,507. | PlanGrid | APROVED
WIR-WAO-EL-3040 | #2799 | Level 05 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 501,502,503,504,505,506,507,508,509,510,511,512. | PlanGrid | REJECT | Site not ready for inspection | APROVED
WIR-WAO-EL-3041 | #2813 | Level 36 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartment. 3610. | PlanGrid | APROVED
WIR-WAO-EL-3042 | #2814 | Level 05 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 508,509,510,511,512. TB | PlanGrid | REJECT
WIR-WAO-EL-3043 | #2815 | Level 01 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 108,109,110,111,112. | PlanGrid | APROVED
WIR-WAO-EL-3044 | #2816 | Level 01 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 108,109,110,111,112.TB | PlanGrid | APROVED
WIR-WAO-EL-3045 | #2817 | Level 03 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 301,302,303,304,305,306,307,308,309,310,311,312. | PlanGrid | APROVED
WIR-WAO-EL-3047 | #2834 | Level 05 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 503,504,505,508,509,510,511,512. | PlanGrid | APROVED
WIR-WAO-EL-3048 | #2843 | Level 03 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 301,302,303,304,305,306,307,308,309,310,311,312. TA & TB | PlanGrid | APROVED
WIR-WAO-EL-3049 | #2844 | Level 02 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 201,202,203,204,205,206,207,208,209,210,211,212. TA & TB | PlanGrid | APROVED
WIR-WAO-EL-3051 | #2849 | Level 6 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 605,607 | PlanGrid | APROVED
WIR-WAO-EL-3064 | #2917 | Level 3 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 301,302,303,304,305,306,307,308,309,310,311,312. | PlanGrid | IN PROCESS
WIR-WAO-EL-3065 | #65 | All Level | Installation of Witnessing for the Testing & commission for INTERCOM. TA & TB -ALL FLOORS As per the attached schematic drawing and checklist, Test report. | PlanGrid | IN PROCESS

## DRAFT
wir | id | lev | de | li
WIR-WAO-EL-3027 | #2727 | Level 02 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 201,202,203,204,205,206,207,208,209,210,211,212. | PlanGrid
WIR-WAO-EL-3039 | #2784 | Level 05 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 501,502,506,507. | PlanGrid
WIR-WAO-EL-3025 | #2725 | Level 36 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 3601,3602,3603,3604,3605,3606,3607,3608,3609,3610. | PlanGrid
WIR-WAO-EL-3028 | #2738 | Level 36 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 3601,3602,3603,3604,3605,3606,3607,3608,3609. | PlanGrid
WIR-WAO-EL-3026 | #2726 | Level 37 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid
WIR-WAO-EL-3023 | #2723 | Level 37 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid
WIR-WAO-EL-3024 | #2724 | Level 37 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 3701,3702,3703,3704,3705,3706,3707,3708,3709. | PlanGrid
wir | id | lev | de | li
WIR-WAO-EL-3040 | #2799 | Level 05 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments. 501,502,503,504,505,506,507,508,509,510,511,512. | PlanGrid
WIR-WAO-EL-3041 | #2813 | Level 36 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartment. 3610. | PlanGrid
WIR-WAO-EL-3042 | #2814 | Level 05 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 508,509,510,511,512. | PlanGrid
WIR-WAO-EL-3043 | #2815 | Level 01 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 108,109,110,111,112. | PlanGrid
WIR-WAO-EL-3044 | #2816 | Level 01 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 108,109,110,111,112. | PlanGrid
WIR-WAO-EL-3045 | #2817 | Level 03 | Inspection request for witnessing for functionality of video intercom. As per the attached Schematic drawing & Test reports. Apartments 301,302,303,304,305,306,307,308,309,310,311,312. | PlanGrid
WIR-WAO-EL-3047 | #2834 | Level 05 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 503,504,505,508,509,510,511,512. | PlanGrid
WIR-WAO-EL-3048 | #2843 | Level 03 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 301,302,303,304,305,306,307,308,309,310,311,312. | PlanGrid
WIR-WAO-EL-3049 | #2844 | Level 02 | Inspection of LPG Gas detector & FAS integration testing of the following apartments. 201,202,203,204,205,206,207,208,209,210,211,212. | PlanGrid
WIR-WAO-EL-3051 | #2849 | Level 6 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 605,607 | PlanGrid
WIR-WAO-EL-3014 | #63 | Level GF to 06 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PlanGrid
WIR-WAO-EL-3014 | #64#95 | Level GF to 06 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PlanGrid
WIR-WAO-EL-3065 | #65#96 | All Level | Installation of Witnessing for the Testing & commission for INTERCOM. TA & TB -ALL FLOORS As per the attached schematic drawing and checklist, Test report. | PlanGrid
WIR-WAO-EL-3082 | #75#97 | All Level | Inspection request for Witnessing of Central battery system as per attached shop drawings and Lux report. | PlanGrid
MIR-WAO-EL-112 | #13582 | N/A | Material inspection request for ANPR System-4 Camera Server & CCTV & BTB Surveillance HDD as per attached DO No. BTS-DL-351,352. | PlanGrid
WIR-WAO-EL-3094 | #2982 | Level 8,10,14,16 | Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 809,1009,1409,1609. | PlanGrid
WIR-WAO-EL-3035 Rev 01 | #2762#99 | All Level | Witnessing of Final Testing and Commission of Fire Alarm System as per the attached reports. | PlanGrid
WIR-WAO-EL-3065 | #65#96 | All Level | Installation of Witnessing for the Testing & commission for INTERCOM. TA & TB -ALL FLOORS As per the attached schematic drawing and checklist, Test report. | PlanGrid
WIR-WAO-EL-3014 Rev 02 | #64#95#102 | Level GF to 06 | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PlanGrid
WIR-WAO-EL-3096 | #105 | All Levels | Inspection request for Witnessing of T&C of Lighting and Control system as per shop drawings. | PlanGrid

## INFORMETION
STAMP INFORMATION FOR ELV
SHEET NAME | STAMP | DOCUMENT | COMMENTS
(3FIN | Q1 BOOSTER (GSM) |  | Manuel Rebera : Antenna installation competed. Activation will be done by DU RFS Team after the BCC handing over.
(3FIN | Q3 BOOSTER (GSM) |  | Manuel Rebera : Antenna installation competed. Activation will be done by DU RFS Team after the BCC handing over.
(6T&C - UNIT AREA | C2 LPG |  | LPG functionality kitchen detector and solenoid valve functionality test completed with fire alarm integration. Approved WIR and photos attached for
(6T&C - UNIT AREA | D2 ONU DATA |  | Fluke Test for Cat 6 cable work is completed, approved WIR copy attached for reference.
(6T&C - UNIT AREA | D4 INTERCOM |  | Intercom T&C Completed, WIR attached for reference.
(6T&C - UNIT AREA | D7 BOOSTER (GSM) |  | Manuel Rebera : GSM- Antenna and cable installation completed. Completed GSM cable pulling as per the Du design drawing and T&C will be done as a system completely one time in coordination with GSM service provider Du.
(6T&C - UNIT AREA | F2 FIRE ALARM |  | FAS loop test was completed and approved WIR has been attached for reference.
(6T&C - UNIT AREA | F3 FIRE ALARM |  | FAS loop test was completed and approved WIR has been attached for reference.
NOTE : Please ignore the previous comment.
(6T&C - COMMON AREA | J3 BOOSTER (GSM) |  | Manuel Rebera : GSM- Antenna and cable installation completed. Completed GSM cable pulling as per the Du design drawing and T&C will be done as a system completely one time in coordination with GSM service provider Du.
(6T&C - COMMON AREA | K2 FIRE ALARM |  | FAS loop test was completed and approved WIR has been attached for reference.
(6T&C - COMMON AREA | K3 FIRE ALARM |  | FAS loop test was completed and approved WIR has been attached for reference.
(6T&C - Specialist system | FIRE ALARM
CBS
ACS
T&C - WIR INFORMATIONS
STAMP & Description | ATTACHMENT | STAMP & Description | ATTACHMENT
( C2 LPG) - Inspection of LPG Gas detector & FAS integration testing of the following apartments. 108,109,110,111,112. | Cable pulling WIR | (D4 INTERCOM ) - Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments. 201,202,203,204,205,206,207,208,209 | Cable pulling WIR
| Checklist |  | Checklist
| Schematic |  | Intercom Schematic
| PANEL photos |  | Device Certificate
| Device photos |  | Intercom IP Details
(D2 ONU DATA)-Inspection request for Witnessing of T&C of Cat 6 Cables for Structured Cabling System as per the attached drawing and Test reports. (FLUKE TEST) Apartments 1401,1402,1403,1404,. | Checklist | ( F2 FIRE ALARM) - Inspection request for the witnessing of Fire Alarm loop test (FACP-01)- Loop 1, Loop 2, Loop 3, Loop 4, Level 8 to Level 14 as per attached drawing. | DATA SHEET REPORT
| Device Certificate |  | Cable pulling WIR
| Telecom SCHEMATIC |  | Device photos
| SHOP DRAWING |  | Checklist
Schematic
SHOP DRAWING
FINAL ELV -INSPECTION WIR DOCUMENTS AND STAMPS
SHEET NAME | SYSTEM | Description
(6T&C - Specialist system | ACS | Installation of Witnessing for the Testing & commission for Access control system. TA & TB GF to Level 6 As per the attached schematic drawing and checklist, Test report. | PHOTOS, SCHEMATIC- DRAWING,CHECKLIST , METHOD OF STATEMENTS, SUBMITTALS,SHOP DRAWING WITH LEVEL , IP ADDRESS EXCEL SHEETS,
(6T&C - Specialist system | INTERCOM | Installation of Witnessing for the Testing & commission for INTERCOM. TA & TB -ALL FLOORS As per the attached schematic drawing and checklist, Test report. | PHOTOS, SCHEMATIC- DRAWING,CHECKLIST , METHOD OF STATEMENTS, SUBMITTALS,SHOP DRAWING WITH LEVEL , IP ADDRESS EXCEL SHEETS,
(6T&C - Specialist system | CBS | Inspection request for Witnessing of Central battery system as per attached shop drawings and Lux report. | PHOTOS, SCHEMATIC- DRAWING,CHECKLIST , METHOD OF STATEMENTS, SUBMITTALS,SHOP DRAWING WITH LEVEL , LUX EXCEL SHEETS REPORT,
(6T&C - Specialist system | FIRE ALARM
(6T&C - Specialist system | BGM
(6T&C - Specialist system | CCTV
(6T&C - Specialist system | LCP PROGRAMING

## MANPOWER
ELV MANPOWER LIST
S.N. | EMP NO | NAME | D.O.J | TRADE | TR | remark
1 | C31241 | Harikesh Yadav Ramdayal Yadav | 2024-05-15 | Electrician | JEBAL ALI -03 | Fire Alarm Trouble Shooting
2 | C31847 | MD Tavish MD Afjal | 2024-05-27 | Electrician | JEBAL ALI -01 | Fire Alarm Trouble Shooting
3 | C32063 | Nijamuddin Zamil Khan | 2024-06-05 | Electrician | JEBAL ALI -01 | CBS Trouble Shooting
4 | C31233 | Santosh Kumar Baliram | 2024-05-15 | Electrician | JEBAL ALI -03 | CBS Trouble Shooting
5 | C60216 | Sudhakar Rajbhar Uday Raj Rajbhar | 2025-01-03 | Electrician | DIP -01 | KeepOut Apt & Corridor
6 | C21801 | Md Arif Md Ali | 2023-12-02 | Electrician | Al Ruwayyah | KeepOut Apt & Corridor
7 | C26806 | Diwakar Verma | 2023-12-02 | Electrician- CH | AL Quoz | Plangrid & site work

## FAS RESPONSE
| CONSULTANT COMMENTS | REPLY TO COMMENTS
1 | Functionality of doors shall be rechecked (Refer video) | Done. | Completed.
2 | Shall be coordinated with civil for door closure as some doors not closing | Noted.
3 | Amenity areas lock termination shall be done properly | Noted | Noted
4 | As agreed earlier, outdoor IP rated device not installed | Done.
Atteched
Done